## Slide 1: Enabling Research Projects 2021-2023(4) Area of Technology & Systems Project Board Tokamak
Denis Kalupin

## Slide 2: Nature of EnR projects
EnR projects should be sufficiently distinct from the work to be carried-out in the main WPs including the Theory, Simulation, Verification and Validation (TSVV) tasks linked to the WPs.
EnR projects must show novel elements compared to the WP or TSVV tasks (i.e., a new fusion-relevant scientific or technological idea to be tested within ENR, a new method to be developed or taken for the first time into use for fusion).
Projects are proposed as packages including: the scientific planning, the team and resources.
The selection is done on the basis of scientific
excellence, relevance, state-of-the-art and
innovation by the dedicated Scientific Board.
SB Enabling Research Technology and Systems
Stéphane Heuraux (CEA-04-UL)
Iván Fernández Berceruelo (CIEMAT)
Søren Bang Korsholm (DTU)
Giuseppe Mazzone (ENEA)
Wolfgang Biel (FZJ)
Jakub Bielecki (IPPLM-07-IFJ PAN)
Igor Girka (KIPT)
Manfred Thumm (KIT)
Hans-Jürgen Hartfuss (MPG)
Konstantina Mergia (NCSRD)

## Slide 3: Roles and Responsibilities
Stakeholder acronym | Stakeholder description | Details, main role and responsibilities
PI | Principal Investigator | PIs are responsible for the organization and implementation of activities within their projects, following the recommendation of the Scientific Board and after approval of the General Assembly.
PMU | Fusion Science Department within EUROfusion PMU | The role of the PMU-FSD is to support the formal implementation of ENR activities, to control the use of resources according to the Work Programme and to provide the overall monitoring of project execution
SB | Scientific Board – Technology and Systems (appointed by the Programme Manager) | The role of the Scientific Board is to select EnR project proposals, following the principle of scientific excellence and the EUROfusion programmatic objectives. The SB will ensure continued quality by overseeing the implementation of activities on a regular basis and, if necessary, providing corrections to the project scope.
PB | Project Board – Tokamak (appointed by the Programme Manager) | The Project Board supports the PIs in their efforts on the basis of SB-TEC recommendations, approves the revision of resources and annual work programme of WP EnR (Technology & Systems area), and resolves possible conflicts between stakeholders.

## Slide 4: Selection of EnR project proposals
Lead Beneficiary | Principal Investigator | Title
Technology & Systems (CfP-FSD-AWP21-ENR-04), project proposal(s): |  | 
DIFFER | Matthijs van Berkel | Multivariable feedback control of radiative loss-processes using multi-spectral imaging
IPPLM | Marek Scholz | Development of GEM detector as a compact neutron spectrometer for fusion plasmas
IST | Filipe Da Silva | Advances in real-time reflectometry plasma tracking for next generation machines: Application to DEMO
KIT | Ioannis Pagonakis | New generation of megawatt-class fusion gyrotron systems based on highly efficient operation at the second harmonic of the cyclotron frequency
MPG | Dmitry Moseev | Reconstruction of 4D and 5D fast-ion phase space distribution functions in tokamaks and stellarators
VTT | Antti Salmi | Silicon photonics steady-state magnetic field sensor
On the 3rd of March 2021, following proposal ranking by Scientific Boards and the recommendation letter by the Programme Manager the General Assembly has endorsed funding for 16 EnR projects distributed over four areas, including 6 EnR-TEC projects:

## Slide 5: Formal arrangements
Project start: 1 July 2021 as latest
The end date will be adjusted accordingly, so the total duration of the project is not affected
Adjustment of proposals and IMS implementation is ready, including:
revision of task specifications and deliverables according to calendar year;
correction of resources (within the project budget);
updates to the team (e.g. filled open positions);
for some projects clarifications on UKAEA staff involvement
2021
2022
2023
2021
2022
2023
2024
proposal
calendar
Project Execution Plan:
Provides high level overview;
Details on individual projects are available at annexes;
All 2021 documents are available @ http://idm.euro-fusion.org/?uid=2PBJ7R

## Slide 6: Work Breakdown Structure
WBS of the WP EnR follows the area / project structure
New call for project proposals is expected in 2023, until then some parts of WBS will stay not allocated

## Slide 7: Project Life cycle
Individual project KoM(s) are organized by PIs in March-June 2021
The monitoring meetings with ENR PIs and the SB will be organised once a year (prov. in Dec.). Before the meeting, PIs must provide the annual report that will be assessed by the SB and the PMU.
At the end of the second year the mid. term review of projects will be done by SBs

## Slide 8: Reporting
All ENR project PIs must submit the annual progress reports on achievement of project deliverables (template and submission instructions will be provided by the PMU) and the final report.
The reports should be as brief and clear as possible, referring to publications and other information for details. However there should be enough information to support statements that deliverables have been achieved.
The SB EnR-TEC will asses the reports and will provide recommendations on the revision of the annual work programme to PB-Tokamak for approval.

## Slide 9: Communications
IMS – information (financial) management
The contractual information for all ENR projects will maintained in https://IMS.euro-fusion.org.
PIs will get access to their project area (implemented under the WP EnR) and must maintain Task and Deliverable description. PMU (in consultation with PIs) will maintain the financial planning of the project in IMS.
IMS must be also used to manage all the missions by the project participants.
IDM – document management
The contractual documents (e.g. Task Agreement) and reporting is to be done through https://IDM.euro-fusion.org.
PIs will get access to the stored documents and the possibility to upload reports.
All systems are linked to the EUROfusion Active Directory (AD) and share user credentials, but the access must be authorized separately.

## Slide 10: Communications
WIKI pages – project working area
All ENR projects will maintain a Wiki page accessible to all EUROfusion members (same as e.g., WPs or TF Wikis) which documents the team, deliverables, scope, meetings, results, links with various WPs, use of experimental data, reports, publications.
https://wiki.euro-fusion.org/wiki/WPENR_wikipages:_Enabling_Research_Work_Package
INDICO – meetings & presentations
All ENR projects will receive a dedicated space at https://indico.euro-fusion.org/category/212/.These must be used to organise meetings and store meeting materials. Principal Investigators are given the management right to the INDICO category (folder) dedicated to their project. Please note that, any materials uploaded to the EUROfusion INDICO system will remain there for the entire Horizon Europe framework (at least).

## Slide 11: Questions / Comments / Suggestions
Thank you!