## Slide 1: Enabling Research Projects 2021-2023(4) Areas of Inertial Fusion Energy and Theory & Modelling Project Board Theory (2/2021)
Denis Kalupin

## Slide 2: EnR projects
On the 3rd of March 2021, following proposal ranking by Scientific Boards and the recommendation letter by the Programme Manager the General Assembly has endorsed funding for 16 EnR projects distributed over four areas, including 1 EnR-IFE and 4 EnR-MOD projects:
Project Reference | Principal Investigator | Title
Inertial Fusion project(s): |  | 
CEA | Dimitri Batani | Advancing shock ignition for direct-drive inertial fusion
Theory & Modelling project(s): |  | 
EPFL | Jonathan Graves | Operation limiting plasma instabilities in high performance tokamaks: fundamental understanding and solutions for critical problems
FZJ | Sven Wiesen | Development of machine learning methods and integration of surrogate model predictor schemes for plasma-exhaust and PWI in fusion
IST | Rogerio Jorge | Energetic particle optimization of stellarator devices using near-axis magnetic fields
MPG | Philipp Lauber | Advanced energetic particle transport models (ATEP)

## Slide 3: Work Breakdown Structure
3 x ENR-MOD + 1 x ENR-IFE projects are started and running smoothly
ENR-MOD.IST project (2yrs) was agreed to start in Jan.2022
Meanwhile all projects have reported minor personnel revisions.
Waiting for formal arrangements (Task Agreements)

## Slide 4: Project Life cycle
Monitoring meetings by the SB
During the meeting Principal Investigators must:
present 2021 activities and their status;
give the forecast regarding achievement of Scientific Deliverables foreseen for 2021; and
report any modifications/changes to the project required in 2022.
The Scientific Board must:
provide remarks regarding 2021 progress, which must be taken into account by PIs when submitting the intermediate report on project achievements; and
recommend corrections to 2022 work programme following the requests by PIs.
4th E-TASC SB (Monitoring of ENR-MOD 2021 activities) 26.11.2021 https://indico.euro-fusion.org/event/1355/
2nd SB.ENR-IFE (Monitoring of 2021 activities)
9.11.2021 https://indico.euro-fusion.org/event/1352/
At the end of 2022 the Mid-term Review of projects will be done by SBs