## Slide 1: TSVV3 – Regular advancement meeting 06/10/2021 – Task 2: sheath boundary conditions Project news
P. Tamain

## Slide 2: Today’s meeting agenda

## Slide 3: Scientific Board meeting 29/09 (1)
  P. Tamain presented progress report at Scientific Board
    No specific question or remark on project orientation / progress
  Key news:
    Support for mobility will increase in 2022, but no official number yet
    Report for 2021 requested for 31/12/2021 but several PIs requested some flexibility following late start of project. SB promises flexibility on achievement of milestones but report should be delivered on time
      Need to plan global project meeting for ~ end of November

## Slide 4: Scientific Board meeting 29/09 (2)
  Long discussion on 2 practical points:
    IMAS-ification: with drop of available resources, ACH proposes to only support implementation in codes (ticketing system) made by code developers
      Acknowledged this will slow-down process
      We should work upstream on identification of key data structures needed for output in our codes => e-mail before next week
    Code progress monitoring: many discussions on exact purpose of it and criteria
      Temptation to add more criteria (e.g., coding standards, compiler compliance…)
      No official decision made but might evolve in the near future

## Slide 5: Update: Gitlab on Gateway
  Correction: after interaction with ACH IPPLM, Gateway’s Gitlab not yet open to non ITM/IMAS-related projects
  Nevertheless, opening an account on the Gateway remains necessary for interaction with ACH on IMAS-ification
    Procedure to open account: https://wiki.eufus.eu/doku.php

## Slide 6: Marconi reporting and call
  Report for 4th cycle of Marconi-Fusion submitted
    Will be made available on the Wiki
  Call for proposals for next cycle out
    EUROfusion deadline: Friday November 19th
    Suggest to prepare task by task => rely on task ROs to gather needs for each task by 05/11
    E-mail will be sent after this meeting

## Slide 7: Latest publications
Reduced turbulence model applied in 2D mean-field simulations W Dekeyser et al : 5th October 2021 ¦ DocumentID : 30660 : A self-consistent k-model for anomalous transport due to electrostatic ExB drift turbulence in the scrape-off layer and implementation in SOLPS-ITER Conference : The 18th International Workshop on Plasma Edge Theory in Fusion Devices (PET21), Lausanne, Switzerland, 13th September 2021. Co-authors : R. Coosemans, S. Carli, M. Baelmans P-adaptivity in HDG edge plasma code G Piraccini et al : 1st October 2021 ¦ DocumentID : 30639 : Spatial adaptivity in SOLEDGE3X-HDG for edge plasma simulations in versatile magnetic and reactor geometries Journal : Contributions to Plasma Physics, . Co-authors : F. Schwander, E. Serre, G. Giorgiani, M. Scotto D’Abusco Kinetic neutrals in SOLEDGE3X 2D simulations for ITER N. RIVALS et al : 29th September 2021 ¦ DocumentID : 30617 : SOLEDGE3X full vessel plasma simulations for computation of ITER first-wall fluxes Conference : The 18th International Workshop on Plasma Edge Theory in Fusion Devices (PET21), Lausanne, Switzerland, 13th September 2021. Co-authors : P. Tamain, Y. Marandet, X. Bonnin, H. Bufferand, R. A. Pitts, G. Falchetto, H. Yang, G. Ciraolo

## Slide 8: Upcoming deliverables
Reference | Title | What exactly? | Who? | Due date
D3.1 | Implementation and generalization of RANS transport models and related BCs in edge codes | a) One-equation k model in EBC/SOLEDGE3X | KUL, CEA | déc-21
 |  | b) Basic two-equation k-ε/ζ models in SOLEDGE3X/SOLPS-ITER |  | déc-21
D4.1 | Report on performance evaluation and gain in each supported code | Flash report on performance evaluation and gains | Codes’ ROs with ACH | déc-21
D5.1 | Implement fluid neutrals models derived in TSVV5 in existing turbulence codes (SOLEDGE3X, EBC, FELTOR) | Turbulence codes with fluid neutrals model embedded | CEA, KUL, DTU | déc-21
D9.1 | Create publicly accessible git repositories for all contributing codes and setup continuous integration environment | Git repositories wit CI environment for each partner code | All partners | déc-21
Remarks:
D4.1: scope of report reduced following compression of ACH support => profiling report
D9.1: full deployment of CI/CD delayed by compression of ACH support => report on advancement

## Slide 9: Today’s meeting agenda