## Team Members
Name | Role | Organisation
Chris Rowley | Project Lead Engineer | UKAEA
Dan Scoon | Project Manager | UKAEA
Luke Norman | Assistant Project Manager | UKAEA
Anna Widdowson | Errosion & Diposition Group Leader | UKAEA
Mikhail Maslov | Diagnostic Physicist (Laser SME) | UKAEA
Ionut Jepu | Tokomak Physicist (RGA SME) | UKAEA
Miroslaw Zlobinski | Project Leader | Juelich
Horst Toni Lambertz | IT & Control Specialist | Juelich
Gennady Sergienko | Optical Design Specialist | Juelich
Alexis Terra | Engineer | Juelich
Jannis Oelmann | Scientist | Juelich
Xi Jiang | Scientist | Juelich
Alexander Huber | Deputy Project Leader (JET SME) | Juelich

## Actions
ID | Task | Responsible | Due Date | Status | Comments
1 | Distribute boundary diagram for team review | CR | 2020-03-12 | C | Sent 12/03/2020
2 | Review the control strategy for an existing diagnostics laser | CR/MM | post restart | OH | Delayed due to site closure.
3 | Prepare schedule of activities required if fibre laser technology was chosen and identify project risks involved | MZ | 2020-03-20 | Y
4 | Perform Zemax analysis on beampath to confirm maximum acceptable divergence and required beam quality | GS | 2020-03-27 | Y | Requires CAD for Zemax model setup. Delayed by missing CAD.
5 | SME discussion on details of pyrometry/spectrometry for laser spot temperature measurement. Present conclusion to ETM | MZ/GS/AH/MM | 2020-03-30 | C | Reviewed topic in 30/3/20 ETM
6 | Investigate radiation hardened fibres in Torus Hall for potential use in laser spot temperature measurement during D-T campaign | MM | 2020-03-30 | C | Presented in 30/3/20 ETM
7 | Develop case for need for active laser spot temperature measurement during D-T campaign | MZ | 2020-03-30 | C | Need to demonstrate temperature measurement during commissioning only or during D-D campaign only is not sufficient for predicting laser spot temperature during D-T campaign. What level of tolerance is required on laser spot temperature control? Can a model for laser spot temperature be built during D-D campaign to provide sufficient accuracy of laser spot temperature prediction during D-T campaign that it doesn't need measuring directly. Presented in 30/3/20 ETM
8 | Check whether errors arise on second CATIA assembly sent | MZ/AT | 2020-03-17 | C | If they are then UKAEA technical support will be escalated Second version worked much better. Report provided detailing missing CAD, being looked in to, see #12
9 | Prepare list of parts for which drawings are required | MZ | 2020-03-24 | C | Confirmed in 30/3/20 ETM that list is as per powerpoint previously e-mailed.
10 | Review Boundary Diagram and send feedback to CR | All | 2020-03-17 | Y
11 | Set up Doodle for regular meeting time | CR | 2020-03-12 | C
12 | Arrange for CAD Designer to review CATIA feedback RE missing CAD | CR | 2020-03-20 | Y | Further CAD provided for missing items between window and tile. CAD Designer reassigned as priority to EDS, to continue once available.
13 | Confirm whetehr water cooling can be realised in KZ3 enclosure | CR/MM | 2020-03-20 | C | Confirmed water circuits are self contained for lasers. All existing lasers are water cooled.
14 | Investigate beam shaping requirements for beampath | GS | 2020-04-06 | G
15 | Confirm diameter of available fibre optics | MM | post restart | OH | Needs onsite investigation
16 | Confirm existing fibres can be routed to KE9 frame | MM | post restart | OH | Low priority, assumed they will
17 | Check sensitivity and emissivity of fibres at 1600nm | MM | post restart | OH | Will need a spectrometer capable to >1600nm
18 | Produce one-pager on fibre optic laser transmission to J1D lab concept | MZ/GS/AH | 2020-04-03 | G
19 | Discuss with Klaus-Dieter opportunity for fibre optics to be installed as per #18 | AW | 2020-04-10 | G | Following production of one-pager per #18
19 | Define concept level strategy for LIDs measurements | MZ | 2020-04-08 | G | To inform minimum number of targets required on the tile
19
19
19
19
19
19

## Future Meeting Topics
Proposed Item | Deliverables | Preferred date
Desorbed fuel per LIDs pulse | Discussion of concerns regarding fuel desorbtion rate as a function of plasma events Discussion of alternative options and their implications on laser design - Rastering - Larger incident spot | w/c 16/3/20
Tile concept | What will tile solution look like? Need to commence design of tile asap as is likely to require high design effort and possibly long lead time. | w/c 16/3/20

## Agenda Topics
Meeting Date | Agenda Item | Deliverables | Status | Return Date
2020-03-10 | Review system boundary diagram | Agree where system boundary lies Agree initial concept of system contents | Reviewed, controls needs more discussion RE requirements for CODAS, power supply required inside frame, document to be distributed,
2020-03-10 | Laser Selection – traditional or fibre | Discussion of merits of fibre laser Agree next steps | Presentation provided, need to establish requirements for laser power and divergence (using Zemax analysis)
2020-03-10 | Angle of incidence of laser on tile 0/1 | Confirm angle of incidence or agree plan to evaluate Confirm requirement for beam shaping Confirm requirement for polarisation | Confirmed need to complete using CAD analysis
2020-03-10 | IR Camera | Update on current JET capabilities Confirm requirements for laser spot temperature control Confirm requirements for bulk tile temperature monitoring | NB topic includes Pyrometer. In depth technical discussion on pyrometry and spectrometry. Further offline technical discussion required. Requirement for temperature measurement needs to be demonstrated. Possible use of radiation hardened fibres already in the torus hall.
2020-03-10 | CAD Model | Confirm plan to fix CATIA issues Confirm whether UKAEA should share model as a JT file | New file created for download at Juelich. Juelich to test file and see if still get errors. If still getting errors then technical support escalation at UKAEA will be requested.
2020-03-17 | Target Tile | - Initial discussions on planned approach for tile design - Interaction with deposition rate and laser spot size - Agree technical requirements for tile - Agree next steps on tile design | Presentation from Miro 'first thoughts' Tungsten thickness hsould be 4-5mm min with 2mm deep cuts based on experience on JET. Some missing CAD has stopped full analysis of laser path through windows. Initial evaluation of 60-70°, 58° from bottom window. Design work will be kicked off by UKAEA to support CAE required (EM loading, thermal analysis) [offline] preferred for W to go to edge of tile to cover high depostion area Beam shaping needs investigation
2020-03-30 | Laser Spot | -Present findings of fibre optics investigation (AW/MM) -Next steps on fibre optics | Presentation from AW/MM showing existing fibres transmit IR wavelength. High transmission at ~1000nm, transmission at 1600nm was unclear due to sensitivity of spectrometer used. Pyrometer needs minimum two differet wavelengths. Recomendation to avoid laser wavelength due to back scattering although potential opportunity to use notch filter for this. Fibre(s) are avaialble to use on LIDs (MM owner). Targetting to read spot temperature is very complex. Would be some scope to target area larger than laser spot (perhaps up to 100mm) but targetting whole tile unlikely to work due to signal strength. Existing fibres could plug in to frame. Feasibility using fibre for laser transmission discussed. Existing fibres at ~30+ years old with no details available on their spec or condition, can not easily be surveyed to assess suitability for laser transmission. Opportunity to install new fibre optics and locate laser elsewhere from roof lab. Fibre optic transmission negates high divergence, allowing for high power laser. Opportunity to be reviewed in parallel to existing prime route.
|  | -Present requirements for laser spot temperature measurement (Juelich) | MZ presented laser spot temperature presentation. Temperature response is a function of deposit layer thickness. Deposits will grow over DTE therefore surface temperature can not be modelled. Without surface temperature measurement, a minimum can be predicted but max temperature can not which could melt the Be layer with potential impact on subsequent absorption/deposition.
tbc |  | oDiscuss how fuel is desorbed as a function of temperature oDiscuss how quickly fuel must be desorbed to be measured by RGA -Discuss how to proceed if it is not possible to perform experiments planned at Easter (ablation laser firing on used tile in torus chamber) – can more dry run RGA analysis be performed? -Agree whether rastering should be planned in and/or larger laser spot size to provide sufficient desorbtion