## Slide 1: PSO training on Annual Management Cycle October 27th, 2021
Project Management Office

## Slide 2: Annual Management Cycle (AMC)
Notes: Walking through the major management steps of the Annual Management Cycle

## Slide 3: Annual Management Cycle (AMC)
1
2
3
4
5
6
7
Progress monitoring
Deliverables recording
4
4
8
9
IMS
IMS
IMS
IMS
Important notes:
The annual cycle explained through the above steps actually covers 1.5 years
In each step the major actions and the potential contribution of the PSOs are indicated

## Slide 4: Step 1 – Definition of objectives of the upcoming year
PL/TFL responsibility to define the objectives of the upcoming year
PL/TFL could decide to organize a meeting involving the WP contributors, or selected contributors
PSOs support the PL/TFL in organising the meeting, collecting and arranging the objectives
The EUROfusion HoD with the PLs/TFLs harmonises the objectives of the individual WPs to ensure the overall programmatic goals are kept in mind

## Slide 5: Step 2 – detailed planning, PMP definition
PL/TFL responsibility to plan for the upcoming year and document the planning in the PMP
PSOs support the PL/TFL in
  Maintaining the PMP consistency (5 year vs. annual)
  Compiling information following the PMP template
  Collecting required information from contributors, wherever needed
  Ensuring the indicative high level resource allocation in the PMP is within overall 5 years budget (2021 allocated in TSs, the remaining 2022-2025 still indicative)
  Handling the IDM upload of the PMP
PL/ TFL to present the PMP to the PB
PB to approve the final PMP

## Slide 6: Step 3 – Revision of IMS indicative resources
PL/TFL responsibility to revise the indicative resources according to the detailed planning, if required
PSOs support the PL/ TFL in the entire revision process of the indicative resources in parallel to the update of the PMP or after it has been completed
IMS training on revision of indicative resources

## Slide 7: Step 4 – various steps combined
PB to review and approve the PMP in IDM
PMO to extract the AWP (next year) information from the then approved PMPs and provide them to ADMIN for compilation
PL/TFL to create campaign call, if required (only guideline, not within the scope of the current meeting)
No action required from PSOs!

## Slide 8: Step 5 – GA meeting approving indicative resources
GA to review and approve the indicative resources and the AWP of the coming year that includes the data provided by the PL/TFL through the IMS and PMP
GA to approve the final resource allocation of the current year (PSOs shall ensure that all TSs are in approved status)

## Slide 9: Step 6 – Definition of Task Specifications in IMS
IMS training on the definition of Task Specifications (including resource allocation)
PL/TFL responsibility to define the task specifications in full details in IMS
PSOs support the PL/ TFL in the task specification definition in
  Initiating the tasks in IMS (“In Draft” status)
  Filling basic information (e.g. TC, DO, standard reviewers, approver)
  Filling all the required information, if the resource allocation has been planned in details outside IMS
  Ensuring that the TCs and DOs are aware of their tasks in IMS
  Following up the TSs in IMS to ensure all of them are reviewed and approved
  Ensuring the annual and overall WP budgets are maintained (inform budget-control for verification)
further info: “Task Spec. Process” 2P8CDM

## Slide 10: Step 7 – Issue of Task Agreements
After the Task Specifications are defined in IMS (resources allocated): ADMIN to issue the Task Agreements of each WPs and get them approved by the Beneficiaries
No action required from PSOs!

## Slide 11: Step 8 – Progress monitoring
PL/TFL responsible to monitor the progress of the work of the WP
PSOs support the PL/TFL in
  Collecting progress information from the contributors on the IMS deliverables level (level 3)
  Organising progress meeting(s)
  Providing progress information to the PMO, as required

## Slide 12: Step 9 – Recording the approved Deliverables in IMS
PL/TFL responsible to ensure that the deliverables in IDM are properly reviewed and approved/ rejected
PSOs support the PL/TFL in
  Coordinating the upload of the deliverables in IDM (naming convention, location) Note: e.g. placeholders for all
  Ensuring the appropriate (predefined – see next slide for details) reviewers and approver are indicated in IDM
  Enhancing the speed of the review process (reminders, etc.)
  Recording the link of the approved IDM deliverable in IMS to authorize payment
IMS training on the recording of the link of the approved IDM deliverable in IMS

## Slide 13: Step 9 – supporting slide (predefined reviewers and approver)
IDM role for Standard Deliverable | Major Actor(s) | Responsibilities of Actors
Author/ Signatory* | Selected WP member (typically Deliverable Owner in IMS TS) | Complete the Deliverable report
Co-Author(s) | Selected WP member | Support the Author in completing the Deliverable report
Reviewer(s) 1 (technical/ scientific; one or more persons)* | Selected WP members (scientific/ technical reviewers as defined in IMS TS) | Confirm technical/ scientific achievement. To be assigned according to the applicable process description (to be defined by WP Leader if not specified).
Reviewer 2 (technical/ scientific/other content) | PMU Representative** | Confirm technical/ scientific achievement from a Department programmatic point of view – if applicable
Reviewer 3 (formal)* | PSO | Confirm quality compliance (formal) – if PSO not a co-Author
Reviewer 4 (formal) | PMO | Confirm quality compliance (formal, i.e. from overall Project Management point of view) – if required
Approver* | PL/TFL | Accountable person according to the defined process (Work Package Leader or other appropriate person)
* mandatory field
** Representatives identified in a separate document: Task Specification Reviewers (Benef, PMU) (2PJP5N) For WPAC and WPENR the PMU representative acts as the PL, therefore no scientific PMU review required