## WBS Overview
WBS-Lvl.1 | WBS-Lvl.2 | WBS-Lvl.3 | Task ID | Task Name | Task Title | Task Description | Deliverable Owner | Reviewer (BEN) | Reviewer (IPP) | PMU Reviewer | Deliverable Name | Deliverable Description | Start Date | End Date | BEN | Allocated PM | Allocated AR (PM@0%) | Travel Cost (k€) | CC Travel | HR Cost | CC HR | Total CC | Task Status | BEN | Total CC | Travel CC | HR CC | Check | IMS 15.03 | Travel + HR 15.03 | Travel 15.03. | HR 15.03 | IMS 15.09 (indicativ)
2022-W7X-1: Project Management | 2022-W7X-1.1: Project Coordination | 2022-W7X-1.1.1 | 2022-W7X-1.1.1-MPG: | WP management | 2022-W7X-1.1.1-MPG: WP management | Project Management of WPW7X in 2022 (TFL/PSO) | Andreas Dinklage | Gregor Neu | - | Sara Moradi | 2022-W7X-1.1.1-MPG: Management Report | Report of management activities by Task Force Leader and Project Support Office for WPW7X. | 2022-01-01 | 2022-12-31 | MPG | 16.8 | 0 | 0 | 0 | 151.375 | 105.9625 | 105.9625 | Approved | CEA | 32.0381 | 2.583 | 29.4551 | 0 | 25.8979 | 25.8979 | 0.861 | 25.0369 | 6.1403
|  | 2022-W7X-1.1.2 | 2022-W7X-1.1.2-CIEMAT: | WP management | 2022-W7X-1.1.2-CIEMAT: WP management | Project Management of WPW7X in 2022 (DTFL) | Ivan Calvo | Enrique Ascasibar | Arturo Alonso | Sara Moradi | 2022-W7X-1.1.2-CIEMAT: Management Report | Report of management activities by Deputy Task Force Leaders for WPW7X. | 2022-01-01 | 2022-12-31 | CIEMAT | 12 | 0 | 13.86 | 12.1275 | 71.625 | 50.1375 | 62.265 | Approved | CIEMAT | 254.0753 | 55.7865 | 198.2888 | 0 | 142.5942 | 142.5942 | 14.553 | 128.0412 | 111.4811
[16 empty] | (14,9) | [7 empty] | CIEMAT@70% | 62.265 | 12.1275 | 50.1375 | 0 | 62.265 | 62.265 | 12.1275 | 50.1375 | 0
2022-W7X-2: Scientific Exploitation | 2022-W7X-2.1: W7-X Campaigns | 2022-W7X-2.1.1: Conduction of the W7-X Campaign OP2.1 | 2022-W7X-2.1.1: CEA | Participation in OP2.1 | 2022-W7X-2.1.1: CEA | t.b.d. | NN | [7 empty] | CEA | 0.92308 | 0 | 1.968 | 1.722 | 8.8365 | 4.4183 | 6.1403 | - | CIEMAT U Seville | 17.9062 | 0 | 17.9062 | 0 | 17.9062 | 17.9062 | 0 | 17.9062 | 0
|  |  | 2022-W7X-2.1.1: CIEMAT | Participation in OP2.1 | 2022-W7X-2.1.1: CIEMAT | t.b.d. | NN | [5 empty] | 2022-11-01 | 2023-03-15 | CIEMAT | 23.5385 | 0 | 47.124 | 41.2335 | 140.4952 | 70.2476 | 111.4811 | - | CIEMAT UPC | 11.9375 | 0 | 11.9375 | 0 | 11.9375 | 11.9375 | 0 | 11.9375 | 0
|  |  | 2022-W7X-2.1.1: DTU | Participation in OP2.1 | 2022-W7X-2.1.1: DTU | t.b.d. | NN | [5 empty] | 2022-11-01 | 2023-03-15 | DTU | 1.3846 | 0 | 2.898 | 2.5357 | 13.226 | 6.613 | 9.1487 | - | CIEMAT BSC | 5.9687 | 0 | 5.9687 | 0 | 5.9687 | 5.9687 | 0 | 5.9687 | 0
|  |  | 2022-W7X-2.1.1: EK-CER | Participation in OP2.1 | 2022-W7X-2.1.1: EK-CER | t.b.d. | NN | [5 empty] | 2022-11-01 | 2023-03-15 | EK-CER | 25.8462 | 20 | 70.56 | 61.74 | 79.4231 | 39.7115 | 101.4515 | - | DTU | 27.3717 | 4.2262 | 23.1454 | 0 | 18.223 | 18.223 | 1.6905 | 16.5325 | 9.1487
|  |  | 2022-W7X-2.1.1: ENEA | Participation in OP2.1 | 2022-W7X-2.1.1: ENEA | t.b.d. | NN | [5 empty] | 2022-11-01 | 2023-03-15 | ENEA | 2.7692 | 0 | 5.472 | 4.788 | 19.6731 | 9.8365 | 14.6245 | - | DTU SDU | 9.5521 | 0 | 9.5521 | 0 | 9.5521 | 9.5521 | 0 | 9.5521 | 0
|  |  | 2022-W7X-2.1.1: EPFL | Participation in OP2.1 | 2022-W7X-2.1.1: EPFL | t.b.d. | NN | [7 empty] | EPFL | - | - | - | - | - | - | - | - | EK-CER | 132.5263 | 78.2775 | 54.2488 | 0 | 31.0748 | 31.0748 | 16.5375 | 14.5373 | 101.4515
|  |  | 2022-W7X-2.1.1: FZJ | Participation in OP2.1 | 2022-W7X-2.1.1: FZJ | t.b.d. | NN | [5 empty] | 2022-11-01 | 2023-03-15 | FZJ | 29.5385 | 0 | 46.08 | 40.32 | 220.6154 | 110.3077 | 150.6277 | - | ENEA | 25.2808 | 4.788 | 20.4928 | 0 | 10.6562 | 10.6562 | 0 | 10.6562 | 14.6245
|  |  | 2022-W7X-2.1.1: IPPLM | Participation in OP2.1 | 2022-W7X-2.1.1: IPPLM | t.b.d. | NN | [5 empty] | 2022-11-01 | 2023-03-15 | IPPLM | 18.4615 | 20 | 40.56 | 35.49 | 69.4231 | 34.7115 | 70.2015 | - | ENEA RFX | 5.1698 | 0.798 | 4.3718 | 0 | 5.1698 | 5.1698 | 0.798 | 4.3718 | 0
|  |  | 2022-W7X-2.1.1: IST | Participation in OP2.1 | 2022-W7X-2.1.1: IST | t.b.d. | NN | [7 empty] | IST | - | - | - | - | - | - | - | - | ENEA UC | 10.6562 | 0 | 10.6562 | 0 | 10.6562 | 10.6562 | 0 | 10.6562 | 0
|  |  | 2022-W7X-2.1.1: KIPT | Participation in OP2.1 | 2022-W7X-2.1.1: KIPT | t.b.d. | NN | [5 empty] | 2022-11-01 | 2023-03-15 | KIPT | 5.0769 | 0 | 8.58 | 7.5075 | 4.3365 | 2.1683 | 9.6758 | - | EPFL | 22.2933 | 0 | 22.2933 | 0 | 22.2933 | 22.2933 | 0 | 22.2933 | 0
|  |  | 2022-W7X-2.1.1: KIT | Participation in OP2.1 | 2022-W7X-2.1.1: KIT | t.b.d. | NN | [7 empty] | KIT | - | - | - | - | - | - | - | - | FZJ | 429.1253 | 68.04 | 361.0853 | 0 | 278.4976 | 278.4976 | 27.72 | 250.7776 | 150.6277
|  |  | 2022-W7X-2.1.1: LPP-ERM | Participation in OP2.1 | 2022-W7X-2.1.1: LPP-ERM | t.b.d. | NN | [5 empty] | 2022-11-01 | 2023-03-15 | LPP-ERM | 16.6154 | 0 | 36.936 | 32.319 | 160.0962 | 80.0481 | 112.3671 | - | IPPLM | 137.583 | 47.9115 | 89.6715 | 0 | 67.3814 | 67.3814 | 12.4215 | 54.9599 | 70.2015
|  |  | 2022-W7X-2.1.1: MPG | Participation in OP2.1 | 2022-W7X-2.1.1: MPG | t.b.d. | NN | [7 empty] | MPG | - | - | - | - | - | - | - | - | IST | 13.592 | 4.725 | 8.867 | 0 | 13.592 | 13.592 | 4.725 | 8.867 | 0
|  |  | 2022-W7X-2.1.1: NCSRD | Participation in OP2.1 | 2022-W7X-2.1.1: NCSRD | t.b.d. | NN | [7 empty] | NCSRD | - | - | - | - | - | - | - | - | KIPT | 69.7757 | 31.2725 | 38.5032 | 0 | 60.0999 | 60.0999 | 23.765 | 36.3349 | 9.6758
|  |  | 2022-W7X-2.1.1: OEAW | Participation in OP2.1 | 2022-W7X-2.1.1: OEAW | t.b.d. | NN | [7 empty] | OEAW | - | - | - | - | - | - | - | - | KIPT KINR | 3.4167 | 0 | 3.4167 | 0 | 3.4167 | 3.4167 | 0 | 3.4167 | 0
|  |  | 2022-W7X-2.1.1: VTT | Participation in OP2.1 | 2022-W7X-2.1.1: VTT | t.b.d. | NN | [5 empty] | 2022-11-01 | 2023-03-15 | VTT | 0.92308 | 0 | 1.884 | 1.6485 | 7.3269 | 3.6635 | 5.312 | - | KIT | 160.7231 | 21.546 | 139.1771 | 0 | 160.7231 | 160.7231 | 21.546 | 139.1771 | 0
| 2022-W7X-2.2: Scientific Preparation | 2022-W7X-2.2.1: Scenario Preparation of OP2.1 | 2022-W7X-2.2.1-OEAW: | Scenario Preparation OEAW | 2022-W7X-2.2.1-OEAW: Scenario Preparation OEAW | Calculation of NEO-2 results for relevant W7-X scenarios (finite collisionality effects for ECCD/EBCD) for further analysis with TRAVIS. | Winfried Kernbichler | Lätitia Unger | Pavel Aleynikov | Sara Moradi | Report 2022-W7-X-2.2.1 OEAW | Report on the provision of NEO-2 results and handover | 2022-01-01 | 2022-12-31 | OEAW | 3 | 0 | 0 | 0 | 23.9688 | 11.9844 | 11.9844 | Review started | LPP-ERM | 268.1019 | 116.9 | 151.2019 | 0 | 155.7348 | 155.7348 | 84.581 | 71.1538 | 112.3671
|  |  | 2022-W7X-2.2.1-CIEMAT: | Scenario Preparation CIEMAT | 2022-W7X-2.2.1-CIEMAT: Scenario Preparation CIEMAT | Calculation of NBI loads, pellet/TESPEL simulations, transport simulations (bulk plasma, impurities, code validation, complementary experiments on TJ-II 8turbulence, rotation studies), development of experiment proposals for OP2.1 and participation in international collaborations | Arturo Alonso | Enrique Ascasibar | Jürgen Baldzuhn Craig Beidler Thomas Wegener Olaf Grulke | Sara Moradi | Report 2022-W7-X-2.2.1 CIEMAT | Report on scenario preparation and progress in the specified subtasks | 2022-01-01 | 2022-12-31 | CIEMAT | 10 | 0 | 0 | 0 | 59.6875 | 29.8438 | 29.8438 | Approved | MPG | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 2022-W7X-2.2.1-CIEMAT BSC: | Scenario Preparation CIEMAT BSC | 2022-W7X-2.2.1-CIEMAT BSC: Scenario Preparation CIEMAT BSC | ICRF modelling with AORSA | Mervi Mantsinnen | Enrique Ascasibar | Dirk Hartmann | Sara Moradi | Report 2022-W7-X-2.2.1 CIEMAT BSC | Report on 3D ICRH Modelling for W7-X with AORSA | 2022-01-01 | 2022-12-31 | CIEMAT BSC | 2 | 0 | 0 | 0 | 11.9375 | 5.9687 | 5.9687 | Approved | MPG 70% | 105.9625 | 0 | 105.9625 | 0 | 105.9625 | 105.9625 | 0 | 105.9625 | 0
|  |  | 2022-W7X-2.2.1-CRPP: | Scenario Preparation CRPP | 2022-W7X-2.2.1-CRPP: Scenario Preparation CRPP | Modelling of combined RF + NBI scenarios for heating and fast ion generation in W7-X | Jonathan Graves | Yves Martin | Christoph Slaby | Sara Moradi | Report 2022-W7-X-2.2.1 CRPP | Report on ICRH modelling | 2022-01-01 | 2022-12-31 | EPFL | 3.52 | 0 | 0 | 0 | 44.5867 | 22.2933 | 22.2933 | Approved | NCSRD | 14.3438 | 0 | 14.3438 | 0 | 14.3438 | 14.3438 | 0 | 14.3438 | 0
|  |  | 2022-W7X-2.2.1-FZJ: | Scenario Preparation FZJ | 2022-W7X-2.2.1-FZJ: Scenario Preparation FZJ | Edge magnetic topology effects on impurity sources, tools for spectroscopic data analysis | Olaf Neubauer | Olaf Neubauer | Marcin Jakubowksi | Sara Moradi | Report 2022-W7-X-2.2.1 FZJ | Report on scenarios with beta effects | 2022-01-01 | 2022-12-31 | FZJ | 19 | 0 | 0 | 0 | 141.9062 | 70.9531 | 70.9531 | Approved | OEAW | 11.9844 | 0 | 11.9844 | 0 | 11.9844 | 11.9844 | 0 | 11.9844 | 0
|  |  | 2022-W7X-2.2.1-IPPLM: | Scenario Preparation IPPLM | 2022-W7X-2.2.1-IPPLM: Scenario Preparation IPPLM | Preparation of impurity transport studies and long pulse operation | Tomasz Fornal | Vladimir Moiseenko | Marcin Jakubowski | Sara Moradi | Report 2022-W7-X-2.2.1 IPPLM | Report on scenrios for long pulse operation and impurity studies | 2022-01-01 | 2022-12-31 | IPPLM | 12 | 12 | 0 | 0 | 45.125 | 22.5625 | 22.5625 | Approved | VTT | 25.1557 | 1.6485 | 23.5072 | 0 | 19.8438 | 19.8438 | 0 | 19.8438 | 5.312
|  |  | 2022-W7X-2.2.1-KIPT Kiev: | Scenario Preparation KIPT - KINR | 2022-W7X-2.2.1-KIPT Kiev: Scenario Preparation KIPT - KINR | Study stochastic losse of fast particles in W7-X | Yaruslav Kolesnichenko | Vladimir Moiseenko | Axel Könies | Sara Moradi | Report 2022-W7X-2.2.1 KIPT KINR | Report on studies of stoachstic loss in W7-X | 2022-01-01 | 2022-12-31 | KIPT KINR | 8 | 0 | 0 | 0 | 6.8333 | 3.4167 | 3.4167 | Approved | 50% | 1856.8051 | 450.6303 | 1406.1749 |  | 1265.7749 |  | 221.326 | 1044.4489 | 591.0302
|  |  | 2022-W7X-2.2.1-KIPT: | Scenario Preparation KIPT | 2022-W7X-2.2.1-KIPT: Scenario Preparation KIPT | Contribute to complementary turbulence studies for W7-X on TJ-2 with HIBP | Kozachek, Alexander | Vladimir Moiseenko | Arturo Alonso | Sara Moradi | Report 2022-W7X-2.2.1 KIPT | Report on studies on HIBP studies in TJ-2 for W7-X | 2022-01-01 | 2022-12-31 | KIPT | 4 | 0 | 10 | 8.75 | 3.4167 | 1.7083 | 10.4583 | Approved |  | 1856.8051 | 1483.5229 | Spent | [5 empty] | 217.748 | unallocated in 2022
|  |  | 2022-W7X-2.2.1-VTT: | Scenario Preparation VTT | 2022-W7X-2.2.1-VTT: Scenario Preparation VTT | Conduct ASCOT simulations of NBI and ICRH ion behavior in preparation for OP2 | Kurki-Suonio, Taina | Antti Hakola | Sam Lazerson | Sara Moradi | Report 2022-W7X-2.2.1 VTT | Report on ASCOT simulation for OP2 | 2022-01-01 | 2022-10-31 | VTT | 5 | 0 | 0 | 0 | 39.6875 | 19.8438 | 19.8438 | Approved |  |  | 1436.297 | Budget |  | 1483.5229 |  |  |  | 373.2822 | unallocated in 2023
| 2022-W7X-2.3: Scientific Exploitation | 2022-W7X-2.3.1: Data Analysis and Modelling of OP2.1 and IC | 2022-W7X-2.3.1: BEN… | [9 empty] | 2022-01-01 |  | - | - | - | - | - | - | - | - | -
[26 empty] | 47.2259 | Balance due
2022-W7X-3: Support for the Exploitation and Preparation of W7-X Campaigns | 2022-W7X-3.1: Support of Enhancement Projects | 2022-W7X-3.1.1: FZJ-led Enhancement Projects | 2022-W7X-3.1.1-FZJ: | Commissioning and preparation of enhancements | 2022-W7X-3.1.1-FZJ: Commissioning and preparation of enhancements | Support for Enhancement projects and complementary actions | Olaf Neubauer | Olaf Neubauer | Ralf König | Sara Moradi | Report 2022-W7-X-3.1.1 FZJ | Report on the implementation of hardware upgrades for W7-X and synthetic diagnostic | 2022-01-01 | 2022-12-31 | FZJ | 38 | 0 | 0 | 0 | 283.8125 | 141.9062 | 141.9062 | Approved
|  |  | 2022-W7X-3.1.1-ERM: | ICRH preparation and commissioning | 2022-W7X-3.1.1-ERM: ICRH preparation and commissioning | Conduct the commissioning of the ICRH EP for W7-X | Jef Ongena | Jef Ongena | Dirk Hartmann | Sara Moradi | Report 2022-W7-X-3.1.1 ERM | Report on ICRH commissioning | 2022-01-01 | 2022-10-31 | LPP-ERM | 14.7692 | 0 | 65.664 | 57.456 | 142.3077 | 71.1538 | 128.6098 | Approved
|  | 2022-W7X-3.1.2: MPG-led Enhancement Projects | 2022-W7X-3.1.2: MPG |  | 2022-W7X-3.1.2: MPG | [9 empty] | - | - | - | - | - | - | - | - | -
|  | 2022-W7X-3.1.3: Long Term Developments | 2022-W7X-3.1.3-KIT: | Neutral gas modelling | 2022-W7X-3.1.3-KIT: Neutral gas modelling | Conduct studies of neutral gas in geomtries relevant to tungsten divertors for W7-X | Varoutis, Stylianos | Mihaela Ionescu-Bujor | Dirk Naujoks | Sara Moradi | Report 2022-W7X-3.1.3 KIT | Report on neutral gas modelling for divertor developments | 0.1.01.2022 | 2022-12-31 | KIT | 6 | 0 | 0 | 0 | 53.875 | 26.9375 | 26.9375 | Approved |  |  |  | 1406.1749 | 361.726 | 1044.4489 |  |  |  | HR (15.03.) | allocated (15.03)
|  |  | 2022-W7X-3.1.3-DTU SDU: | Divertor Design | 2022-W7X-3.1.3-DTU SDU: Divertor Design | Development of a divertor design with AI methods | Nadimi, Esmaeil S. | Stefan Kragh Nielsen | Dirk Naujoks | Sara Moradi | Report 2022-W7X-3.1.3 DTU SDU | Report on Divertor Design | 0.1.01.2022 | 2022-12-31 | DTU SDU | 2 | 0 | 0 | 0 | 19.1042 | 9.5521 | 9.5521 | Approved
| 2022-W7X-3.2: Diagnostics Developments | 2022-W7X-3.2.1: Diagnostics Preparation for W7-X Campaigns | 2022-W7X-3.2.1-CEA: | IR imaging | 2022-W7X-3.2.1-CEA: IR imaging | Development of data acquisition and processing tools w/ support actions | Michael Houry | Christel Fenzi | Aleix Puig | Sara Moradi | Report 2022-W7-X-3.2.1 CEA | Report on developments and integration of tools | 2022-01-01 | 2022-10-31 | CEA | 5.2308 | 0 | 0.984 | 0.861 | 50.0737 | 25.0369 | 25.8979 | Approved |  |  |  | 450.6303 | 241.4318 | 209.1985 |  |  |  | Travel (15.03.) | unallocated 2022 (travel outside of OP2.1) (15.03)
|  |  | 2022-W7X-3.2.1-CIEMAT: | CIEMAT E-band reflectometer and TESPEL pellets delivery | 2022-W7X-3.2.1-CIEMAT: CIEMAT E-band reflectometer and TESPEL pellets delivery | Delivery and commission of E-band Doppler reflectometer and fabrication and delivery of TESPEL pellets. | Teresa Estrada | Enrique Ascasibar | Thomas Windisch | Sara Moradi | Report 2022-W7-X-3.2.1 CIEMAT | Report on delivery and integration | 2022-03-01 | 2022-10-31 | CIEMAT | 29.1538 | 0 | 16.632 | 14.553 | 174.012 | 87.006 | 101.559 | Approved |  |  |  |  | 12.1275 | 1253.6474 |  |  |  | IMS(15.03)
|  |  | 2022-W7X-3.2.1-CIEMAT U Seville: | Fast Ion Diagnostics Developments | 2022-W7X-3.2.1-CIEMAT U Seville: Fast Ion Diagnostics Developments | Development of a detailed design for a W7-X scintillating FILD detector and Planning of component production and assembly. | Anton Jansen Van Vuuren | Enrique Ascasibar | Samuel Lazerson | Sara Moradi | Report 2022-W7-X-3.2.1 CIEMAT - U Seville | Report on detailed design and production planning | 2022-01-01 | 2022-12-31 | CIEMAT U Seville | 6 | 0 | 0 | 0 | 35.8125 | 17.9062 | 17.9062 | Approved | [5 empty] | 217.748 |  |  |  |  | unallocated (2022 part of OP2.1) (15.03)
|  |  | 2022-W7X-3.2.1-CIEMAT UPC: | IR analysis tools | 2022-W7X-3.2.1-CIEMAT UPC: IR analysis tools | Analysis of spatio-temporal events and evolution forecast in the thermal and video domains | Josep Casas | Enrique Ascasibar | Aleix Puig | Sara Moradi | Report 2022-W7-X-3.2.1 CIEMAT - UPC | Report on tools for the analysis of spatio-temporal and evolution forecasts | 2022-01-01 | 2022-12-31 | CIEMAT UPC | 4 | 0 | 0 | 0 | 23.875 | 11.9375 | 11.9375 | Approved | [5 empty] | 12.1275 |  |  |  | IMS(15.03) | Secondment
|  |  | 2022-W7X-3.2.1-DTU: | CTS diagnostics | 2022-W7X-3.2.1-DTU: CTS diagnostics | Development and commissioning of CTS diagnostic | Stefan Kragh Nielsen | Stefan Kragh Nielsen | Dimitri Moseev | Sara Moradi | Report 2022-W7-X-3.2.1 DTU | Report on the delivery and commpissiioning of the CTS diagnsotic on W7-X | 2022-01-01 | 2022-10-31 | DTU | 3.4615 | 0 | 1.932 | 1.6905 | 33.0649 | 16.5325 | 18.223 | Approved
|  |  | 2022-W7X-3.2.1-EK-CER: | AM-Beam and Video Diagnostics | 2022-W7X-3.2.1-EK-CER: AM-Beam and Video Diagnostics | Development and comissioning of AM-Beam and video diagnostics, analysis software development and accompanying analysis | Gabor Kocsis | Gabor Kocsis | Matthias Otte Marco Krause | Sara Moradi | Report 2022-W7-X-3.2.1 EK-CER | Report on the preparation and commissioning of the AM-Beam diagnsotics, video diagnostics and respecitve developments of analysis tools and physics analysis | 2022-01-01 | 2022-10-31 | EK-CER | 9.4615 | 8 | 18.9 | 16.5375 | 29.0745 | 14.5373 | 31.0748 | Approved
|  |  | 2022-W7X-3.2.1-ENEA UC: | Development of imaging tools | 2022-W7X-3.2.1-ENEA UC: Development of imaging tools | Extension of machine learning and deep learning methods for strike-line characterization and spatial calibration software. | Fabio Pisano | Flavia Miele | Marcin Jakuboski | Sara Moradi | Report 2022-W7-X-3.2.1 ENEA UC | Report on AI methods for strike-line characterization | 2022-01-01 | 2022-10-31 | ENEA UC | 3 | 0 | 0 | 0 | 21.3125 | 10.6562 | 10.6562 | Approved
|  |  | 2022-W7X-3.2.1-ENEA RFX: | Probe head development | 2022-W7X-3.2.1-ENEA RFX: Probe head development | Development of probe head concepts and commissioing of probe heads | Monika Spolaore | Flavia Miele | Carsten Killer | Sara Moradi | Report 2022-W7-X-3.2.1 ENEA RFX | Report on probe head concepts and commisioning | 2022-01-01 | 2022-10-31 | ENEA RFX | 1.2308 | 0 | 0.912 | 0.798 | 8.7436 | 4.3718 | 5.1698 | Approved
|  |  | 2022-W7X-3.2.1-FZJ: | Commissioning of components and diagnostics | 2022-W7X-3.2.1-FZJ: Commissioning of components and diagnostics | Commissioning of spectroscopy systems, endoscopes, manipulators, refelctometer and support actions | Olaf Neubauer | Olaf Neubauer | Olaf Grulke | Sara Moradi | Report 2022-W7-X-3.2.1 FZJ | Report on commissiong of FZJ contributions | 2022-01-01 | 2022-10-31 | FZJ | 10.1538 | 0 | 31.68 | 27.72 | 75.8365 | 37.9183 | 65.6383 | Approved
|  |  | 2022-W7X-3.2.1-IPPLM: | Preparation and commissioning of diagnostics and software tools | 2022-W7X-3.2.1-IPPLM: Preparation and commissioning of diagnostics and software tools | Commissioning of spectroscopy systems (PHA, CO monitor) and data analysis tools | Marta Gruca | Monika Kubkowksa | Ulrich Neuner | Sara Moradi | Report 2022-W7-X-3.2.1 IPPLM | Report on commissioning of IPPLM contributions to W7-X | 2022-01-01 | 2022-10-31 | IPPLM | 17.2308 | 17 | 14.196 | 12.4215 | 64.7949 | 32.3974 | 44.8189 | Approved
|  |  | 2022-W7X-3.2.1-IST: | Preparation of fast electronics | 2022-W7X-3.2.1-IST: Preparation of fast electronics | Development and deployment of FPGA developments for fast interlocks | Bernardo Carvalho | Rui Coelho | Birger Buttenschön | Sara Moradi | Report 2022-W7-X-3.2.1 IST | Report on commissioning of IST contributions to W7-X | 2022-01-01 | 2022-12-31 | IST | 3.3846 | 0 | 5.4 | 4.725 | 17.734 | 8.867 | 13.592 | Review started
|  |  | 2022-W7X-3.2.1-KIPT: | Preparation of plasma start-up and wall conditioning | 2022-W7X-3.2.1-KIPT: Preparation of plasma start-up and wall conditioning | Studies of ICRH plasma start-up at U-2M and LHD and data analysis in support of OP2 scenarios and development of scenarios for ICWC on U-2M and LHD in support of W7-X, including a scenario at low magnetic field, improvements and developments for ICWC related diagnostics. ICRH start-up scenarios in support of W7-X and start-up ICRH / ECRH modeling for W7-X and U-2M. | Yurij Kovtun | Vladimir Moissenko | Torsten Stange | Sara Moradi | Report 2022-W7-X-3.2.1 KIPT | Report on prepartory actions for OP2.1 from KIPT | 2022-01-01 | 2022-12-31 | KIPT | 81.0769 | 0 | 17.16 | 15.015 | 69.2532 | 34.6266 | 49.6416 | Approved
| 2022-W7X-3.3: Support actions for EU Components and W7-X | 2022-W7X-3.3.1: Support Actions for the Integration of EU Components | 2022-W7X-3.3.1: BEN… |  | 2022-W7X-3.3.1: BEN… | [7 empty] | 2022-01-01 |  | - | - | - | - | - | - | - | - | -
|  | 2022-W7X-3.3.2: Support Actions for W7-X | 2022-W7X-3.3.2-ENEA: | Gyrotron development support | 2022-W7X-3.3.2-ENEA: Gyrotron development support | Multi physics simulations for 1.5 and 2MW gyrotrons | Laura Savoldi | Falvia Miele | Heinrich Laqua | Sara Moradi | Report 2022-W7-X-3.3.2 ENEA | Report on multi-physics simulations for 1.5 and 2MW gyrotrons | 2022-01-01 | 2022-12-31 | ENEA | 2 | 0 | 0 | 0 | 14.2083 | 7.1042 | 7.1042 | Approved
|  |  | 2022-W7X-3.3.2-KIT-IAM: | Gyrotron tests and support actions | 2022-W7X-3.3.2-KIT-IAM: Gyrotron tests and support actions | Diamond window stress calcuations and gyrotron tests | Dirk Strauß | Mihaela Ionescu-Bujor | Heinrich Laqua | Sara Moradi | Report 2022-W7-X-3.3.2 KIT-IAM | Report on gyrotron tests and stress calculations | 2022-01-01 | 2022-12-31 | KIT | 3 | 0 | 0 | 0 | 26.9375 | 13.4688 | 13.4688 | Review started
|  |  | 2022-W7X-3.3.2-KIT-IHM: | Gyrotron Development and Testing | 2022-W7X-3.3.2-KIT-IHM | Development and testing of 1.5 MW 140 GHz gyrotrons for the upgraded ECRH at W7-X | Gerd Gantenbein | Mihaela Ionescu-Bujor | Heinrich Laqua | Sara Moradi | Report 2022-W7-X-3.3.2 KIT-IHM | Preparation of teststand, installation and adjustment of magnet + tests of 1.5 MW short-pulse gyrotron + short-pulse tests of isolated beam tunnel | 2022-01-01 | 2022-12-31 | KIT | 22 | 0 | 24.624 | 21.546 | 197.5417 | 98.7708 | 120.3168 | Review started
|  |  | 2022-W7X-3.3.2-NCSRD: | Gyrotron development support | 2022-W7X-3.3.2-NCSRD: Gyrotron development support | Investigations on advanced configurations for the beam tunnel, provision of the E/M part for multi-physics simulations of upgraded cavity designs with advanced cooling circuits (in collaboration with ENEA-PoliTo), and initiation of studies towards a 2 MW 140 GHz CW gyrotron (i.e. identification of suitable operating modes). | Chelis, Ioannis | Yannis Kominis | heinrich Laqua | Sara Moradi | Report 2022-W7-X-3.3.2 NCSRD | Report on NCSRD support to gyrotron development | 2022-01-01 | 2022-12-31 | NCSRD | 6 | 0 | 0 | 0 | 28.6875 | 14.3438 | 14.3438 | Approved
2022-W7X-5: International Collaborations, ITER, DEMO and HELIAS Basis | 2022-W7X-5.1: Coordinated Working Group | 2022-W7X-5.1.1: Joint Actions | 2022-W7X-5.1.1: BEN… | [11 empty] | - | - | - | - | - | - | - | - | -
|  | 2022-W7X-5.1.2: Joint Experiments | 2022-W7X-5.1.2: BEN… | [11 empty] | - | - | - | - | - | - | - | - | -
| 2022-W7X-5.2: ITER (linked to FSD-PrIO) | 2022-W7X-5.2.1: ITPA | 2022-W7X-5.2.1-ENEA: | Feasibility studies Thomson scattering | 2022-W7X-5.2.1-ENEA: Feasibility studies Thomson scattering | Conduct feasibility studies for the ITER Thomson scattering in line with prototypical applications for W7-X | Giudicotti, Leonardo | Flavia Miele | Ekkehard Pasch | Sara Moradi | Report 2022-W7X-5.2.1: ENEA | Feasibiltiy study | 2022-01-01 | 2022-12-31 | ENEA | 1 | 0 | 0 | 0 | 7.1042 | 3.5521 | 3.5521 | Approved
|  | 2022-W7X-5.2.2: Direct Support Actions | 2022-W7X-5.2.2: BEN… | [11 empty] | - | - | - | - | - |  |  |  | -
| 2022-W7X-5.3: DEMO & HELIAS Basis (linked to FTD) | 2022-W7X-5.3.1: HELIAS Physics Basics | 2022-W7X-5.3.1-CIEMAT: | Stellarator Database | 2022-W7X-5.3.1-CIEMAT: Stellarator Database | Maintenance and IMASsification of the Stellaraor Database | Alfonso Baciero | Entrique Ascasibar | Golo Fuchert | Sara Moradi | Report 2022-W7X-5.3.1: ENEA | Report on the IMAS version of the Stellarator database | 2022-04-01 | 2022-09-01 | CIEMAT | 3.75 | 0 | 0 | 0 | 22.3828 | 11.1914 | 11.1914 | Approved
|  | 2022-W7X-5.3.2: Direct Support Actions | 2022-W7X-5.3.2: BEN… | [11 empty] | - | - | - | - | - | - | - | -
|  | unallocated | Stepanov | [11 empty] | LPP-ERM |  |  | 31 | 27.125 |  |  | 27.125
[19 empty] | 450.6302 | 2723.1498 | 1406.1749 | 1856.8051
Note on AE27: Autor: Preparation and scientific phase w/o proposlas
Note on AI27: Autor: OP21.
Note on AI28: Autor: Op21. 2022
Note on AE38: Autor: vgl. Zelle AC27 - Diskrepanz 4 k€

## Status as in IMS
Actual Status in IMS exported 02.03.2022
Work Package | Deliverable ID | Title | Deliverable Owner | Beneficiary | Year | Status | PM @ 0% | PM @ 40% | PM @ 44% | PM @ 50% | PM @ 70% | PM @ 80% | PM @ 100% | Total PM | Costs Eq./OGS @ 0% [k€] | Costs Eq./OGS @ 40% [k€] | Costs Eq./OGS @ 44% [k€] | Costs Eq./OGS @ 50% [k€] | Costs Eq./OGS @ 70% [k€] | Costs Eq./OGS @ 80% [k€] | Costs Eq./OGS @ 100% [k€] | Total Eq./OGS Costs [k€] | Costs Missions @ 70% [k€] | Costs Missions @ 100% [k€] | Total Missions Cost [k€] | Unit Costs [k€] | Costs Subcontracting [k€] | Costs Financial Support to 3rd Parties [k€] | Total Indirect Costs [k€] | Total Resources [k€] | Total Cons. Contr. [k€] | SUMME | Total Commission Contr. [k€]
W7X | W7X-GenTask-Missions | Missions of Work Package 2022 | Andreas Dinklage(MPG) | LPP-ERM-KMS | 2022 | Running | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.4574 | 0 | 14.4574 | 0 | 0 | 0 | 3.6143 | 18.0718 | 12.6502 |  | 9.9395
W7X | W7X-PMB-Not Allocated | Missions Budget for Not Allocated-2022 | Andreas Dinklage(MPG) | Not Allocated | 2022 | Running | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188.426 | 0 | 188.426 | 0 | 0 | 0 | 47.1065 | 235.5325 | 164.8727 | 177.523 | 129.5429 | (=131 k€ indicative mission budget + 46 k€ INCO)
W7X | W7X-T003-D002 | 2022 Unit Costs / Secondment WPW7X | Andreas Dinklage(MPG) | Not Allocated | 2022 | Draft | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.744 | 0 | 0 | 0 | 63.744 | 46.085 | 46.085 | 35.0592
W7X | W7X-2.1.1-T001-D001 | 2022-W7X-2.1.1: Proxy Deliverable for Campaign OP2.1 | Andreas Dinklage(MPG) | Not Allocated | 2022 | Draft | 0 | 0 | 0 | 92.75 | 0 | 0 | 0 | 92.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144.9219 | 724.6094 | 425 | 425 | 398.5352
W7X | W7X-2.1.1-T003-D001 | Report 2022-W7X-2.2.1-MPG | Hans-Stephan Bosch(MPG-Greifswald) | MPG | 2022 | Running | 72.02 | 0 | 0 | 0 | 0 | 180.04 | 0 | 252.06 | 1220 | 0 | 0 | 0 | 0 | 3049 | 0 | 4269 | 0 | 0 | 0 | 0 | 0 | 0 | 1521.4831 | 7607.4156 | 4346.7883 | 4346.7883 | 4184.0786
W7X | W7X-3.1.1-T005-D001 | Report 2022-W7X-3.1.1-FZJ | Olaf Neubauer(FZJ) | FZJ | 2022 | Running | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 450 | 180 | 180 | 247.5
W7X | W7X-1.1.1-T002-D001 | Management Report 2022-W7X-1.1.1-MPG | Andreas Dinklage(MPG) | MPG | 2022 | Running | 0 | 0 | 0 | 0 | 16.8 | 0 | 0 | 16.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30.275 | 151.375 | 105.9625 | 1044.4283 | 83.2562
W7X | W7X-1.1.2-T002-D001 | Management Report 2022-W7X-1.1.2-CIEMAT | Ivan Calvo(CIEMAT) | CIEMAT | 2022 | Running | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.325 | 71.625 | 50.1375 |  | 39.3937
W7X | W7X-2.2.1-T009-D001 | Report 2022-W7-X-2.2.1 OEAW | Winfried Kernbichler(OEAW) | OEAW | 2022 | Draft | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7938 | 23.9688 | 11.9844 |  | 13.1828
W7X | W7X-2.2.1-T010-D001 | Report 2022-W7-X-2.2.1 CIEMAT | Arturo Alonso(CIEMAT) | CIEMAT | 2022 | Running | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.9375 | 59.6875 | 29.8438 |  | 32.8281
W7X | W7X-2.2.1-T011-D001 | Report 2022-W7-X-2.2.1 CIEMAT BSC | Mervi Mantsinen(10-BSC) | CIEMAT | 2022 | Running | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3875 | 11.9375 | 5.9688 |  | 6.5656
W7X | W7X-2.2.1-T013-D001 | Report 2022-W7-X-2.2.1 CRPP | Jonathan Graves(EPFL) | EPFL | 2022 | Running | 0 | 0 | 0 | 3.52 | 0 | 0 | 0 | 3.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.9173 | 44.5867 | 22.2933 |  | 24.5227
W7X | W7X-2.2.1-T014-D001 | Report 2022-W7-X-2.2.1 FZJ | Olaf Neubauer(FZJ) | FZJ | 2022 | Running | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.3813 | 141.9062 | 70.9531 |  | 78.0484
W7X | W7X-2.2.1-T015-D001 | Report 2022-W7-X-2.2.1 IPPLM | Tomasz Fornal(IPPLM) | IPPLM | 2022 | Running | 12 | 0 | 0 | 12 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.05 | 90.25 | 22.5625 |  | 49.6375
W7X | W7X-2.2.1-T016-D001 | Report 2022-W7X-2.2.1 KIPT KINR | Yaroslav Kolesnichenko(KIPT) | KIPT | 2022 | Running | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.3667 | 6.8333 | 3.4167 |  | 3.7583
W7X | W7X-2.2.1-T017-D001 | Report 2022-W7X-2.2.1 KIPT | Alexander Kozachek(KIPT) | KIPT | 2022 | Running | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.68333 | 3.4167 | 1.7083 |  | 1.8792
W7X | W7X-2.2.1-T018-D001 | Report 2022-W7X-2.2.1 VTT | Taina Kurki-Suonio(VTT) | VTT | 2022 | Running | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9375 | 39.6875 | 19.8438 |  | 21.8281
W7X | W7X-3.1.1-T003-D001 | Report 2022-W7-X-3.1.1 FZJ | Olaf Neubauer(FZJ) | FZJ | 2022 | Running | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56.7625 | 283.8125 | 141.9062 |  | 156.0969
W7X | W7X-3.1.1-T004-D001 | Report 2022-W7-X-3.1.1 ERM | Jozef Ongena(LPP-ERM-KMS) | LPP-ERM-KMS | 2022 | Running | 0 | 0 | 0 | 14.77 | 0 | 0 | 0 | 14.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28.463 | 142.3151 | 71.1576 |  | 78.2733
W7X | W7X-3.1.3-T005-D001 | Report 2022-W7X-3.1.3 KIT | Stylianos Varoutis(KIT) | KIT | 2022 | Running | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.775 | 53.875 | 26.9375 |  | 29.6313
W7X | W7X-3.1.3-T006-D001 | Report 2022-W7X-3.1.3 DTU SDU | Esmaeil Nadimi(01-SDU) | DTU | 2022 | Accepted | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8208 | 19.1042 | 9.5521 |  | 10.5073
W7X | W7X-3.2.1-T006-D001 | Report 2022-W7-X-3.2.1 CEA | Michael Houry(CEA) | CEA | 2022 | Running | 0 | 0 | 0 | 5.23 | 0 | 0 | 0 | 5.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.0133 | 50.0664 | 25.0332 |  | 27.5365
W7X | W7X-3.2.1-T007-D001 | Report 2022-W7-X-3.2.1 CIEMAT | Teresa Estrada(CIEMAT) | CIEMAT | 2022 | Accepted | 0 | 0 | 0 | 29.16 | 0 | 0 | 0 | 29.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34.8098 | 174.0488 | 87.0244 |  | 95.7268
W7X | W7X-3.2.1-T008-D001 | Report 2022-W7-X-3.2.1 CIEMAT - U Seville | Anton Jansen van Vuuren(09-US) | CIEMAT | 2022 | Running | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.1625 | 35.8125 | 17.9062 |  | 19.6969
W7X | W7X-3.2.1-T009-D001 | Report 2022-W7-X-3.2.1 CIEMAT - UPC | Josep R. Casas(05-UPC) | CIEMAT | 2022 | Running | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.775 | 23.875 | 11.9375 |  | 13.1312
W7X | W7X-3.2.1-T010-D001 | Report 2022-W7-X-3.2.1 DTU | Stefan Kragh Nielsen(DTU) | DTU | 2022 | Running | 0 | 0 | 0 | 3.46 | 0 | 0 | 0 | 3.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.61 | 33.0502 | 16.5251 |  | 18.1776
W7X | W7X-3.2.1-T011-D001 | Report 2022-W7-X-3.2.1 EK-CER | Gabor Kocsis(EK-CER) | EK-CER | 2022 | Running | 8 | 0 | 0 | 9.46 | 0 | 0 | 0 | 17.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.7306 | 53.6531 | 14.5349 |  | 29.5092
W7X | W7X-3.2.1-T012-D001 | Report 2022-W7-X-3.2.1 ENEA UC | Fabio Pisano(ENEA) | ENEA | 2022 | Running | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2625 | 21.3125 | 10.6562 |  | 11.7219
W7X | W7X-3.2.1-T013-D001 | Report 2022-W7-X-3.2.1 ENEA RFX | Monica Spolaore(ENEA) | ENEA | 2022 | Running | 0 | 0 | 0 | 1.23 | 0 | 0 | 0 | 1.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7476 | 8.7381 | 4.3691 |  | 4.806
W7X | W7X-3.2.1-T014-D001 | Report 2022-W7-X-3.2.1 FZJ | Olaf Neubauer(FZJ) | FZJ | 2022 | Running | 0 | 0 | 0 | 10.15 | 0 | 0 | 0 | 10.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15.1616 | 75.8078 | 37.9039 |  | 41.6943
W7X | W7X-3.2.1-T015-D001 | Report 2022-W7-X-3.2.1 IPPLM | Marta Gruca(IPPLM) | IPPLM | 2022 | Running | 17 | 0 | 0 | 17.23 | 0 | 0 | 0 | 34.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25.7438 | 128.7191 | 32.396 |  | 70.7955
W7X | W7X-3.2.1-T016-D001 | Report 2022-W7-X-3.2.1 IST | Bernardo Carvalho(IST) | IST | 2022 | Draft | 0 | 0 | 0 | 3.38 | 0 | 0 | 0 | 3.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.542 | 17.7098 | 8.8549 |  | 9.7404
W7X | W7X-3.2.1-T017-D001 | Report 2022-W7-X-3.2.1 KIPT | Yurii Kovtun(KIPT) | KIPT | 2022 | Running | 0 | 0 | 0 | 81.08 | 0 | 0 | 0 | 81.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.8512 | 69.2558 | 34.6279 |  | 38.0907
W7X | W7X-3.3.2-T011-D001 | Report 2022-W7-X-3.3.2 ENEA | Laura Savoldi(ENEA) | ENEA | 2022 | Running | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8417 | 14.2083 | 7.1042 |  | 7.8146
W7X | W7X-3.3.2-T012-D001 | Report 2022-W7-X-3.3.2 KIT-IHM | Gerd Gantenbein(KIT) | KIT | 2022 | Draft | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39.5083 | 197.5417 | 98.7708 |  | 108.6479
W7X | W7X-3.3.2-T013-D001 | Report 2022-W7-X-3.3.2 NCSRD | Ioannis Chelis(NCSRD) | NCSRD | 2022 | Running | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.7375 | 28.6875 | 14.3438 |  | 15.7781
W7X | W7X-3.3.2-T014-D001 | Report 2022-W7-X-3.3.2 KIT-IAM | Dirk Strauss(KIT) | KIT | 2022 | Draft | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.3875 | 26.9375 | 13.4688 |  | 14.8156
W7X | W7X-5.2.1-T005-D001 | Report 2022-W7X-5.2.1: ENEA | Leonardo Giudicotti(01-RFX) | ENEA | 2022 | Running | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4208 | 7.1042 | 3.5521 |  | 3.9073
W7X | W7X-5.3.1-T003-D001 | Report 2022-W7X-5.3.1: CIEMAT | Alfonso Baciero(CIEMAT) | CIEMAT | 2022 | Accepted | 0 | 0 | 0 | 3.75 | 0 | 0 | 0 | 3.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4766 | 22.3828 | 11.1914 |  | 12.3105
6219.8246
[31 empty] | Actual Status in IMS |  |  | Planning made by AD |  | Discrepancy
[31 empty] | Allocated HR: | 1044.4283 |  | see WBS: | 1044.4489 | -0.020634
[31 empty] | Unallocated OP2: | 425 |  | see WBS: | 217.748 | 207.252
[31 empty] | Secondment: | 46.085 |  | see WBS: | 12.1275 | 33.9575 |  |  | * | HR |  | OP&Maint | ENH
[31 empty] | Mission Budget w/o INCO: | 131.523 |  | see WBS: | 209.1985 | -77.6755 |  |  | Leftover 2021 | 181.4127 | *
[31 empty] | Total: | 1647.0363 |  |  | 1483.5229 | 163.5134 | * |  | Spent 2021 | 2964.5353
[39 empty] | Transferred to 2022 | 45.065 | **
[31 empty] | ENH: | 180 |  | see IR Grid: | 180 | 0 |  |  | 2022 | 1601.5372 |  | 4346.7883 | 180
[31 empty] | OP&Maint: | 4346.7883 |  | see IR Grid: | 4346.7883 | 6.6667e-07 |  |  | 2023 | 1551.5952 |  | 5391.9783 | 180
[39 empty] | 2024 | 929.34 |  | 6810.6963 | 180
[31 empty] | Total Annual Budget in IMS: | 6219.825 | [6 empty] | 2025 | 929.2309 |  | 6640.5583 | 180
[31 empty] | Allocated Status IMS: | 6219.8246 |  | Total: | 6010.3112 | 209.5134 |  |  | Total | 8202.7163 |  | 23190.0212 | 720 | 32112.7376
[31 empty] | Available: | 0.000401 |  |  |  | 163.5134 |  |  | HR Available 2023-25 | 3754.6582
[31 empty] | INCO: | 46 | [6 empty] | HR p.a. | 1251.5527
[31 empty] | 2021 Mission Budget to be transferred in summer: | 181.5
Note: * 163,5 k€ + 181,4 k€ are foreseen to be used in 2023-2025
Note: * Values of table transferred from MBT
Note: ** Secondment from 2021 transferred to 2022 on 02/03/22