## Slide 1: 9th WPSA Planning Meeting Budapest, 5-9 September 2022 WPSA Summary
C.Sozzi (PL)

## Slide 2: Purpose and structure of this meeting
Planning of 2023 activities and tasks
Review/update of the status of the tasks: progress, difficulties, new facts, constraints, needs, priorities
Focusing of the objectives
Evaluate the need of resources
Evaluate the need of new tasks
Reinforce the interaction with the TGLs and start to seed the ET
Aim of this morning
Review of the discussion points, open questions, list of actions
  PL, Area Coordinators & Experiment Team Summaries
  Next steps, Discussion and conclusions

## Slide 3: WPSA Planning Meeting 2022: Final session
Session topics
Data access tools
IC preparation, including some new development: RE detection
Discharge simulator and Scenario modelling
Modelling of MHD stability, Fast particles, RE heat loads, Edge and SOL, Assessment of the equilibrium
Scientific Real time networks
Enhancement projects: feasibility studies
Enhancement projects under procurement: preparation of the commissioning
Disruptions: prediction, avoidance, operational management
Remarks
Generally, significant room for discussion during the sessions
However, let’s keep open the channel for further interactions
Indico page of the meeting WPSA General Planning Meeting (5-9 September 2022): Overview · Indico (euro-fusion.org)
WPSA wiki page https://wiki.euro-fusion.org/wiki/WPSA_wikipages:_JT-60SA_Work_Package
Simply by email and phone
Suggestions for the next meeting? Format, place…

## Slide 4: Grant Agreement Milestones
GA Milestone No. | GA Milestone Title | Due Date [mm/yyyy] | Proposed revised due date (at the PB in March 2022) | Proposed revised due date to be discussed at the next PB
SA.M.01 | Participation in the Integrated Commissioning before plasma operations | June 2021 |  | 
SA.M.02 | Start of the EU-REC project | Apr. 2022 |  | 
SA.M.03 | Decision on plan and resources of EU enhancements for BA Phase II – 2025-2029 | Mar. 2023 |  | June 2023
SA.M.04 | Call to start EU enhancement programme for 2025-2029 | Jun. 2023 |  | Sept. 2023
SA.M.05 | Start of the new EU enhancement projects (TBD) Start of the new EU enhancement projects (TBD) | Oct. 2023 |  | Nov. 2023
SA.M.06 | Participation to the development of scenario at high plasma current in H-mode | Dec. 2023* | Dec. 2024* | Dec. 2025*
*Milestones dependent on external conditions to which the workpackage is constrained

## Slide 5: Grant Agreement Deliverables
GA Deliverable No. | GA Deliverable Title | Due Date [mm/yyyy] | Proposed revised due date (at the PB in March 2022) | Proposed revised due date to be discussed at the next PB
SA.D.01 | Appointment of Experiment Leader from EU (after call issued end 2020) | Apr. 2021 |  | 
SA.D.02 | Report on the first phase of the Integrated Commissioning (before plasma operations). Results and return of experience, mainly for DTT | Dec. 2021* |  | 
SA.D.08 | Final Report on the Integrated Commissioning (including plasma operations) |  | Dec. 2022* | Dec.2023
SA.D.03 | Report on the initial organisation of the JT-60SA scientific exploitation | Dec. 2021 |  | 
SA.D.04 | Documented plan of EU enhancement programme for BA Phase II– 2025-2029 | May 2022 | Dec. 2022 | 
SA.D.05 | Delivery and final tests of EU-REC completed | Jan 2023 | Jun. 2023 | Jun.2024
SA.D.06 | Installation of the EU systems before the OP2 campaign. | Jun. 2023 |  | Dec. 2024
SA.D.07 | *Report on participation to the OP.2 campaign. Results and return of experience | Dec. 2024* |  | Dec. 2025*
SA.D.10 | Delivery of EU procurements (TBD) for the OP3 campaign completed. | Dec. 2025* |  | 
*Deliverable dependent on external conditions to which the workpackage is constrained

## Slide 6: What’s next?
Output of this planning meeting: tasks status and tentative plans (to be further elaborated). What we are doing of this?
Draft of the task assignment for 2023. Further interactions with PL/Area coordinators where needed
Proposal of the resources assigned to each task. This also concerns ETL, TGLs, Contact Persons for TGs
General criteria: focus the effort to support
  Integrated Commissioning and related analysis
  the Experiment Team in preparing the scientific programme (OP2 & OP3)
  Prioritizations of the enhancements:
    support the completion of the running projects
    new enhancements coherent with priorities and timeline of the scientific programme (and of course available resources)
  Modeling for mid-long term objectives: revision of the plasma scenarios, W-divertor…
The JT-60SA EU community is at its first steps: even if some task has to be frozen, there is a strong interest in keeping in touch with all the valuable expertises. JT-60SA will evolves in time and will offer opportunities of involvement
Preparation of the Annual Workplan 2023
Achievements/ highlights + objectives for AWP23 - Discussion/Approval at the Project Board (26 October)

## Slide 7: FP8 Timeline
2022 Reporting
FP8 Grant Agreement ends the 31st December 2022
    Mandatory
1st December  Report signed on IDM by all authors and co-authors
*Note: review and approval process can only start if the document is signed by the author and all co-authors
23rd December Report reviewed and approved by PL

## Slide 8: FP9 Timeline: report and budget review
2022 Reporting
1st October  Report templates ready on IDM
Enhancements
15 November  Reports signed on IDM by all authors and co-authors
1st December  Reports reviewed and approved on IDM
All others area
15th December  Reports signed on IDM by all authors and co-authors
23rd or 31st December*  Reports reviewed and approved on IDM
*According to IMS deadline
If you are already aware of delay or open issues that can affect the preparation of the report, please inform asap your area coordinator
**Note: review and approval process can only start if the document is signed by the author and all co-authors

## Slide 9: AW 2023 budget timeline
2022 Budget review
10th October  Any budget review need to be comunicate to the Area coordinator
 2022 Budget will be updated No more change will be possible
AWP2023 Budget
15th October  Area coordinator collects all information to update 2023 Indicative Resources (distribution by beneficiary requested)
26th October  AWP2023 shared on PB
5th November  Budget reviews and updates post PB
11th November  AWP 2023 final budget uploaded on IMS
12th-13th December AWP2023 approval by General Assembly

## Slide 10: Events in 2023
Review of the EU machines (=> overall scientific programme, roadmap)
Review of the TSVVs
JT-60SA restart & IC with plasma operations
Call for interest: IC analysis
Selection for a EEG trainee ongoing (VUV divertor diagnostics). Suggestions for next call, either EEG and ERG?