## Slide 1: JT-60SA Massive Gas Injection system Status and project plan
M. Dibon, G. Matsunaga, S. Nakamura, G. Phillips, C. Sozzi
Acknowledgement: G. Giruzzi, M. Hanada, M. Beck

## Slide 2: System status

## Slide 3: System status

## Slide 4: System status
Valves function test
No pressure drop
Atmospheric leak test
Piezo charge and discharge
Perfect charge and discharge curves for all piezo actuators

## Slide 5: System status
Lab setup
Control
PC
Central
PLC
Trigger
electronics
MGI
valves
Gas panel
Profibus cable (110 m)
Central PLC <-> gas panel
Atmospheric trigger
and signal cables
(250 m) and (280 m)
Pressure
regulators
In-vessel
fixtures
Vacuum
Feed throughs

## Slide 6: System status
Deliverables named in Annex B
2 MGI valves with mounting clamps and pipes to go through the stabilizing plate
2 feedthrough flanges ICF 114 with pressure gauges, pneumatic valves and potential breaks
2 mineral/PEEK insulated cable bundles for electrical supply in vessel (bundle diameter: 18 mm)
2 cables for electric supply from trigger modules in transfer room to vessel feedthroughs
1 gas preparation station with control equipment
2 trigger modules for the MGI valves
2 trigger signal selection modules
2 delay modules for timer signals
1 Siemens S7 PLC for controlling the gas preparation station and the trigger modules
1 control computer with monitor for control interface
1 Profibus cable from the gas preparation station under the torus hall to the PLC in the transfer room
2 signal cables (10x0.25mm) from two boundary boxes in the torus hall to the PLC in the transfer room
1 optical fibre cable from the PLC in the transfer room to the control computer in the control room
1 pressure booster for H2 and D2
4 pressure regulators for gas bottles
spare parts as defined in section 10
documentation as defined in section 12.1

## Slide 7: Future activities
Valve testing at IPP (Sep. 2022 – Nov. 2022)
  Function tests
  Pressure test of front reservoir at 100 bar (1.25 times design pressure)
  Pressure test of rear reservoir at 25 bar (1.25 times design pressure)
  200 operation cycle tests
  1st Vacuum leak test in hot and cold states
  Baking at 200 °C for 10 days
  2nd Vacuum leak test in hot and cold states
  Outgassing test
  Inspector from QST on site
System testing at IPP (Sep. 2022 – Dec. 2022)
  Electrical insulation
  Full setup of MGI system in the lab
  Test of manual and automatic operation modes
  Documentation
Offsite testing

## Slide 8: Future activities
Packing and shipping (Dec. 2022 – Jan. 2023)
  Transfer of ownership from IPP to F4E
  F4E organizes packing and transport
System inspection on arrival in Naka (early 2023)
  Unpacking and on-site inspection
  Quick assembly of the system for function test if possible
  Transfer of ownership from F4E to QST
Installation of the MGI system (Feb. 2024)
 | S 22 | O 22 | N 22 | D 22 | J 23 | F 23
MGI valves function tests |  |  |  |  |  | 
Pressure / leak tests |  |  |  |  |  | 
System tests |  |  |  |  |  | 
Packing and shipping |  |  |  |  |  | 
On-site system inspection |  |  |  |  |  | 
Project plan

## Slide 9: Future activities
Commissioning plan
Commissioning can be done directly after installation of the MGI system
No vacuum / plasma necessary for commissioning
Commissioning will include
  System test
  Inclusion of interlock signals
  Inclusion of H2 alarm signal
  Test of machine timer signals
  Adjustment of system parameters (Filling time, pressure drop, etc.)
  Final system test
Vacuum vessel has to be empty when valves are fired
Detailed commissioning plan has to be worked out together with QST colleagues