## Slide 1: Implementation of data management plan within EUROfusion
P. Strand

## Slide 2: Scenarios
Scenario A: making metadata only available and searchable using IMAS data subsets for
interoperable definitions of quantities [F,(I)]; Implement!
Scenario B: adds to Scenario A by allowing a subset of the data to be accessed using common tools (for example UDA). Facilities are responsible for the access level and qualification of data through the data mappings [F,A,I,(R)]; prototype! But new action Imasifiaction of Machine data is essentially an extension of this action!
Scenario C: builds on the previous stages and allows for enhanced data provenance and referencing through PID’s [F,A,I,R]. Defer!  Possibly into 2026-27 extension
Scenario D: adds a lightweight layer for open access to non-embargoed metadata and, where allowed, by the facilities also data access for export in human readable formats (CSV files) [F,A,I,R] and open. Defer!

## Slide 3: Status
Budget approved and active project in IMS
  Scenario A + prototyping scenario B  Hopefully we can accelerate/extend this
Formal responses
  VR – coordination
  PSNC – core services
  IPP, WEST, and TCV – site services
Informal contacts
  MAST-U
  JET
  ITER
Just started: Kick of meeting held

## Slide 4: Implementation
Extension of the Fair 4 Fusion tool set +
  Metadata ontology based on IDS_summary etc
  IMAS installation for data storage/access
  UDA proposed for data transfer
   Dependence on IMAS/ITER collaboration
The portal interface and development activities will be hosted on the Gateway (minor hardware need to be made available)
Supported by a Core team for the central services
Documentation, software and ticketing will be integrated with the existing PSNC based gitlab and jira services.
The Infrastructure will be built on the Fair for Fusion provided software tools and developed practices
Initial sites consists of
  AUG, TCV and WEST with JET, MAST-U, ( and ITER?) Contributing in kind  JT-60SA + W7-X
  To provide first metadata (A) and then data access and mappings for data to run interpretative, predictive and other tools (B)

## Slide 5: Next steps
Initiate Gitlab project(s) @PSNC (PS+Core)
  Documentation
  Mirror/move F4F software to psnc gitlab
  Communications channels: mailing list(s), trello and slack channel
Actions: Inventory of post F4F status for metadata and tools (core + sites)
Actions: Inventory of IMAS installations on devices (Sites)
Series of regular Site + Core (SiCo) Technical meetings to guide/steer/support implementation in two weeks from now? Monthly meetings
  Present (updated?) detailed Core plan (first meeting) then regular status meetings/discussion forums
  First meeting: Present F4F metadata status
    Review of current IMAS status on devices
    outcome resource loaded time line for scenario A. Strategy for prototyping or implementation of scenario B
  Proposal: Second meeting:
    Infrastructure components(status and plans): IMAS infrastructure (Olivier Hoenen, ITER),
    UDA at CODAC (Lana Abadie (?), ITER),
    UDA in practice (Adam Parker, CCFE/MAST-U)
  ITER is about to initiate its own ”data collection”/validation activity ? - need to keep aligned/informed about this – ITER observer or occasional guest at SiCo?
Stakeholders Data Coordination meeting with TSVVs, WPs and others that have data access needs.
  Initiate work on capturing data requirements and needs for data searches and modelling requirements – questionnaire.
  First meeting: Early may (after first capture and followup questions).
  Present strategy and plans for core + site services
   outcome first version of live document on data needs – for A ) metadata searches and B) data access for TSVV activities.
Core
Users
Sites