## Slide 1: JT-60SA Enhancement Projects – Cryopumps (CRP) Project Update
Chr. Day, for the CRP Team
WPSA Annual Meeting, 31 Mar 2020
Sam Davis,
Nandor Hajnal,
Kazuya Hamada,
Volker Hauer,
Go Matsunaga,
Shigetoshi Nakamura,
Kyohei Natsume,
Carla Piccinni,
Santiago Ochoa,
Carlo Sozzi,
Holger Strobel,
Manfred Wanner

## Slide 2: Four party scope sharing
KIT under EUROfusion WPSA delivers the engineering design of the system, validation and according documentation.
F4E does the procurement and delivers the cryopump system hardware, utilizes KIT under EUROfusion for tight project monitoring.
  3.7 K coated cryopanels equipped with heaters fully cabled to the cable interface at the even-numbered lower vertical ports
  80 K base plate and thermal shield plates
  80 K chevron baffle, blackened (absorptive) where needed
  Temperature sensors attached and with cabling to reach the even-numbered lower vertical ports
  All parts required to mount the pumps and connecting to in-vessel cryopiping at the odd-numbered lower vertical ports
QST provides:
  the electric feedthroughs
  the recording of the signals, conversion and control.
  Isolation of the cryopumps from the cryostat by potential breaks in the supply pipes
  The power supplies of the heaters
  The cable trays for the heater and sensor cables to guide them from the odd to the even numbered lower ports
New items

## Slide 3: Cryopump environment
40° sector
Contract: 9 identical cryopump units + 1 spare

## Slide 4: CAD model - Full assembly

## Slide 5: CAD model – Chevrons removed

## Slide 6: CAD model - 4K-supports
Sliding supports allow the contraction/expansion/rotation of the 4K panel

## Slide 7: CAD model – 80K-supports to vessel
Free movement in direction of the yellow arrows.
must be adapted to the actual curves of the vessel

## Slide 8: FEM simulations – schedule and status

## Slide 9: FEM simulations – Load cases

## Slide 10: 2D drawing for CfT – 80 K system

## Slide 11: 2D drawing for CfT – 4 K system

## Slide 12: 2D drawing for CfT – Full assembly

## Slide 13: Present detailed design status
Critical thermomechanical analyses are closed, no further issue remaining.
Remaining analysis to be done is seismic (started).
Then, final report will be compiled (200 pages +).
Interfaces with QST have been clarified (connection with cryopiping, feedhrough ratings for heater and sensor cables, cable trays even/odd numbered lower ports).
CAD model has been re-integrated and clash check performed, found 6 clashes which were resolved in a meeting with QST. Design amendment actions partly still ongoing (minor changes).
Current CAD model is considered as sufficiently final to be used for Call for tender.
Re-import from ANSYS to CATIA ongoing.
2D drawings for call for tender under final iteration.
BA_D_255UTZ

## Slide 14: Present management status
Call for tender policy changed: Now, only one contract for everything, one main supplier + sub-contractors.
Elaboration of Call for Tender Annex B (Technical Spec) has seen various iteration loops, is now in a very close to final status.
Elaboration of Call for Tender Annex A (Management Spec) is in a close to final status.
PA Annex B Tech Spec with QST still not approved, to be finalised (recent points Matsunaga-san, Natsume-san, Hamada-san), solutions have been agreed. The next version v1.2 to come very soon will then be the final one.
IMPORTANT: Make sure that the CfT Annex B is well in line with the PA Annex B, to have no surprises in the end.
PA and PA Annex A is on IDM for signature.
PA Annex B [T.R.72.] and Article 4.2 Annex A - Drawings and technical specifications sent to suppliers defining the design for manufacture shall be approved by QST.
This meeting / design review has not yet taken place, but will take place the latest when we have the manufacturing drawings.
BA_D_28GA8M
BA_D_29VESF

## Slide 15: QST timeline (from 2019, assumed to still hold)

## Slide 16: Work Plan
Stage | Activity | Initial Plan 10/18 | Updated 1/19
1 | Set-up of contract documents F4E | Q1/2019 | Q1/2019
2 | Detailed design | Q2-Q4/2019 | Q4 /2019
3 | Drawings and call for tender | Q1-Q3/2020 | Q1/2020-Q2/2020
4 | Manufacturing, FAT, delivery, project control and monitoring | Q4/2020-Q1/2022 | Q3/2020 – Q3/2021
5 | Installation | Q2/2022 | Q4/2021
6 | Commissioning | 2023 | 2022
~ Still holds
(delivery 10/2021)
High level milestones as per updated BA II work plan 2020