## Slide 1: FSD Change Management process
B. Meszaros et al
28 Feb 2023

## Slide 2: Overall process
Part1
Part2
Part3

## Slide 3: Process – Part1
Guiding Criteria for significant:
if anticipated change impacts on Grant Deliverable or Milestone (due date delay more than 6 months, scope change, cancellation, addition of new, etc.)
if anticipated change impacts a Grant risk in the unfavourable direction

## Slide 4: Process – Part2
“PCR package” includes:
WP change proposal
WP justification
PL/ TFL evaluation of the impact on the WP level
FSD evaluation of the impact on the programmatic level
FSD HoD proposal for decision

## Slide 5: Process – Part3
“Revision requested” if:
the PB requests revision of the PCR by the PL/ TFL
the PB endorses the change but does not agree to the decision proposed by the HoD

## Slide 6: Significant PCR summary template (for PB decision)

## Slide 7: Not significant PCR summary template (HoD decision)