## Slide 1: FSD Project Control status
B. Meszaros
21 Sept 2023

## Slide 2: Annual WP Management Cycle (FSD 2023)
Generic cycle in IDM: 2P56W9

## Slide 3: Grant Deliverables status https://eurofusionpilot.sharepoint.com/:x:/s/PMO/ETRUZnErEpBBphrOg3Ok0cQBlrURI6o5dPiPAFM8ne5I2w
Sygma | Title in CWP | Due Date | Expected del date | Status | Comments/Reason for delay
TE.D.03 | High fluence operation on actively cooled divertor at WEST assessed and documented. | 31/12/2022 | 31/12/2023 | delayed | …late start of WEST…
TE.D.05 | The role of turbulent and MHD driven transport in the vicinity of the separatrix for the stability of the pedestal quantified and the implications for predictions for ITER and DEMO reported. | 31/12/2022 | 31/12/2023 | delayed | … take advantage of the high current experiments in JET…
TE.D.06 | Achievement of state-observer based control of radiative detachment using multiple diagnostics. | 31/12/2023 |  | on track | 
TE.D.07 | The disruption and run-away electron mitigation efficiency by single and multiple shattered pellet injectors on different sized devices to validate the ITER Strategy assessed and documented. | 31/12/2023 |  | on track | 
TE.D.08 | Balance between gross and net erosion of W under diff. operational conditions in full-met. tor. Devices | 31/12/2023 |  | at risk | 
TE.D.09 | Establishment and comparison of N and Ne-seeded partially-detached divertor in high-power operations in view of ITER radiative scenario. | 31/12/2023 |  | on track | 
TE.D.10 | The role of electron and ion heat channels and plasma rotation on the access to H-mode for hydrogen, helium and mixed plasmas in view of the ITER non-active phase quantified. | 31/12/2023 |  | on track | 
TE.D.11 | Incorporation of turbulence in multi-fluid calculations using physics-based diffusion coefficients (TSVV4). | 31/12/2023 |  | on track | Not cancelled!
SA.D.08 | Final Report on the Integrated Commissioning (including plasma operations) | 31/12/2023 |  | on track | 
W7X.D.05 | Assessment report on fast-ion generation and divertor exhaust (energy limit 1 GJ) | 31/12/2023 |  | on track | 
W7X.D.06 | Report on conducted scenario & campaign preparation (focus: preparation of steady-state scenarios turbulent and core neoclassical transport) | 31/12/2023 |  | on track | 
AC.D.04 | Advanced Computing Hubs including JET data centre support to the EUROfusion simulation programme including IMAS exploitation and portfolio of EUROfusion standard software for ITER and DEMO | 31/12/2023 |  | on track | 
AC.D.05 | Availability of HPC and Gateway in support of simulation programme as set by the KPIs | 31/12/2023 |  | on track | 
PWIE.D.06 | Damage matrix from the exposition of advanced W materials in HHF and plasma devices. | 31/12/2023 |  | on track | 
PWIE.D.07 | PSI modelling of DEMO main chamber erosion, deposition and fuel retention. PIC modelling of the sheath in the DEMO divertor (with TSVV-7). | 31/12/2023 |  | on track | 
PWIE.D.08 | Neutral gas kinetics modular code upgraded and midterm verification/validation (with TSVV-05). | 31/12/2023 |  | on track | 
PWIE.D.09 | Initial PSI modelling of W sources, screening, transport and core concentration in full W-devices. | 31/12/2023 |  | on track | 
PWIE.D.10 | Recommendation to ITER-IO on Material Research Laboratory on the ITER site regarding T, Be and neutron-activated materials: minimum requirement and auxiliary systems. | 31/12/2023 | 31/12/2024 | at risk | Delay until final ITER position on the topic.
PWIE.D.11 | Comprehensive catalogue on dust in metal devices: generation, migration, quantity, impact of moisture on dust generation. | 31/12/2023 |  | on track | 
PWIE.D.12 | In-situ fuel inventory assessment with the use of laser induced desorption techniques to monitor T retention in JET. | 31/12/2023 |  | on track | 
PRIO.D.02 | Report on the procedure for an automated and systematic validation of predictive integrated modelling including uncertainty quantification ( TSVV11 responsibility) | 31/12/2022 | 01/10/2023 | delayed | …testing is planned for 2023…
PRIO.D.03 | Report on the exploitation of the EUROfusion multi-machines database | 31/12/2023 |  | on track | 
PRIO.D.09 | Report on best practices in training of operational staff in EUROfusion facilities | 30/06/2023 | 07/07/2023 | delayed | The report is close to completion, at ~ 95% readiness.
PRIO.D.14 | Report on EUROfusion participation in ITER NBTF, ELISE and BUG activities | 31/12/2023 |  | on track | 
PRIO.D.15 | Report on the long pulse operation 3600s extraction of D- on ELISE facility | 31/12/2023 |  | on track | 
PRIO.D.23 | Report on Occupational Radiation Exposure and waste data collected at JET in DT operation | 31/12/2022 | 31/12/2024 | delayed | No new ORE data provided by UKAEA…
PRIO.D.24 | Report on calibration verification at JET in DT operation | 31/12/2022 | 31/12/2023 | delayed | Validated n calibration … not finalised by the JET operator
PRIO.D.25 | Report on JET neutronics experiments, validation of nuclear data and codes in JET DT | 31/12/2023 | 31/12/2024 | at risk | 
PRIO.D.26 | Report on neutron induced activation in ITER materials and on radiation damage in functional materials at JET following DT operation | 31/12/2023 | 31/12/2024 | at risk | 
PRIO.D.27 | Report on the implication of JET DT technological program for ITER | 31/12/2023 | 31/12/2024 | at risk | 

## Slide 4: Grant Milestones status https://eurofusionpilot.sharepoint.com/:x:/s/PMO/ETRUZnErEpBBphrOg3Ok0cQBlrURI6o5dPiPAFM8ne5I2w
Sygma | Title in CWP | Due Date | Expected del date | Status | Comments/Reason for delay
TE.M.01 | Completion of the disruption and run-away mitigation experimental programme with the SPIs. | 31/12/2022 | 31/10/2023 | delayed | Delay of C44 campaign on JET by 2 months. The campaign was reduced to 4 weeks only. This programme has been started but not completed
TE.M.02 | Access stable operation at low collisionality and high beta | 31/12/2023 |  | on track | 
TE.M.03 | JET scenarios ready for DTE3 operation | 31/12/2023 |  | on track | 
TE.M.04 | High performance reduced/no ELM scenario in a metallic wall operated routinely | 31/12/2023 |  | on track | 
TE.M.05 | H-mode access for the ITER non-activated phase (H, He, H/D) reliably established | 31/12/2023 |  | on track | 
SA.M.04 | Call to start EU enhancement programme for 2025-2029 | 30/09/2023 |  | on track | 
SA.M.05 | Start of the new EU enhancement projects (TBD) | 30/11/2023 |  | on track | 
W7X.M.03 | Operation with water-cooled PFCs Completed | 31/12/2023 |  | on track | 
AC.M.05 | Availability (defined by KPIs) of Gateway and HPC to EUROfusion users for production runs | 31/12/2023 |  | on track | 
AC.M.06 | Release core-edge IMAS workflow for fully integrated core SOL divertor modelling | 31/12/2023 |  | on track | 
PWIE.M.04 | High fluence experiments in deuterium (L-mode) discharges on ITER-like PFUs in WEST executed. | 30/06/2022 | 31/12/2023 | delayed | WEST long pulse operation is Delayed due to a cryogenic issue.
PWIE.M.07 | Interpretative modelling of W migration and D retention in WEST high fluence discharges Completed. | 31/12/2022 | 30/06/2024 | delayed | WEST long pulse operation is Delayed due to a cryogenic issue.
PWIE.M.08 | Exposition of initial set of reference and advanced W materials for DEMO and JT-60SA in HHF and plasma devices executed. | 31/12/2023 |  | on track | 
PWIE.M.09 | 3D Modelling of first wall erosion and fuel retention in the DEMO-1 reference scenario Completed (TSVV-07). | 31/12/2023 |  | on track | 
PWIE.M.10 | Initial neutral particle code development done and interface to plasma boundary code coupling specified (TSVV-05). | 31/12/2023 |  | on track | 
PRIO.M.04 | Coupling of existing breakdown/burn-through models to the European Plasma Simulator (TSVV11 responsibility) | 31/12/2022 | 31/12/2023 | delayed | …The validation … will be performed during 2023.
PRIO.M.05 | European Plasma Simulator available for full pulse simulation | 31/12/2023 |  | on track | 
PRIO.M.06 | Integrate synthetic diagnostics in European Plasma Simulator | 31/12/2023 |  | on track | 
PRIO.M.16 | Completion of collection of Occupational Radiation Exposure and waste data | 31/12/2022 | 31/12/2023 | delayed | UKAEA manpower unavailability in 2022 causes delays (task PrIO 5.3.ORE-T001)
PRIO.M.17 | Completion of calibration verification at JET in DT operations | 31/12/2022 | 31/12/2023 | delayed | validated neutron calibration and data consistency not finalised by the JET operator and extension for DTE3
PRIO.M.18 | Completion of the analyses of measurements, simulations of JET nuclear quantities (neutron flux, dose rate, neutron induced activation, radiation damage) in DT and code validation | 31/12/2023 |  | on track | 

## Slide 5: Critical Risks status - FSD
WPID | Description of risk | Proposed Mitigation Measure | apply risk mitigation? | risk materialise? | Comments (grey text is spring 2023 update)
TE | SPI experiments are not conclusive in mitigating the disruption loads on tokamaks. | Find alternative mitigation solution to be developed on tokamaks | NO | NO | Awaiting experiments, so far no reason to apply mitigating action. SEVERITY changed from Medium to High, because there is no other options on the market at this point.
TE | Transferability of no/reduced ELM scenario to ITER and DEMO not feasible. | Increase focus on JT-60SA and the importance of stellarator research | NO | NO | Increase focus on JT-60SA and the importance of stellarator research
TE | Monitoring of the retention in metallic devices not sufficiently quantifiable | Develop alternative monitoring methods | NO | NO | Awaiting experiments, so far no reason to apply mitigating action.
W7X | Delay in the preparation of metallic wall operation for W-7X | Close monitoring of strategic planning (with large lead times), revision of resource allocation, cooperation with WPs in FSD and FTD | YES | YES | EEG grant works in the field from mid of 2023, project group is set up. Resources for neutral gas calculations kept on the same level as 2022.
W7X | Delay in the provision of the HELIAS physics basis | Close monitoring with FTD, support of database activities, enforcement of international collaborations | YES | YES | Continue task for the provision of data to databases. FTD collaboration not pursued but will be followed up to be resumed after the 2023 campaign. INCOs conducted.
AC | Reduced HPC availability for scientific use | Resource levelling and concentration on higher priorities | NO | NO | (no change)
PWIE | ADC conclusion on DEMO relevant DTT divertor comes too late to influence the procurement | Constant exchange with DTT on the schedule in relation to ADC divertor solution or increase of resources. | n/a | n/a | CLOSED risk
PWIE | Additional JET samples after DTE2 not available and ready for analysis (SP E) | Adjustment of the project resources according to the development of JET situation and potential association of UK to EURATOM. | YES | NO | (no change)
SA | High Beta, highly shaped plasma scenarios not reliable for long pulse operations | Consider a less demanding alternative scenario in view of its application in ITER and DEMO | NO | NO | (no change)
SA | Negative Ion Beams not enough energetic to give realistic insight on the high energy particles physics of ITER and DEMO. | Consider alternative heating techniques, e.g. using Ion Cyclotron schemes | NO | NO | (no change)
W7X, SA, TE, PrIO | Non-availability or delay of operation of unique facilities (e.g. W7X,NBTF, ELISE, JET...) due to technical issues | None | YES | YES | JT60-SA experiences further delays due to technical problems, therefore countermeasure are being taken (repair, development of auxiliary/additional systems, plans for saving time towards the scientific objectives)
TE,PWIE | Non-availability or delay of operation of facilities (Medium Size Tokamak, linear facilities) due to technical issues | Move the activities to other/ available facilities (international facilities could be also considered); bring forward preparatory actions | YES | YES | WEST is operational and the campaign is ongoing after merging content of the C2 with the C3 campaign
TE,PWIE | Delay of PEX and other critical upgrades | rescoping activities, resource levelling and reprioritization | NO | NO | (no change)

## Slide 6: Critical Risks status - PMU
WPID | Description of risk | Proposed Mitigation Measure | risk mitigation measures? | risk materialise? | Comments
PMU | Restrictions on the collaboration with Russia. | Search for alternative solutions (both in EU and through international collaboration). | Y | Y | FTD: We have looked for alternative irradiation possibilities. Several mitigation actions are being implemented, e.g., [1] for WPTFV: the DEMO pellet injection system will be developed completely in-house within the EU; and [2] research of alternative irradiation possibilities is being conducted (WPMAT, WPTFV, WPBB and WPDC).
PMU | External circumstances causes higher costs of operation of facilities and hardware purchase | No mitigation action for the occurrence. In case of occurrence, mitigation action: rescoping of the activity. | Y | Y | We are presently making a detailed budget overview to see where we are in terms of schedules, costs, planning to see whether we need to reprioritise. FTD, WPTFV: higher costs of DIPAK. A mitigation plan has been proposed and accepted by the DEMO Project Board (additional funds provided by KIT and some de-scoping).
PMU | External partner within international collaboration unilaterally change of priorities | Optimize the coordination between EUROfusion and external partners | Y | Y | FTD, WPSAE: Idaho National Laboratory (INL- US) will not integrate MELCOR 1.8.6 and the code TMAP. FTD, WPMAG: For the rebuilding of the EDIPO magnets, EPFL got a big funding from Switzerland and the EDIPO coils shall be procured from the Swiss budget and not from EUROfusion funds anymore. However, the Swiss funds will become available only in 2025, and beforehand it’s necessary to build and test a cable and a small coil by 2024. The manufacturing and test of prototype cable and coil demonstrators for the EDIPO rebuilt magnet would replace the old scope of the associated Grant Milestone (MAG.M.02), if the next amendment request is accepted by EC.