## Sheet1
Mission | Objective | Elements of the objective | WP(s) | SRL 2023 spring | SRL 2023 autumn | SRL 2024 spring | SRL 2024 autumn | SRL 2025 spring | SRL 2025 autumn | Comments (e.g. where progress is made and what is the result of it on the overall question? , what next?, ...) | Connection to Ds/Ms
| ITER scenario validated and optimised; DEMO scenario selected and investigated on EU machines | [8 empty] | Possible scenario investigated on JET |  | SCIENTIFIC READINESS LEVELS
M2 |  | Solutions to transient/ELM exhaust problem | TE / PWIE / TSVV/ W7X | Proof of concept, Initial experiment support, Qualitative emerging understanding | Proof of concept, Initial experiment support, Qualitative emerging understanding |  |  |  |  | the development of new elm free/small elm scenarios, ELM control mitigation through RMPs, ETC, … | TE.D.04 | Validated and Demonstrated Mature Science, transferable between machines
M2 |  | Solutions to exhaust problem (divertor design, Detachment, seeding, ...) | TE / PWIE / TSVV / W7X | Proof of concept, Initial experiment support, Qualitative emerging understanding | Proof of concept, Initial experiment support, Qualitative emerging understanding |  |  |  |  | Development of ADCs, detachment control, predictions of lambda q to ITER and DEMO parameters, and the physics of SOL turbulence and transport | TE.D.02, TE.D05, TE.D.08, TE.D.09, TE.D.11, TE.D.12, TE.D.13, PrIO.D.05, PWIE.M.02, PWIE.D.18 | Consolidated Science, End to End performance Simulations, Quantitative understanding
M1 |  | Assesment on Heating mix compatible with the scenarios | TE / W7-X / SA | Consolidated Science, End to End performance Simulations, Quantitative understanding | Consolidated Science, End to End performance Simulations, Quantitative understanding |  |  |  |  | Special view on DEMO and ITER available heating methods and eventual impact on scenario and control | TE.D.10 | Proof of concept, Initial experiment support, Qualitative emerging understanding
M1 |  | Assesment on the fuel mix/isotops/impuritries | TE / PWIE / TSVV / W7X | Consolidated Science, End to End performance Simulations, Quantitative understanding | Consolidated Science, End to End performance Simulations, Quantitative understanding |  |  |  |  | steady state control of the fuel mix profiles and the impurity content demonstrated | TE.D.09, TE.D.13 | Consolidated Idea and Observation-Experiment Requirements, Well defined idea on how to solve issue advance understanding
M1 |  | Assessment of high beta, highly shaped plasma scenario in long pulse operation | SA / TE / W7X | Consolidated Idea and Observation-Experiment Requirements, Well defined idea on how to solve issue advance understanding | Consolidated Idea and Observation-Experiment Requirements, Well defined idea on how to solve issue advance understanding |  |  |  |  | Development of the control schemes of long pulse at high β | TE.M.02 | Initial Scientific Idea
M1 | Integrated predictive capability/control for a plasma scenario (flight simulator) | [8 empty] | Initiation to end simulation validated on at least one device and extended to others | TE.D.06, TE.D.11, PrIO.D.01, PrIO.D.02, PrIO.D.04, PrIO.D.06, PrIO.D.07
M1 |  | Integrated modelling, edge to core, including detachment | TE/ PWIE/ TSVV/ W7X/ AC/ SA | Proof of concept, Initial experiment support, Qualitative emerging understanding | Proof of concept, Initial experiment support, Qualitative emerging understanding |  |  |  |  | Simulations for ITER performed, a range of parameters tested and validated on TE machines.
M1 |  | Disruption control (mitigation, avoidance) | TE / TSVV/ SA | Consolidated Science, End to End performance Simulations, Quantitative understanding | Consolidated Science, End to End performance Simulations, Quantitative understanding |  |  |  |  | Mitigation capabilities for disruptions demonstrated for a number of disruption scenarios with a high reliability (tbd) | TE.D.07, TE.D.14
M1 |  | Transferability of Scenarios between machines | TE / TSVV | Consolidated Science, End to End performance Simulations, Quantitative understanding | Consolidated Science, End to End performance Simulations, Quantitative understanding |  |  |  |  | Physics of scenarios clarified, access identified, modelled and successfully transferred to another machine) if possible, else reason identified why scenario is not achievalbe on other machine
M1 |  | Integrated modelling with fast ion stabilisation | TE / TSVV / W7X/ SA | Proof of concept, Initial experiment support, Qualitative emerging understanding | Proof of concept, Initial experiment support, Qualitative emerging understanding |  |  |  |  | A reduced model implemented and simulations achieved_validated on at least one device and extended to others
M1 |  | Capability of modelling ITER discharge from the breakdown to current ramp-up termination, from the plasma axis to the wall | TSVV / PrIO / TE | Consolidated Idea and Observation-Experiment Requirements, Well defined idea on how to solve issue advance understanding | Consolidated Idea and Observation-Experiment Requirements, Well defined idea on how to solve issue advance understanding |  |  |  |  | A numerical package capable of performing simulations as described in the objectives, validated on TE machines and availble to users on the Gateway (including the manual and the documentation) | PrIO.M.01, PrIO.M.02, PrIO.M.04
M1 |  | IMAS format implemented across EUROfusion for the exchange of numerical and experimental data | TSVV / TE/ PrIO/ SA | Consolidated Idea and Observation-Experiment Requirements, Well defined idea on how to solve issue advance understanding | Consolidated Idea and Observation-Experiment Requirements, Well defined idea on how to solve issue advance understanding |  |  |  |  | I/O of codes developed within TSVV is adapted to IMAS format. + routines (converters) available for all TE experiments to convert at least the required minimum set of data from local to IMAS format
M2 | PFC materials | [9 empty] | PWIE.D.01-25
M2 |  | Material lifetime and performance | PWIE | Consolidated Idea and Observation-Experiment Requirements, Well defined idea on how to solve issue advance understanding | Consolidated Idea and Observation-Experiment Requirements, Well defined idea on how to solve issue advance understanding |  |  |  |  | Test of W PFMs either post-mortem or produced in lab, high fluence experiments, HHF experiments, incl. synergistic effects by impurities, neutron damage or self-damage | TE.D.03, PWIE.D.01, 04-08, 14, 20-21, 23-24
M2 |  | T retention | PWIE | Consolidated Science, End to End performance Simulations, Quantitative understanding | Consolidated Science, End to End performance Simulations, Quantitative understanding |  |  |  |  | Test of W and Be PFMs, incl. synergistic effects by impurities, HHF, neutron damage or self-damage | TE.D.03, PWIE.D.05, 07-08, 11-13, 16-17, 19, 21-24
M2 |  | T-retention in DEMO relevant materials under synergetic neutron load | PWIE | Consolidated Idea and Observation-Experiment Requirements, Well defined idea on how to solve issue advance understanding | Consolidated Idea and Observation-Experiment Requirements, Well defined idea on how to solve issue advance understanding |  |  |  |  | T retention in W and EUROFER, incl. synergistic effects of impurities, HHF, neutron damage or self-damag | TE.D.03, PWIE.D.05, 07-08, 11-13, 16-17, 19, 21-24
M1 | EUROfusion ITER operation planning/preparation | Review of EUROfusion capabilities in support to ITER operation and proposal of EUROfusion strategy for involvement in ITER operation (Efficient start-up of large superconducting devices) | PrIO/ SA | Consolidated Idea and Observation-Experiment Requirements, Well defined idea on how to solve issue advance understanding | Consolidated Idea and Observation-Experiment Requirements, Well defined idea on how to solve issue advance understanding |  |  |  |  | Mode of EU participation in ITER Ops clarified. Input to be provided for GA, F4E, EC and IO interaction. | PrIO.D.10
M5 | Neutronics and safety | Support of the preparation of ITER nuclear phase, and early support to DEMO | PrIO | Consolidated Idea and Observation-Experiment Requirements, Well defined idea on how to solve issue advance understanding | Consolidated Idea and Observation-Experiment Requirements, Well defined idea on how to solve issue advance understanding |  |  |  |  | Nuclear codes validated (neutron flux, neutron streaming for shutdown dose rate calculation, materials activation, water activation, neutron calibration etc) using JET DTE2, DTE3 data and specific EU facilities (e.g. FNG, TRIGA) for water activation and activated corrosion products experiments. Does the code need acceptance by regulators? | TE.D.15, PrIO.D.22,23,24,25,26, 28
M8 | Stellarator as viable option |  | W7X | [6 empty] | High density, high ion temperature scenario in steady state on W7X | W7X-D.01-15
M8 |  | Integrated predictive capability/control for a plasma scenario (flight simulator) | TSVV (W7X) | Consolidated Idea and Observation-Experiment Requirements, Well defined idea on how to solve issue advance understanding | Consolidated Idea and Observation-Experiment Requirements, Well defined idea on how to solve issue advance understanding |  |  |  |  | Initiation to end simulation validated on W7-X | W7X-D.03, W7X-D.02