## ACH_Tasks_2024
ACH tasks planned for 2024
Tasks recommended for ACH support in 2024:
ACH | Customer Project/WP | Code | Project Coordinator | Priority | PM's requested | PM's estimated | ACH team members | Tasks description | Comments
CIEMAT | ACH | management | Mervi Mantsinen |  | 3 | 3 | Mervi Mantsinen | management of ACH activities | rate agreed by the E-TASC SB
CIEMAT | TSVV-03 | BIT1 | David TSKHAKAYA | high | 2 | 3 | Fusion group (X. Saez; A.Silanes; new recruiment) | Pursue GPUization of code. Target: first production run on Leonardo by end of 2024. | Task distributed between TSVV3, TSVV4 and TSVV7 for a total of 6pm
CIEMAT | TSVV-04 | BIT1 | David TSKHAKAYA | high | 2 | 3 | Fusion group (X. Saez; A.Silanes; new recruiment) | Pursue GPUization of code. Target: first production run on Leonardo by end of 2024. | Task distributed between TSVV3, TSVV4 and TSVV7 for a total of 6pm
CIEMAT | TSVV-04 | GENE-X | Philipp Ulbl | high | 6 | 6 | M.Garcia's team & Fusion group (tbd) | GENE-X is a full-f gyrokinetic continuum code implementing a locally field-aligned coordinate system following the flux-coordinate independent approach. The implementation is based on a hybrid OpenMP and MPI parallelization that was successfully tested up to 512 compute nodes and against the Roofline model. To improve the cache usage of GENE-X, we would like the ACH to optimize the memory access patterns. This shall be achieved by reordering the unstructured computational grid. The tasks for ACH are: • Implementing the ability to access the unstructured computational grid in arbitrary order • Testing the performance of different reordering strategies
CIEMAT | TSVV-07 | BIT1 | David TSKHAKAYA | high | 2 | 3 | Fusion group (X. Saez; A.Silanes; new recruiment) | Pursue GPUization of code. Target: first production run on Leonardo by end of 2024. | Task distributed between TSVV3, TSVV4 and TSVV7 for a total of 6pm
CIEMAT | TSVV-07 | ERO2.0 | Juri Romazanov | high | 6 | 10 | 6PM Fusion group (A. Silanes); 4PM M.Garcia's team | HPC optimization, GPU enabling | Continuation of ongoing project
CIEMAT | TSVV-07 | SPICE2 | Michael Komm | high | 10 | 12 | Fusion group (A. Soba) | Domain decomposition, GPU solver, improvement of code portability & availability | Continuation and extension of ongoing project
CIEMAT | TSVV-08 | JOREK | Matthias Hoelzl | high | 12 | 12 | Fusion group (F. Cipolletta) | JOREK-CARIDDI eddy current coupling for 3D plasma 3D wall simulations has been completed by TSVV 8 in 2023. Optimization of the coupling between JOREK and CARIDDI is needed for high resolution cases (plasma resolution as well as wall resolution); a substantial step was taken here already in 2023 with CIEMAT ACH support, but that has to be continued in view of full MHD coupling and halo current coupling, which are both under development and introduce a significant number of new coupling terms | Federico Cipolletta would be an excellent person to work on this due to experience from this year
CIEMAT | TSVV-10 | XTOR-K | Hinrich Lütjens | high | 4 | 12 | Fusion group (X. Saez, A.Silanes) | Porting XTOR-K onto GPU systems | BSC has proposed to port XTOR-K onto GPU’s. From the developer side, this transfer has been prepared including typical run cases and tests of the results. The code is ready now with both full trajectory and guiding centre particle integrators working in all configurations
CIEMAT | TE | SOLPS | David Coster | medium |  | 12 | D. Vicente's team | Continue work started in 2023 along the following lines: (1) Identify and exploit new other multi-threading opportunities, in particular in newer parts of the code, such as the ones related to the dynamic time-dependent mode (b2news_m routines and those called within), and the new routines related to the Zhdanov closure. (2) For coupled runs in which both the B2.5 and Eirene components are meant to run using their parallelized versions, propose compiler options and/or job submission script instructions (on as wide a variety of compilers and platforms as possible) that allow for an optimal use of the available CPU resources by enforcing the regular re-assignment of these resources from MPI to OpenMP tasks and back. (3) Consider possible vectorization of the code wherever profitable for use on Cray platforms like on the JFRS cluster at IFERC.
CIEMAT | TSVV-13 | STELLA | Michael Barnes | high | 5 | 6 | 5PM M. Garcia's team; 1 PM Fusion group | stella’s implicit treatment of parallel streaming is made possible by a Green’s function approach that requires pre-computation and LU factorization of a response initialization matrix. For simulations requiring high resolution in both the radial and parallel-to-the-field coordinates, the computation of the LU decomposition has until recently been a bottleneck, and has required its parallelization and distribution of the memory demand. At present, the code can carry out the matrix inizialization distributing it across he CPUs of a single node, independently on whether more than one node is requested in the simulation. If more than 1 one node is requested, there is no speed-up in the calculation of the initialization matrix. The present task aims at enabling the LU factorization across all the nodes requested for the simulation when the number of nodes requested is more than 1 in order to reduce the time spent by the code in the inizialization and to afford finer resolution and larger size of the computation domain. Part of this task began in 2023 but has not been accomplished and must be continued and finished in 2024.
82

## Rejected_projects
Rejected/Postoned Projects
Project Acronym | Project Coordinator | Customer Project/WP | Priority | PM's requested | PM's estimated | ACH (requested in the proposal) | Tasks required | Comments on reasons for rejection

## ACH_manpower balance
ACH | Planned Resources (as in IMS) | Relocation of 2022 resources (requested by PIs) | Management | TSVVs | ENR | W7X | PrIO | TE | OTHER | Balance
CIEMAT | 72 |  | 3 | 67 | 0 | 0 | 0 | 12 | 0 | -10
EPFL | 72 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72
IPPLM | 108.4 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108.4
MPG | 108 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108
VTT | 96 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96
| 456.4 |  | 3 | 67 | 0 | 0 | 0 | 12 | 0 | 374.4