## Slide 1: LID project schedule risks and mitigations
6.4.2020 I Miroslaw Zlobinski

## Slide 2
LID schedule risks
A list of delays in EUROfusion projects due to Corona will be submitted from EUROfusion to EU commission as a bundle. We can add our project specifying affected project tasks, explanation and prolongation duration.
Project task | Issue | Prolongation
supply CAT drawing and model of JET | CATIA DMU is not functioning correctly (due to remote access ?) | ???
Evaluation of JET model (laser accessible area, max. laser diameter etc.) + Iteration of mechanical and optical design | teamwork decelerated due to remote work | few weeks
Information on specifications of JET components (fibres, lenses e.g. lens on KZ3 penetration tube etc.) | delayed due to missing access to torus hall and/or office | CCFE shutdown duration
Determination of RGA sensitivity in experimental tests at JET (GIMs, Laser blow-off, TS, …) | JET is out of operation | JET shutdown duration
… |  | 

## Slide 3
probably unaffected tasks and mitigation strategy
Design of the LID target plate and mechanical, magnetic, thermal analysis by simulations (ANSYS)
Definition of main system parameters
Assume that missing CAT part behind laser window is not limiting the laser beam.
Once we have a sufficient CAT model, the mechanical and optical design process can start.
If specifications of JET components cannot be determined, we could continue with the choice to replace them by new and known components.
If RGA sensitivity tests cannot be conducted, we could assume them to be successful as the first test were promising. If sensitivity yields to be too low, still multi spot accumulation by rastering of target should overcome this.

## Slide 4
Completion of concept design phase
Until now we focused on mirror guided laser beam from roof lab to target: needed: First (rough) ZEMAX model to indicate which laser divergence acceptable (=> laser choice)
new possibility discovered by M.M. recently: 4 radiation hard fibres (2 good) in torus hall that were inspected for pyrometer IR light => fibres could be used for laser guiding
  simplifies optical setup considerably as mirror beam guidance not necessary (only last mirrors)
  very sharp beam edge
  pyrometer measurement in laser spot straightforward
  specifications of these 30 year old fibres unknown, absolute transmission unknown,
  spectral transmission already measured and good in laser range and IR for pyrometry alternative: new similarly doped fibres
A.M. on last meeting: We should extend concept phase initially in proposal: until August then changed in PMP: June extend concept phase or mainly pursue initial plan (mirror based), fibre guidance as backup