## Slide 1: Points to address (1)
  Review of call content
  Choice of PI
    I can act as PI for the 2-year extension, but I am also fully open to a change
    Decision made that Patrick will be PI
  Project team
    I propose to keep the same teams contours and global balance
    PPY reduction to apply (7ppy -> 6ppy), 2 options:
      Apply uniformly across the board (-15%)?
      Be more selective (longer & complex discussions)
    Consensus for uniform reduction on all teams

## Slide 2: Points to address (2)
  Project content: our draft is an accurate answer to the call
    High priority topics explicitly mentioned in call: task 1 (dissipative regimes), task 3 (non-axi configurations), task 4 (validation against scaling laws), task 6 (HPC performances)
    Other topics not explicitly mentioned in call but we should keep: task 2 (high confinement modes), task 5 (higher fidelity models), task 7 (standard software)
    Need to revisit each of the tasks to adapt the scope according to the ppy reduction (URL: https://docs.google.com/document/d/19Azg_PbIbJBCAdTUlsmylAhJ1yn59-30/edit?usp=sharing&ouid=116675827872058805499&rtpof=true&sd=true)
  Planning of preparation of answer: due date September 19th
    July 18th: finalization of ppy distribution (by e-mail)
      Local team leaders: launch preparation of commitments letters by all beneficiaries
      All: Prepare CVs for all contributors following provided template
    August 20th: refinement of draft answer to call to adapt ambitions to resources => review of draft status at bi-weekly meeting
      all: final polishing plan and deliverables
    September 3rd: final discussion validation of draft by all
      PI: cast into expect template
    September 10th: validation by all of final document