## Slide 1: SP X kick-off meeting – VTT task in 2024
Antti Hakola

## Slide 2: Deliverable and foreseen work plan
Deliverable | Title | Volume (PM)
D009 | (CF-)LIBS on Be containing coatings with different type of fuel content (VTT) | 2
This deliverable is considered as a supporting activity for the LIBS@JET project (under SP E)
analysis of Be test samples and existing JET samples using the foreseen setup for LIBS@JET
developing methods and processes for efficient analysis of the measurement data obtained from the measurements and later on from JET
The work plan consists of the following steps
commissioning of the new LIBS setup at VTT laboratory
carrying out a measurement campaign with external collaborators (ENEA, UT, CU, IPPLM,…) at VTT
analysis of the obtained data and drawing conclusions for LIBS@JET

## Slide 3: Status of activities
Deliverable | Title | Volume (PM)
D009 | (CF-)LIBS on Be containing coatings with different type of fuel content (VTT) | 2
LIBS box (for LIBS@JET) with accessories arrived at VTT – 01/2024
  Includes spectrometer from ENEA, optical fibre from IPPLM, and a replacement Montfort laser (ns pulses)
Commissioning of the system scheduled with ENEA – 19-23 February, 2024
Actual ps laser expected to arrive in Week 10 - 4-8 March, 2024
Measurement campaign with all collaborators in Weeks 11/12 – 11-22 March, 2024
  Focus on bulk Be samples and W-coated CFC samples from earlier JET exposures
  Concentrate on determining the retention profiles of D (and other isotopes if applicable)
LIBS system to be shipped to JET (tentatively) in Week 13 – after 25 March, 2024
Plan B under discussion – ex vessel experiments at JET later in the spring in case of delays