## Slide 1: High level JT-60SA project summary
Research phase | Focus of exploitation | Operation Campaign | Expected operation schedule |  | RH | Divertor | Installed NB power | ECRF | Max. usable aux. power
- | Integrated pre-plasma Commissioning | Op-1 | 2020-2021 (6M) 2023 (6M) First plasma 2023 | H | R&D | Open upper inertially cooled carbon | 0 | 1.5 MW (2 Gryo.) | 1.5MW
Initial research phase I | Initial stable and reliable operation H operation for commissioning towards D operation. Stable operation at high current heated plasma |  |  |  |  |  |  |  | 
 |  | Op-2 | 2025-2026 (9M) |  |  | Inertially cooled lower pumped carbon | 16MW (with H) 23.5 MW (with D) PNB 8 units, plus NNB) | 3.0 MW (4 gyro) | 19MW
 |  |  |  | D |  |  |  |  | ~26MW (limited by divertor cooling)
Initial research phase II | ITER and DEMO regime access (high power and high Ip with short pulses) Acces to the ITER standard scenario High beta access ITER risk mitigation (ELM, disruption) | Op-3 | 2026-2027 (9M) |  |  |  |  |  | 
 |  | Op-4 | 2027-2028 (8M) |  |  |  | 30 MW (PNB 12 units, plus NNB) |  | 33 MW
Integrated research phase I | High beta long pulse Burning plasma relevant ITER standard and hybrid stationary (~2-3tR) High beta steady-state (~2-3tR), DEMO contribution | TBD | TBD |  |  | Actively cooled lower pumped carbon |  | 7MW (9 gyro.) | 37MW
Integrated research phase II | High beta and metal wall compatibility Radiative divertor with impurity seeding Impurity pumpout from core | TBD | From ~2030 (TBC) |  | Use | Actively cooled lower pumped tungsten |  |  | 
Extended research phase |  | TBD | >5y |  |  | Actively cooled tungsten advanced structure (Upper div. TBC) | 34MW |  | 41MW