## PB-05 (30.10.24)
WP | PCR proposal description | PCR justification | PSD evaluation (department scope, resources, schedule, risk) | PSD decision | WP Resources requested
WPW7X | Complete the HELIAS physics basis and develop high performance scenarios for W7-X | Enhance the involvement of the CIEMAT team in studies related to HELIAS physics to expedite progress and ensure timely readiness for the decision point regarding the HELIAS-based reactor. | Funding source: redistribution within the WP Scope retained, however activities for the Gyrotron project are partially reduced (lack of personnel) | approved | 24PM CIEMAT (81.8k€ CC)
WPW7X | Increase the efforts on the analysis and modelling for OP2.2 & OP2.3 | Increased expenditures driven by the emphasis on 'high beta' and 'long pulse' research in OP2.3, aimed at studying divertor physics in high-beta discharges, as well as the behavior of impurities and filaments at the plasma boundary. | Funding source: redistribution within the WP and transfer of 12.5PM unspent 2024 resources (49k€ CC) from WPSA Scope retained | approved | 12PM FZJ (54k€ CC); 12PM IPPLM (24k€ CC); 18PM EK-CER (32k€ CC)
WPW7X | Increase missions budget in 2025 | Bringing mission budget to the level of 2024 is essential; otherwise, participation in the campaign could prove inadequate, significantly increasing the risk of not achieving the 2025 objectives and overall deliverables. | Funding source: redistribution within the WP | approved | 63k€ CC
PWIE | Preparation of transition to W for JT-60SA | Expertise is within WPPWIE | Funding source: SA 2024 unspent 12PM not allocated (47k€ CC) Scope retained | approved | 12PM not allocated (47k€ CC)
TE | Increase campaign participation | COMPASS-U is not operational. In 2025 TE increases the use of the operating facilities. EUROfusion increases its machine time within the facilities. | Funding source: redistribution within the WP using resources of COMPASS-U operation from 2024 and 2025 (2024: 76.7k€ CC; 2025: 103.2k€ CC) | approved | 179.9k€ CC

## Sheet1
PB decision
Approved
Approved, subject to changes
Revision requested (referring back to PB)
Rejected
Refer to GA