## PB-05 (30.10.24)
WP | PCR proposal description | PCR justification | PSD evaluation (department scope, resources, schedule, risk) | PSD proposal for decision | Brief WP impact assessment |  |  |  |  | PB decision
[5 empty] | WP Scope | WP Resources | WP Schedule | WP Risk | other WP
WPW7X | Identify stellarator DEMO physics gaps and research priorities in collaboration with SPPS inside WPPRD (similar exercise as was done for tokamak DEMO) | Concept of stellarator DEMO is not defined as yet | Funding source: SA 2024 unspent 24PM not allocated (94k€ CC) | approve | increase of scope, high relevance for the stellarator line | 24PM (94k€ CC)
WPPWIE | Facility costs increase and hardware increase | Cost increase of facility operation. This is due to additional diagnostics, capabilities as well as general machine cost. Same number of machine days maintained as previous years. | Funding source: PrIO released secondments 200k€ (not allocated) and 11.5PM NBTF allocated to EPFL (76k€ CC) | approve | scope retained | 140kCC -TOMAS (40 days) ~35 k€ in addition -GYM (30 days) ~35 k€ in addition -ion beam facilities + new facilities to analyse samples ~50 k€ -additional consumables (e.g. bor gas) beyond what is in stock ~ 20k€
WPPWIE | Increase Mission budget in 2025 | Bringing mission budget to the level of 2024 is essential; otherwise, no participation in the activities is possible, significantly increasing the risk of not achieving the 2025 objectives and overall deliverables. |  | approve | scope retained | 100k CC missions |  | n.a.
WPPWIE | Support in analysis and interpretation of boron retention analysis matrix and new sets of experiments and diagnostics | New device developed in IAP with usage of diborane to produce B layers with D content. Producktion of samples to ass D fuel content as fucntion of impact energy, temperature etc. Analysis of samples in different labs. |  | approve | Increase of scope: High priority studies for ITER regarding boron layers for O reduction, W supression and D retention are added. | 12PM IAP (36k€ CC) |  | n.a.
WPPWIE | JULE-PSI budget redistribution to a number of tasks (including campaign missions) | JULE-PSI not available in 2025 due to transfer into HML. Reuse of budget according to risk mitigation scheme by transfer to other linear facilties. Refocusing work on boron layers instead of beryllium foreseen before change of ITER baseline in the WP plans. Use of linear machines with in-situ boron layer analysis regarding retention and erosion as well as fuel removal. | Funding source: JULE-PSI budget | approve | Original scope with GD (D15 and D21) is no longer achievable within the 5 years Grant period. Increase of scope: High priority studies for ITER regarding boron layers for O reduction, W supression and D retention. In-operando or in vacuo studies in linear machines with ion-beam, LIBS or material samples without air exposure. | 517k€ CC |  | risk materialized
WPTE | increase missions budget in 2025 | Bringing mission budget to the level of 2024 is essential; otherwise, participation in the campaign could prove inadequate, significantly increasing the risk of not achieving the 2025 objectives and overall deliverables. | Funding source: redistribution within WPTE and transfer from WPSA of - 2025 missions 240k€ CC; - 2025 secondments 106k€ CC (incl. missions for ET); - 2024 secondments 14k€ CC; | approve | scope retained | 376k€ CC missions
SA | Possible support for VNS/DEMO1, TSVV related and DTT activities pending decisions of GA and recommendations of E-TASC SB | To address dynamic programmatic needs | funding source: SA 2024 unspent 33PM not allocated (129k€ CC) | approve | increase of scope | 33PM (129k€ CC)
INCO/SA | Funding the topical coordinators for BEST Research Plan and related analysis and modelling | Assess potential value of the new device for European Programme | funding source: PrIO 2024 unspent Session leader training 8PM not allocated (31k€ CC) and WPSA 2024 unspent 24PM not allocated (94k€ CC) | approve | increase of scope | 8PM (31k€ CC) +24PM (94k€ CC)

## Sheet1 (hidden)
PB decision
Approved
Approved, subject to changes
Revision requested (referring back to PB)
Rejected
Refer to GA