## Slide 1: Financial Overview
E. Genangeli, L. Grella, P. Haucke, Y. Kotsehub,
M. Farawana, M. Oron-Carl
PMU Admin & Coordinator Unit
PSD-DSD Project Board #5 30th October 2024

## Slide 2: EC Evolution of 2021-25 budget
(CC M€)
2023 Budget decreased by -0.5M€  unused PMB and PSB was moved to 2024.
2024 Budget decreased by -1.15M€:
  PMB/PSB left over shift to 2024 (+0.5M€)
  Shift to EPFL (-0.2M€)
  Shift to IRs 2025 (-1.5M€) within the same WP or to another (PCR) as below: PrIO (-0.45M€), SA (0.42M€), PWIE (-0.28M€), AC (0.18M€), W7X(-0.15M€) and TE (0.02M€).
2025 Budget increased by +1.3M€ :
  Shift to EPFL (-0.4M€): AC-TSVV.15 tasks implementation and additional SA staff costs;
  Impact of salary rate change (+0.2M€);
  Shift from 2024 (+1.5M€) as below PWIE (+0.56M€), TE (+038M€), W7X (+0.19M€), AC (+0.18M€), PrIO (+0.14M€) and SA (+0.04M€).
PMB = Planned Mission Budget
PSB = Planned Secondment Budget
IMS data export 22.10.2024

## Slide 3: Resources 2021-25 EPFL and UKAEA
EPFL:
2024 Budget increased by +0.2M€ mainly in TE (2024 camp);
2025 Budget increased by +0.6M€:
impact of salary rate change (+0.2M€);
implementation of AC-TSVV.15 (+0.15M€);
increase of EPFL Staff costs in WP SA (+0.15M€);
increase of EPFL Staff costs in WP PrIO (+0.1M€);
UKAEA (Total resources)
2024 Budget increased by +0.1M€ mainly in PWIE (3 new 2024 del: 11 PM50%) and TE (2024 camp)..
2025 Budget decreased by -0.2M€  reduction of staff costs in WP SA

## Slide 4: Not Allocated Resources
(CC M€)
2024
2M€ CC of resources Not yet Allocated:
  TE (+1.3M€): +1.0M€ camp and +0.3M€ TE-4 Enhancements (EQ/OGS);
  SA (+0.2M€): Mission Budget;
  ENR (+0.2M€): Mission Budget;
  PrIO (+0.1M€):Mission and Secondment Budget;
  W7X (+0.15M€): Mission Budget;
  PWIE (+0.04M€): Mission Budget;
  AC (+0.01M€): Mission Budget.
2025
15.1M€ CC of resources Not yet Allocated:
  TE (+8.4M€): +4.8M€ ScientExploit, +3.4M€ PCRs money and +0.2M€ ENH;
  AC (+2.1M€): mostly PCR for LTSF not approved;
  PWIE (+1.8M€): +1.5M€ PCRs money and +0.3M€ shifts from 2024;
  W7X (+1.2M€): +1M€ PCRs money and +0.2M€ Budget for missions;
  SA (+0. 7M€): +0.4M€ staff costs, +0.2M€ Mission budget and +0.1 PCRs money;
  PrIO (+0.7M€): +0.3M€ PCRs money and +0.3M€ Budget for missions and Secondments and +0.1M€ staff costs;
  ENR (+0.1M€): Mission Budget.

## Slide 5: EC 2024 Budget update
SA: unused funds redirected to other WPs (PCRs)
PrIO: unused funds redirected to other WPs (PCRs)
AC: implementation of TSVV15, funds moved from 2024 to 2025
PWIE: unused funds shifted to 2025
W7X: unused funds shifted to 2025
ENR: unused mission budget from 2023

## Slide 6: EPFL and UKAEA 2024 Budget update
TE: Campaign
AC: TSVV 15
PrIO: NBTF
TE: Campaign
PWIE: Additional PM

## Slide 7: EC 2025 Budget update
2025 Indicative Resources

## Slide 8: EPFL and UKAEA 2025 Budget update

## Slide 9: PSD+DSD reporting and projection (EC Contribution)
It looks good thanks to
he Accompanying Research,
But
what if AR is not reported?

## Slide 10: 2023 IMS deliverables status of achievement
w/o EPFL and UKAEA
54 deliverables not yet achieved out of 1001, for an amount of ~1M€ to be withheld from 1st payment 2023
Status as of
31st August 2024

## Slide 11: 2023 Missions planned vs reported
Total budget approved: 1.5M€
Reported: 1.2M€
Will be reported: 0.1M€
Unused (?): 0.2M€

## Slide 12: Conclusion
Underspending trend continues
1.5M€ already shifted to 2025 further shifts may be requested in the coming weeks (e.g. part of the 2M€ non yet allocated)
Data shows that the budget for missions is not fully used, nevertheless the WPs continue asking of an increase
Projection of costs reported vs budget shows that a fraction of 2024-25 resources will (potentially) be used in 2026-27
Level of the 2026-27 budget is not yet known

## Slide 13
THANK YOU