## Slide 1: TE Enhancements Questionnaire - Analysis
    TE Enhancements Questionnaire - Outcome
    The assessment is that currently there are no major delays but this and the evolution of the projects will be looked into again at the next review point.
    The delays focus mostly on questions Q1 to Q5.
TE Enhancements Questionnaire - Procedure
The PIs are to complete a status review process which is to be requested 3 times a year – 15 January, 15 May, 15 September
Questions focus on design (Q1), installation (Q2), plasma commissioning (Q3), deliverables/milestones (Q4), reporting (Q5), human resources (Q6), procurement (Q7), missions (Q8)
Replies use a traffic light based replies [to help obtaining feedback uniformity]
    Green – Everything progressing as planned no delays.
    Yellow – There are delays but it’s not foreseen they will impact the agreed deadline for the completion of the project.
    Red – There are delays and it’s foreseen they will impact the agreed deadline for the completion of the project.
    Replies are scored in the following away: Green - 1; Yellow - 0.5; Red - 0
  Text replies - If the status for any question is red, yellow or if the question so requires the PI is to provide a written answer as well.
    The PIs have been made aware that it is important to be as accurate and realistic as possible to maintain an updated clear picture of the allocated resources that might not be needed for any given year.

## Slide 2: TE Enhancements Questionnaire - Analysis
Proposal Title | Code | PI Name | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Average (%)
Direct Digital Synthesis for the O-mode Profile Reflectometer at ASDEX Upgrade | AUG: DPR | António Silva |  |  |  |  |  |  |  |  | 0
Runaway electron mitigation and velocity analysis by magnetic-ripple manipulation [at TCV] | TCV: REMR | Umar Sheikh | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1.0 | 1.0 | 63
LIBS4FUSION: in-vessel fuel Inventory and deposited layers composition in a full tungsten device | WEST: LIBS | Arnaud Bultel | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 1.0 | 1.0 | 1.0 | 69
ONCOMING-Optimized taNgentially spaCe resOlved geM ImagiNG [at MAST-U] | MAST-U: GEM | Andrea Muraro | 1.0 | 0.5 | 0.5 | 1.0 | 1.0 | 1.0 | 0.5 | 0.5 | 75
Upgrade of the TCV ECRH high voltage power supply | TCV: ECRH | Damien Fasel | 0.5 | ---- | ---- | 1.0 | 1.0 | 0.5 | ---- | ---- | 75
High DEfinition Visible Endoscope for WEST | WEST: HIDEVE | Philippe Moreau | 1.0 | 0.5 | 0.5 | 0.5 | 0.5 | 1.0 | 1.0 | 1.0 | 75
Neutron Detectors suite for 14 MeV neutron triton burnup and 2.5 MeV neutron spectroscopy measurements at MAST Upgrade | MAST-U: NSU | Davide Rigamonti | 0.5 | 1.0 | 1.0 | 0.5 | 0.5 | 1.0 | 1.0 | 1.0 | 81
New 100-Hz Laser for the TCV Thomson Scattering System | TCV: TS | Benjamin Vincent | 1.0 | 1.0 | 1.0 | 0.5 | 1.0 | 1.0 | 0.5 | ---- | 86
Real-time control system for ELM buffering at ASDEX Upgrade | AUG: RTCS | Michael Komm | 0.5 | 1.0 | 1.0 | 1.0 | 1.0 | 0.5 | 1.0 | 1.0 | 88
Collective Thomson Scattering (CTS) diagnostic for TCV | TCV: CTS | Laurie Porte | 0.5 | 1.0 | 1.0 | 1.0 | 0.5 | 1.0 | 1.0 | 1.0 | 88
IRBO IR Bolometry for WEST | WEST: IRBO | Pascal Devynck | 1.0 | 1.0 | ---- | 1.0 | 1.0 | 1.0 | 0.5 | ---- | 92
Tungsten impurity monitoring and control at the COMPASS-U tokamak | COMPASS-U: SXR_IR_ECH | Martin Hron | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 0.5 | 1.0 | 94
Characterisation of advanced confinement modes at COMPASS-U | COMPASS-U: TS | Petra Bilkova | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 0.5 | 1.0 | 94
Upgrade of the TCV LHPI antenna | TCV: LHPI | Joan Decker | 0.5 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 94
FIRE&GO - Fast Ion Research Enhancements and Gamma-ray Observations [at ASDEX] | AUG: GNS | Massimo Nocente | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 100
Real-time spectroscopy at ASDEX Upgrade | AUG: RTS | Marco Cavedon | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 100
Ultra-fast-swept profile reflectometer on AUG | AUG: UFR | Garrard Conway | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 100
PFCs and diagnostics for power exhaust studies at COMPASS-U | COMPASS-U: PFC | Renaud Dejarnac | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 100
Implementation of the 4th dual-frequency gyrotron for TCV | TCV: Gyro | Jean-Philippe Hogge | 1.0 | 1.0 | ---- | ---- | 1.0 | 1.0 | ---- | ---- | 100
Runaway Electron Mitigation Coil for TCV | TCV: REMC | Umar Sheikh | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 100
Boronization Probes for WEST | WEST: BORO | Mathilde Diez | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | ---- | 100
Fast Ion Loss Detector in WEST | WEST: FILD | Samuele Mazzi | 1.0 | ---- | ---- | 1.0 | 1.0 | 1.0 | ---- | 1.0 | 100
A RETARDING FIELD ANALYZER FOR ION TEMPERATURE MEASUREMENTS IN THE SOL OF WEST | WEST: RFA | James Gunn | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 1.0 | 100

## Slide 3: TE Enhancements Questionnaire - Analysis
Proposal Title | Code | PI Name | Average (%) | Comments
Direct Digital Synthesis for the O-mode Profile Reflectometer at ASDEX Upgrade | AUG: DPR | António Silva | 0 | 6 month delay in hardware procurement (36k€ equipment in 2025). Not yet on critical path. [Project ends in 2027]
Runaway electron mitigation and velocity analysis by magnetic-ripple manipulation [at TCV] | TCV: REMR | Umar Sheikh | 63 | Project ends in 2025
LIBS4FUSION: in-vessel fuel Inventory and deposited layers composition in a full tungsten device | WEST: LIBS | Arnaud Bultel | 69 | Project ends in 2026
ONCOMING-Optimized taNgentially spaCe resOlved geM ImagiNG [at MAST-U] | MAST-U: GEM | Andrea Muraro | 75 | Project ends in 2025
Upgrade of the TCV ECRH high voltage power supply | TCV: ECRH | Damien Fasel | 75 | Project ends in 2027
High DEfinition Visible Endoscope for WEST | WEST: HIDEVE | Philippe Moreau | 75 | Project ends in 2027

## Slide 4: TE Enhancements Questionnaire - Analysis
1) Are the design activities for your project going on and/or do you foresee they will proceed as scheduled?
2) Are installation activities for your project progressing and/or do you foresee they will progress as scheduled taking in consideration the most updated machine timeline? Please indicate what the machine timeline is.
3) Is the system plasma commissioning completed or do you foresee it will be completed as scheduled taking in consideration the most updated machine timeline? Please indicate what the machine timeline is.
4) Will you achieve all the deliverables/milestones by the dates defined by you in the Project Management Plan?
5) Will you be able to hand in the deliverable reports as planned?Is the system plasma commissioning completed or do you foresee it will be completed as scheduled taking in consideration the most updated machine timeline?
6) Are the human resources in your project being used and do you foresee to keep on using them as allocated? If not, could you please indicate the percentage of used resources against your original plan?
7) Is the procurement of equipment for your project going on and/or do you foreseen it’ll happen as planned? Could you please state if you have received a quote for the equipment to be procured within the project, if you have ordered it or if it has already been delivered? Will you achieve all the deliverables/milestones by the dates defined by you in the Project Management Plan?
8) Are the planned missions for your project happening and/or do you foresee they will keep on happening as planned?
Answers
  Traffic light based replies [to help obtaining feedback uniformity]
    Green – Everything progressing as planned no delays.
    Yellow – There are delays but it’s not foreseen they will impact the agreed deadline for the completion of the project.
    Red – There are delays and it’s foreseen they will impact the agreed deadline for the completion of the project.
  Text replies - If the status for any question is red, yellow or if the question so requires it please provide a written answer as well.
    Important to be as accurate and realistic as possible to maintain an updated clear picture of the allocated resources that might not be needed for any given year.