## Slide 1: Delayed Grant Deliverables
ID | Title in CWP | Due Date | Expected deliverable date | Status | Comments/Reason for delay
TE.D.12 | The physics basis for the decision for an alternative divertor configuration for DEMO. | 31/12/2024 | 31/12/2025 | delayed | Delayed to Dec 2025 to include additional input from AUG
TE.D.13 | Recommendation on the seeding impurity mix in view of a future reactor. | 31/12/2024 | 31/12/2025 | delayed | Delayed to Dec. 2025 to extend interpretative modelling of impurity seeding and execute further cross device experiments
TE.D.09 | Establishment and comparison of N and Ne-seeded partially-detached divertor in high-power operations in view of ITER radiative scenario. | 31/12/2023 | 31/12/2025 | delayed | Delayed to December 2025 to finalize the associated high-fidelity modelling
SA.D.05 | Delivery and final tests of EU-REC Completed | 30/06/2024 | 31/12/2025 | delayed | Activity performed in conjunction with QST and F4E and in pace with the schedule of the machine preparation for next operational phase (2026?).
SA.D.06 | Installation of the EU systems before the OP2 campaign | 31/12/2024 | 31/12/2025 | delayed | The installation plan is strongly dependent on the schedule of the shutdown for the Machine Enhancement 1 (now ongoing), in turn depending on high priority repair/reinforcements activities only partially defined up to now. At present, no installation of EU systems is completed in 2024.
W7X.D.09 | Assessment report on scenarios with optimized transport and high-beta operation (energy limit 6 GJ) | 31/12/2024 | 31/12/2025 | delayed | Request has been made to change the deliverable title as follows: "Assessment report on scenarios with optimized transport and high-beta operation (energy limit 2 GJ)". Justification: The W7-X facility is capable of delivering pulses with an energy throughput of 6 GJ. However, between OP2.3 and OP2.4 (2025-2026), several diagnostic systems at W7-X will be replaced by steady-state compatible alternatives. For OP2.2, scheduled to run until the end of 2024, an energy throughput of 2 GJ is planned. With plasma durations of several minutes and an input power of around 5 MW, physics questions related to long-pulse operation can also be addressed within the 2 GJ energy throughput. As long as the Grant Agreement is not amended accordingly the GD is put in delay.
PWIE.D.14 | Properties of JET bulk tungsten and beryllium after extensive test under reactor conditions. | 31/12/2024 | 31/12/2025 | delayed | Delayed to 2025 to consider post DT samples as well.
PWIE.D.15 | Initial exploration of HML (PEX Upgrade) capabilities regarding JUDITH-3 and JULE-PSI usage. | 31/12/2024 | 31/12/2025 | delayed | To be cancelled and reinstated for the extension of the Grant Agreement. The installation of Jule-PSI and JUDITH-3 facilities into the HML (hot cell) is long delayed and will not be available for measurements within the current Grant Agreement period. Expected delivery date is 31/12/2027.
PWIE.D.16 | Exploitation of experiments (WEST, JET, ASDEX Upgrade) related to material migration, fuel retention, and fuel recovery including interpretative plasma-edge and PWI modelling. | 31/12/2024 | 31/07/2025 | delayed | Delayed availability of contributing documentation needed for the compilation of the Grant Deliverable
PWIE.D.18 | Simulation of JET and PEX Upgrades results in view of ITER divertor and DEMO alternative configurations and its implementation in DTT. Quantitative comparison of potential benefits alternative configurations with respect to conventional solutions in view of exhaust performances and core compatibility (input to overarching PEX.M1 milestone). | 31/12/2024 | 31/08/2025 | delayed | Delayed availability of contributing documentation needed for the compilation of the Grant Deliverable

## Slide 2: Delayed Grant Milestones
ID | Title in CWP | Due Date | Expected deliverable date | Status | Comments/Reason for delay
PWIE.M.11 | FZJ PEX facility with JULE-PSI and JUDITH-3 is fully operational and ready for scientific exploitation. | 31/12/2024 | 31/12/2025 | delayed | To be cancelled and reinstated for the extension of the Grant Agreement. The installation of Jule-PSI and JUDITH-3 facilities into the HML (hot cell) is long delayed and will not be available for measurements within the current Grant Agreement period. Expected delivery date is 31/12/2027.

## Slide 3: Important upcoming deadlines
Running calls:
12/09/2025 - Call for the Nomination of a deputy TFL for WPTE
12/09/2025 - Call for the Nomination of a deputy PL for WPPWIE
22/09/2025 - Call for Participation in AWP26-27 (WP: SA, STEL, PWIE)
PLs to present initial evaluation of the CfP: 30/09/2025 (PSD Man meeting, starting at 10:00!)
06/10/2025 – evaluation of the CfP in AWP2026-27 (WP: SA, STEL, PWIE)
28/07/2025 - Call for Participation in EEG
19/09/2025 – Call for Project Proposals for TSVV Activities
19/09/2025 – Call for Proposals for Development of a Digital Twin Environment for Fusion Reactor Modelling
12/09/2025 – Call for E-TASC SB members
26/09/2025 – Call for Proposals for EnR (various areas)
26/09/2025 – Call for Participation in EF Coordinated Data Management activities
Physics Project Board: 27-28/10/2025 (noon to noon)

## Slide 4: List of 2026-27 Grant Deliverables
WP | YEAR | TITLE
TE | 2026 | Report on fully integrated simulation of high current partial detachment plasma scenario including assessment of PFC erosion in D and DT plasma
TE | 2026 | Report on reduced model validation for plasma reattachment on multiple devices and wide operational space
TE | 2026 | Report on providing input on design and operation of conditioning systems for next step full W devices, with a focus on standard boronization systems
TE | 2027 | Report on qualification with experiment/modelling the most promising no-ELM scenario in term of confinement, exhaust capabilities, Plasma Wall Interaction
TE | 2027 | Report on optimized scheme for “benign termination” of runaway beams document in view of possible applicability for ITER
SA | 2027 | Report on first measurement of the pedestal density and temperature at sub-cm spatial resolution in JT-60SA
PWIE | 2026 | Report on scaling the integrated first wall W sources in toroidal devices as function of edge plasma conditions, impurity composition, wall clearance deduced from high fidelity PWIE simulations for AUG, JET, ITER and DEMO (H-mode)
PWIE | 2027 | Report on the erosion /deposition pattern and fuel (tritium) retention in Be and W PFCs in JET deduced from post-mortem analysis and laser-based techniques information and PWIE simulations
PWIE | 2027 | Report on summarising the efficiency of wall conditioning and fuel removal techniques obtained in TOMAS and toroidal devices with metallic PFCs (w/wo boron) in view of application in tokamaks and stellarators, and recommendations to ITER new baseline
PWIE | 2027 | Report on quantification of fuel retention in self-damaged (or neutron-damaged) W exposed in JULE-PSI (or PSI-2) using in-situ laser-based methods and comparison with post-mortem analysis techniques
STEL | 2027 | Report on high confinement scenarios via plasma profile control and high power scenarios at low magnetic field to reach reactor relevant collisionalities (ν* < 0.1) and high beta (⟨β⟩ ≥ 2.5%)
STEL | 2027 | Report on experimentally validated modelling predictions for fast ion physics and turbulent transport
STEL | 2027 | Report on long pulse scenarios with nτTi > 0.1e20 and plasma duration of up to 1000 s
TM | 2027 | Report on code dissemination, model validation, and comparison with experimental data (for both tokamaks and stellarators)
TM | 2027 | Report on TSVV Research Software Compliance with EUROfusion Standards (Priority 1 and 2 Criteria)

## Slide 5: List of 2026-27 Grant Milestones
WP | YEAR | TITLE
TE | 2026 | Proper figure of merit for cross-scenario comparison among no-ELM/ADC defined
TE | 2026 | First wall particle and heat fluxes quantified via experiment or modelling in XPR in metallic devices
TE | 2026 | ADCs characterized in H-mode conditions in relevant TE devices
TE | 2027 | Modelling of SPI experiment on JET and ASDEX-Upgrade completed
TE | 2027 | Impact of N-NBI on plasma behaviour documented in JT-60SA and extrapolation to ITER
SA | 2026 | Commissioning of the Edge Thomson Scattering diagnostics in JT-60SA completed
PWIE | 2026 | Provide a matrix describing the fuel retention in boron layers as function of flux composition, impact energy, and surface temperature on tungsten and steel substrate available
PWIE | 2027 | Execution of high fluence plasma exposure of PFCs solutions for DEMO, JT-60SA ,W7-X in MAGNUM-PSI and PSI-2 mimicing divertor and first wall conditions covering seeding species composition and thermal cycling completed

## Slide 6: Status of 2024 level 3 deliverables
WP | Area | Total no | Approved | In review | Not available
TE | Campaigns | 11 | 11 | - | -
 | JT-60SA | 7 | 7 | - | -
 | Machine operation | 4 | 4 | - | -
 | Enhancements (PEX, Diagnostics) | 37 | 13 | 3 | 21
 | (AI) | 3 | 0 | 3 | -
SA | All | 42 | 0 | 37 (in combined reports) 4 (in single reports) | 1 to be cancelled
W7X | all | 54 | 54 | - | -
PWIE | all | 183 | 162 | 10 | 11 (4AI/ML, 1PEX, ?)

## Slide 7: Status of news items
WP | News item expected | PL/TFL reminded | Draft received | Sent to COM | Published by COM | Title of news item
PWIE | 25/01/2025 |  |  |  |  | LIBS
TE | 10/03/2025 | 26/02 | 20/03/2025 |  | 28/03/2025 | ITER physics publication DIVSOL and TC ITPAs
SA | 25/03/2025 | 26/02; 10/03 |  |  |  | 
TE | 10/04/2025 |  | 20/03/2025 | 02/04/2025 | 16/04/2025 | QCE
W7X | 25/04/2025 |  | 16/05/2025 | 21/05/2025 |  | First successful post-diction of plasma profiles in an optimised stellarator
TE | 10/05/2025 |  |  |  |  | 
PWIE | 25/05/2025 |  |  |  |  | 
TE | 10/06/2025 |  |  |  |  | 
PWIE | 25/06/2025 |  |  |  |  | 
TE | 10/07/2025 |  | 09/07/2025 | 10/07/2025 | 17/07/2025 | ADC
SA | 25/07/2025 |  |  |  |  | Possibly diagnostic installation (TS)
TE | 10/08/2025 |  |  |  |  | 
W7X | 25/09/2025 |  |  |  |  | 
TE | 10/09/2025 |  |  |  |  | 
PWIE | 25/09/2025 |  |  |  |  |