## Slide 1: SP B - W and B samples and their analyses
Antti Hakola
On behalf of the SP B team and task holders
Status meeting, 10 July, 2025

## Slide 2: Goals of this meeting
As discussed in the kick-off meeting in February, a follow-up discussion on the foreseen activities for W and B samples is necessary
We need to clarify the following key points:
Where are we with the sample production programme?
  Have all the agreed W and B samples been produced?
  If yes, have the samples been sent to the labs for analyses or follow-up experiments?
  If no, where do we have the bottlenecks?
Do we know what to do next for the different reference coatings?
  Is the analysis chain clear? Do we all know what to expose to linear plasmas and how?
  Is it clear to whom the exposed samples should be sent next?
Do we need to introduce changes to the agreed production and analysis programmes?
  Is the set of samples agreed reasonable – in particular concerning W where the plans were made already a year ago?
  Are there needs for additional samples? If yes, which ones and how urgently/desperately they would be required?

## Slide 3: W sample matrix (as agreed in 2024): exposures in linear devices
Research Unit | Coating | Coating thickness (um) | Substrate | Sample size (mm) | # of samples | To whom? | For which purpose? | Follow-up actions | Follow-up RU | Produced by
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | DIFFER | MAGNUM exposures | SEM + profilometry | IPPLM | 12/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | DIFFER | MAGNUM exposures | IBA | IST | 12/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | DIFFER | MAGNUM exposures | TOF-ERDA | RBI | 12/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | DIFFER | MAGNUM exposures | SIMS | VTT | 12/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | ENEA | GyM exposures | SEM + profilometry | IPPLM | 12/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | ENEA | GyM exposures | IBA | IST | 12/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | ENEA | GyM exposures | TOF-ERDA | RBI | 12/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | ENEA | GyM exposures | SIMS | VTT | 12/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | FZJ | PSI-2 exposures | SIMS | CIEMAT | 12/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | FZJ | PSI-2 exposures | SEM | FZJ | 12/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | FZJ | PSI-2 exposures | IBA | VR | 12/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | FZJ | PSI-2 exposures | IBA + XRD | NCSRD | 12/2024
ENEA | Nanocolumnar W | 2,0 | W | PSI-2 geometry | 1 | DIFFER | MAGNUM exposures | SIMS | CIEMAT | 07/2024
ENEA | Nanocolumnar W | 2,0 | W | PSI-2 geometry | 1 | DIFFER | MAGNUM exposures | SEM | FZJ | 07/2024
ENEA | Nanocolumnar W | 2,0 | W | PSI-2 geometry | 1 | DIFFER | MAGNUM exposures | XPS + IBA | JSI | 07/2024
ENEA | Nanocolumnar W | 2,0 | W | PSI-2 geometry | 1 | DIFFER | MAGNUM exposures | IBA | VR | 07/2024
ENEA | Nanocolumnar W | 2,0 | W | PSI-2 geometry | 1 | ENEA | GyM exposures | SIMS | CIEMAT | 07/2024
ENEA | Nanocolumnar W | 2,0 | W | PSI-2 geometry | 1 | ENEA | GyM exposures | SEM | FZJ | 07/2024
ENEA | Nanocolumnar W | 2,0 | W | PSI-2 geometry | 1 | ENEA | GyM exposures | XPS + IBA | JSI | 07/2024
ENEA | Nanocolumnar W | 2,0 | W | PSI-2 geometry | 1 | ENEA | GyM exposures | IBA | VR | 07/2024
ENEA | Nanocolumnar W | 2,0 | W | PSI-2 geometry | 1 | FZJ | PSI-2 exposures | SIMS | CIEMAT | 07/2024
ENEA | Nanocolumnar W | 2,0 | W | PSI-2 geometry | 1 | FZJ | PSI-2 exposures | SEM | FZJ | 07/2024
ENEA | Nanocolumnar W | 2,0 | W | PSI-2 geometry | 1 | FZJ | PSI-2 exposures | XPS + IBA | JSI | 07/2024
ENEA | Nanocolumnar W | 2,0 | W | PSI-2 geometry | 1 | FZJ | PSI-2 exposures | IBA | VR | 07/2024
Comments: MAGNUM samples are all different from each other  how to adapt the exposure programme?
Only one nanocolumnar sample exposed in GyM but work largely pending for consensus on exposure parameters

## Slide 4: W sample matrix (as agreed in 2024): LIBS and dust experiments
Research Unit | Coating | Coating thickness (um) | Substrate | Sample size (mm) | # of samples | To whom? | For which purpose? | Follow-up actions | Follow-up RU | Produced by
ENEA | Nanocolumnar W | 2,0 | Mo | Diam. <30 mm, thick 1 mm | 1 | DIFFER | in situ LIBS | SEM | IPPLM | 07/2024
ENEA | Nanocolumnar W | 2,0 | Mo | See above | 1 | DIFFER | in situ LIBS | IBA | IST | 07/2024
ENEA | Nanocolumnar W | 2,0 | Mo | See above | 1 | DIFFER | in situ LIBS | IBA + XRD | NCSRD | 07/2024
ENEA | Nanocolumnar W | 2,0 | Mo | See above | 1 | DIFFER | in situ LIBS | TOF-ERDA | RBI | 07/2024
ENEA | Nanocolumnar W | 2,0 | Mo | See above | 1 | DIFFER | in situ LIBS | SIMS | VTT | 07/2024
ENEA | Porous W-O | 2,0 | Mo | See above | 1 | DIFFER | in situ LIBS | SEM | IPPLM | 10/2024
ENEA | Porous W-O | 2,0 | Mo | See above | 1 | DIFFER | in situ LIBS | IBA | IST | 10/2024
ENEA | Porous W-O | 2,0 | Mo | See above | 1 | DIFFER | in situ LIBS | IBA + XRD | NCSRD | 10/2024
ENEA | Porous W-O | 2,0 | Mo | See above | 1 | DIFFER | in situ LIBS | TOF-ERDA | RBI | 10/2024
ENEA | Porous W-O | 2,0 | Mo | See above | 1 | DIFFER | in situ LIBS | SIMS | VTT | 10/2024
ENEA | Compact W | 0,5 | Mo | See above | 1 | DIFFER | in situ LIBS | IBA | IST | 10/2024
ENEA | Compact W | 0,5 | Mo | See above | 1 | DIFFER | in situ LIBS | SIMS | VTT | 10/2024
ENEA | Compact W | 1,0 | Mo | See above | 1 | DIFFER | in situ LIBS | IBA | IST | 10/2024
ENEA | Compact W | 1,0 | Mo | See above | 1 | DIFFER | in situ LIBS | SIMS | VTT | 10/2024
ENEA | Compact W | 1,5 | Mo | See above | 1 | DIFFER | in situ LIBS | IBA | IST | 10/2024
ENEA | Compact W | 1,5 | Mo | See above | 1 | DIFFER | in situ LIBS | SIMS | VTT | 10/2024
ENEA | Compact W | 2,0 | Mo | See above | 1 | DIFFER | in situ LIBS | IBA | IST | 10/2024
ENEA | Compact W | 2,0 | Mo | See above | 1 | DIFFER | in situ LIBS | SIMS | VTT | 10/2024
ENEA | Amorphous W-O | 4,0 | Flat W | PSI-2 geometry | 1 | ENEA | Dust studies | SEM + profilometry | IPPLM | 06/2024
ENEA | Amorphous W-O | 4,0 | Flat W | PSI-2 geometry | 1 | ENEA | Dust studies | SEM + profilometry | IPPLM | 06/2024
ENEA | Amorphous W-O | 4,0 | Flat W | PSI-2 geometry | 1 | ENEA | Dust studies | SEM + profilometry | IPPLM | 06/2024
Comments: Dust samples analyzed and work completed
Status of in-situ LIBS samples?

## Slide 5: W sample matrix (as agreed in 2024): sample analyses
Research Unit | Coating | Coating thickness (um) | Substrate | Sample size (mm) | # of samples | To whom? | For which purpose? | Comments | Produced by
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1-5 | DIFFER | SEM + IBA | Sequence IPPLM --> NCSRD --> CIEMAT or DIFFER --> RBI --> VTT | 09/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1-5 | IPPLM | SEM + profilometry | Sequence IPPLM --> NCSRD --> CIEMAT or DIFFER --> RBI --> VTT | 09/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1-5 | NCSRD | IBA + XRD | Sequence IPPLM --> NCSRD --> CIEMAT or DIFFER --> RBI --> VTT | 09/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1-5 | RBI | TOF-ERDA | Sequence IPPLM --> NCSRD --> CIEMAT or DIFFER --> RBI --> VTT | 09/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1-5 | VTT | SIMS | Sequence IPPLM --> NCSRD --> CIEMAT or DIFFER --> RBI --> VTT | 09/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1-5 | CIEMAT | SIMS | Sequence IPPLM --> NCSRD --> CIEMAT or DIFFER --> RBI --> VTT | 09/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | IPPLM | SEM |  | 12/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | IST | IBA |  | 12/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | RBI | TOF-ERDA |  | 12/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | VTT | SIMS |  | 12/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | CIEMAT | SIMS |  | 12/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | FZJ | SEM |  | 12/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | NCSRD | IBA + XRD |  | 12/2024
DIFFER | Re-deposited W | Nominal | W | PSI-2 geometry | 1 | VR | IBA |  | 12/2024
ENEA | Amorphous W | 3,0 | Si | 10 x 10 | 1 | MPG | FIB sputtering |  | 09/2024
IAP | W + Mo marker | 2,0 | W | 12 x 15 | 1 | CU | LIBS |  | 07/2024
IAP | W + Mo marker | 2,0 | W | 12 x 15 | 1 | CIEMAT | SIMS |  | 07/2024
IAP | W + Mo marker | 2,0 | W | 12 x 15 | 1 | ENEA | LIBS + profilometry |  | 07/2024
IAP | W + Mo marker | 2,0 | W | 12 x 15 | 1 | JSI | XPS + IBA |  | 07/2024
IAP | W + Mo marker | 2,0 | W | 12 x 15 | 1 | NCSRD | IBA + XRD |  | 07/2024
IAP | W + Mo marker | 2,0 | W | 12 x 15 | 1 | UT | LIBS |  | 07/2024
IAP | W | 5,0 | Mo | 12 x 15 | 1 | CU | LIBS |  | 11/2024
IAP | W | 5,0 | Mo | 12 x 15 | 1 | ENEA | LIBS + profilometry |  | 11/2024
IAP | W | 5,0 | Mo | 12 x 15 | 1 | IST | IBA |  | 11/2024
IAP | W | 5,0 | Mo | 12 x 15 | 1 | RBI | TOF-ERDA |  | 11/2024
IAP | W | 5,0 | Mo | 12 x 15 | 1 | UT | LIBS |  | 11/2024
IAP | W | 5,0 | Mo | 12 x 15 | 1 | VTT | SIMS |  | 11/2024
IAP | W | 2,0 | Mo | 12 x 15 | 1 | CEA | Raman |  | 09/2024
IAP | W | 2,0 | Mo | 12 x 15 | 1 | IPPLM | SEM |  | 09/2024
IAP | W | 2,0 | Mo | 12 x 15 | 1 | IST | IBA + XRD |  | 09/2024
IAP | W | 2,0 | Mo | 12 x 15 | 1 | NCSRD | IBA + XRD |  | 09/2024
IAP | W | 2,0 | Mo | 12 x 15 | 1 | VR | IBA |  | 09/2024
w/o gas
w/ D(10 at.%)
D(10 at.%)
D(5 at.%)+H(5 at.%)
H(10 at.%)
N(10 at.%)
N(5 at.%)+O(5 at.%)
O(10 at.%)
Comments: Re-deposited W samples are all different from each other (see previous slides); IAP samples delivered and largely analysed

## Slide 6: B sample matrix (as agreed in 2025): exposures in linear devices
Research Unit | Producing lab | Coating | Coating thickness (nm) | Substrate | Sample size (mm) | # of samples | To whom? | For which purpose? | Follow-up actions | Follow-up RU | Comments | Produced by
DIFFER | Tom | B | 100,0 | W | PSI-2 geom | 1 | DIFFER | MAGNUM-PSI experiments | SEM | FZJ + IPPLM | Sequence: FZJ --> IPPLM | 05/2025
DIFFER | Tom | B | 100,0 | W | PSI-2 geom | 1 | DIFFER | MAGNUM-PSI experiments | IBA | VR + IST | Sequence: VR --> IST | 05/2025
DIFFER | Tom | B | 100,0 | W | PSI-2 geom | 1 | DIFFER | MAGNUM-PSI experiments | SIMS | CIEMAT + VTT | Sequence: CIEMAT --> VTT | 05/2025
FZJ | Anne | B | 100,0 | W | PSI-2 geom | 1 | FZJ | PSI-2 experiments | SEM | DIFFER + IPPLM | Sequence: DIFFER --> IPPLM | 05/2025
FZJ | Anne | B | 100,0 | W | PSI-2 geom | 1 | FZJ | PSI-2 experiments | IBA | VR + IST | Sequence: VR --> IST | 05/2025
FZJ | Anne | B | 100,0 | W | PSI-2 geom | 1 | FZJ | PSI-2 experiments | SIMS | CIEMAT + VTT | Sequence: CIEMAT --> VTT | 05/2025
FZJ | Anne | B+W | 100,0 | W | PSI-2 geom | 1 | FZJ | PSI-2 experiments | TBD | TBD | To be discussed separately | 07/2025
ENEA | POLIMI | B | 100,0 | W | PSI-2 geom | 1 | ENEA | GyM experiments | SEM | FZJ + IPPLM | Sequence: FZJ --> IPPLM | 06/2025
ENEA | POLIMI | B | 100,0 | W | PSI-2 geom | 1 | ENEA | GyM experiments | IBA | VR + IST | Sequence: VR --> IST | 06/2025
ENEA | POLIMI | B | 100,0 | W | PSI-2 geom | 1 | ENEA | GyM experiments | SIMS | CIEMAT + VTT | Sequence: CIEMAT --> VTT | 06/2025
Comments: B samples from DIFFER expected in the autumn; all these samples different  change analyses to sequential
FZJ produced B samples for MAGNUM experiments  outside of the matrix but physically interesting  status?
ENEA samples will be produced now that relocation of the lab is completed
Exposure conditions for the B samples need to be agreed
Handling after the exposure  sealed in vacuum bags and delivery to analyses?

## Slide 7: B sample matrix (as agreed in 2025): round-robin exercise
Research Unit | Producing lab | Coating | Coating thickness (nm) | Gas inclusion | Production temperature (deg C) | Substrate | Sample size (mm) | # of samples | To whom? | For which purpose? | Produced by
DIFFER | Tom | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | CEA | Raman | 02/2025
DIFFER | Tom | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | FZJ | SEM + LIBS | 02/2025
DIFFER | Tom | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | NCSRD | IBA + SEM + XRD | 02/2025
DIFFER | Tom | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | RBI | TOF-ERDA | 02/2025
DIFFER | Tom | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | VR | IBA | 02/2025
FZJ | Anne | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | CEA | Raman | 02/2025
FZJ | Anne | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | DIFFER | IBA + SEM | 02/2025
FZJ | Anne | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | NCSRD | IBA + SEM + XRD | 02/2025
FZJ | Anne | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | RBI | TOF-ERDA | 02/2025
FZJ | Anne | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | VR | IBA | 02/2025
FZJ | Anne | B | 100,0 | D | Nominal | Steel | PSI-2 geom | 1 | FZJ | Permeation | 07/2025
FZJ | Anne | B+W | 100,0 |  | Nominal | Steel | PSI-2 geom | 1 | FZJ | Permeation | 07/2025
ENEA | POLIMI | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | CEA | Raman | 04/2025
ENEA | POLIMI | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | CIEMAT | SIMS | 04/2025
ENEA | POLIMI | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | DIFFER | SEM + IBA | 04/2025
ENEA | POLIMI | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | FZJ | SEM + LIBS | 04/2025
ENEA | POLIMI | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | IPPLM | SEM | 04/2025
ENEA | POLIMI | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | IST | IBA | 04/2025
ENEA | POLIMI | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | JSI | XPS + TDS | 04/2025
ENEA | POLIMI | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | NCSRD | IBA + SEM + XRD | 04/2025
ENEA | POLIMI | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | RBI | TOF-ERDA | 04/2025
ENEA | POLIMI | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | VR | IBA | 04/2025
ENEA | POLIMI | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | VTT | SIMS | 04/2025
VTT | Uni Helsinki | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | CEA | Raman | 09/2025
VTT | Uni Helsinki | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | DIFFER | IBA + SEM | 09/2025
VTT | Uni Helsinki | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | FZJ | SEM + LIBS | 09/2025
VTT | Uni Helsinki | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | NCSRD | IBA + SEM + XRD | 09/2025
VTT | Uni Helsinki | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | RBI | TOF-ERDA | 09/2025
VTT | Uni Helsinki | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | VR | IBA | 09/2025
VTT | Uni Helsinki | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | VTT | SIMS | 09/2025
Comments: B samples from DIFFER expected in the autumn; all these samples different  change analyses to sequential
ENEA samples will be produced now that relocation of the lab is completed
Status of FZJ samples?
VTT samples to be produced only late in 2025

## Slide 8: B sample matrix (as agreed in 2025): round-robin exercise
Research Unit | Producing lab | Coating | Coating thickness (nm) | Gas inclusion | Production temperature (deg C) | Substrate | Sample size (mm) | # of samples | To whom? | For which purpose? | Produced by
IAP | Bobi | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | CEA | Raman | 02/2025
IAP | Bobi | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | CIEMAT | SIMS | 02/2025
IAP | Bobi | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | DIFFER | SEM + IBA | 02/2025
IAP | Bobi | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | FZJ | SEM + LIBS | 02/2025
IAP | Bobi | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | IPPLM | SEM | 02/2025
IAP | Bobi | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | IST | IBA | 02/2025
IAP | Bobi | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | JSI | XPS + TDS | 02/2025
IAP | Bobi | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | NCSRD | IBA + SEM + XRD | 02/2025
IAP | Bobi | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | RBI | TOF-ERDA | 02/2025
IAP | Bobi | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | VR | IBA | 02/2025
IAP | Bobi | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | VTT | SIMS | 02/2025
IAP | Bobi | B | 500,0 |  | Nominal | EUROFER | diam 40 | 5 | JSI | Permeation | 02/2025
IAP | Bobi | B | 500,0 |  | Nominal | W | 10 x 10 | 5 | JSI | IBA + TDS | 02/2025
IAP | Bobi | B | 500,0 |  | Nominal | W | 10 x 10 | 1 | CIEMAT | SIMS | 02/2025
IAP | Bobi | B | 500,0 |  | Nominal | W | 10 x 10 | 1 | IST | IBA | 02/2025
IAP | Bobi | B | 1000,0 |  | Nominal | EUROFER | diam 40 | 5 | JSI | Permeation | 02/2025
IAP | Bobi | B | 1000,0 |  | Nominal | W | 10 x 10 | 5 | JSI | IBA + TDS | 02/2025
IAP | Bobi | B | 1000,0 |  | Nominal | W | 10 x 10 | 1 | CIEMAT | SIMS | 02/2025
IAP | Bobi | B | 1000,0 |  | Nominal | W | 10 x 10 | 1 | IST | IBA | 02/2025
IAP | Bobi | B | 5000,0 |  | Nominal | EUROFER | diam 40 | 5 | JSI | Permeation | 02/2025
IAP | Bobi | B | 5000,0 |  | Nominal | W | 10 x 10 | 5 | JSI | IBA + TDS | 02/2025
IAP | Bobi | B | 5000,0 |  | Nominal | W | 10 x 10 | 1 | CIEMAT | SIMS | 02/2025
IAP | Bobi | B | 5000,0 |  | Nominal | W | 10 x 10 | 1 | IST | IBA | 02/2025
VR | Eduardo | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | CEA | Raman | 02/2025
VR | Eduardo | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | DIFFER | IBA + SEM | 02/2025
VR | Eduardo | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | FZJ | SEM + LIBS | 02/2025
VR | Eduardo | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | NCSRD | IBA + SEM + XRD | 02/2025
VR | Eduardo | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | RBI | TOF-ERDA | 02/2025
VR | Eduardo | B | 100,0 |  | Nominal | W | PSI-2 geom | 1 | VTT | SIMS | 02/2025
w/o gas
w/ D(10 at.%)
Comments: IAP and VR samples produced and delivered

## Slide 9: B sample matrix (as agreed in 2025): impact of annealing
Research Unit | Producing lab | Coating | Coating thickness (nm) | Gas inclusion | Production temperature (deg C) | Substrate | Sample size (mm) | # of samples | To whom? | For which purpose? | Produced by
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal | W | 5 x 5 | 1 | CEA | Raman | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal | W | 5 x 5 | 1 | JSI | TDS | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal | W | 5 x 5 | 1 | NCSRD | IBA | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal | W | 5 x 5 | 1 | RBI | TOF-ERDA | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal | W | 5 x 5 | 1 | VTT | SIMS | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 50 C | W | 5 x 5 | 1 | CEA | Raman | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 50 C | W | 5 x 5 | 1 | JSI | TDS | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 50 C | W | 5 x 5 | 1 | NCSRD | IBA | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 50 C | W | 5 x 5 | 1 | RBI | TOF-ERDA | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 50 C | W | 5 x 5 | 1 | VTT | SIMS | 04/2025
 |  |  |  |  | Etc. |  |  |  |  |  | 
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 400 C | W | 5 x 5 | 1 | CEA | Raman | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 400 C | W | 5 x 5 | 1 | JSI | TDS | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 400 C | W | 5 x 5 | 1 | NCSRD | IBA | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 400 C | W | 5 x 5 | 1 | RBI | TOF-ERDA | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 400 C | W | 5 x 5 | 1 | VTT | SIMS | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 450 C | W | 5 x 5 | 1 | CEA | Raman | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 450 C | W | 5 x 5 | 1 | JSI | TDS | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 450 C | W | 5 x 5 | 1 | NCSRD | IBA | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 450 C | W | 5 x 5 | 1 | RBI | TOF-ERDA | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 450 C | W | 5 x 5 | 1 | VTT | SIMS | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 500 C | W | 5 x 5 | 1 | CEA | Raman | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 500 C | W | 5 x 5 | 1 | JSI | TDS | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 500 C | W | 5 x 5 | 1 | NCSRD | IBA | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 500 C | W | 5 x 5 | 1 | RBI | TOF-ERDA | 04/2025
IAP | Bobi | B | 5000,0 | D (10 at.%) | Nominal + annealing 500 C | W | 5 x 5 | 1 | VTT | SIMS | 04/2025
Comments: Request for pure B samples with the same heating schemes to support already performed analyses