## Slide 1: Status of Grant Deliverables 1/2
ID Sygma | Title in CWP | Due Date | Exp. del. date | Status | Comments/Reason for delay
TE.D.09 | Establishment and comparison of N and Ne-seeded partially-detached divertor in high-power operations in view of ITER radiative scenario. | 31/12/2023 | 31/12/2025 | delayed | In review (Emmanuelle missing)
TE.D.12 | The physics basis for the decision for an alternative divertor configuration for DEMO. | 31/12/2024 | 31/12/2025 | delayed | In review (Emmanuelle missing)
TE.D.13 | Recommendation on the seeding impurity mix in view of a future reactor. | 31/12/2024 | 31/12/2025 | Completed | 
SA.D.05 | Delivery and final tests of EU-REC Completed | 30/06/2024 | 31/12/2025 | delayed | Activity performed in conjunction with QST and F4E and in pace with the schedule of the machine preparation for next operational phase (2026?).
SA.D.06 | Installation of the EU systems before the OP2 campaign | 31/12/2024 | 31/12/2025 | delayed | The installation plan is strongly dependent on the schedule of the shutdown for the Machine Enhancement 1 (now ongoing), in turn depending on high priority repair/reinforcements activities only partially defined up to now. At present, no installation of EU systems is completed in 2024.
SA.D.10 | Delivery of EU procurements (TBD) for the campaign 2026 Completed. | 31/12/2025 |  | delayed | 
W7X.D.09 | Assessment report on scenarios with optimized transport and high-beta operation (energy limit 2 GJ) | 31/12/2024 | 31/12/2025 | delayed | In review
W7X.D.10 | Verified and validated stellarator gyrokinetic codes for the calculation of turbulent transport (TSVV-13) | 31/12/2025 |  | Completed | 
W7X.D.11 | Report on conducted scenario & campaign preparation (focus: high-power steady-state operation) | 31/12/2025 |  | Completed | 
W7X.D.13 | Report on conducted scenario & campaign preparation (focus: PFC upgrades) | 31/12/2025 |  | Completed | 
W7X.D.14 | Comparative assessment of the HELIAS reactor physics basis with respect to other stellarator concepts (with International Collaborations). | 31/12/2025 |  | delayed | In review
W7X.D.15 | Modern European stellarator optimization code and its use to determine options for next-generation devices. | 31/12/2025 |  | Completed | 

## Slide 2: Status of Grant Deliverables 2/2
ID Sygma | Title in CWP | Due Date | Exp. del. date | Status | Comments/Reason for delay
PWIE.D.14 | Properties of JET bulk tungsten and beryllium after extensive test under reactor conditions. | 31/12/2024 | 31/12/2025 | delayed | Awaiting approval
PWIE.D.16 | Exploitation of experiments (WEST, JET, ASDEX Upgrade) related to material migration, fuel retention, and fuel recovery including interpretative plasma-edge and PWI modelling. | 31/12/2024 | 31/12/2025 | delayed | In review
PWIE.D.18 | Simulation of JET and PEX Upgrades results in view of ITER divertor and DEMO alternative configurations and its implementation in DTT. Quantitative comparison of potential benefits alternative configurations with respect to conventional solutions in view of exhaust performances and core compatibility (input to overarching PEX.M1 milestone). | 31/12/2024 | 31/12/2025 | delayed | In review
PWIE.D.19 | Characterization and predictive modelling of plasma-wall interactions in He und He/H mixed plasmas for ITER in Pre-Fusion Power phase. | 31/12/2025 |  | delayed | In review
PWIE.D.20 | High fluence exposition of mono blocks made of references W and advanced W materials for DEMO, JT-60SA, DTT in MAGNUM-PSI and UPP including pre- and post-characterisation. | 31/12/2025 |  | delayed | In review
PWIE.D.22 | Comparison of in-situ (LID-QMS in JET) and ex-situ examination (FREDIS, TDS) of the laser-irradiated components regarding fuel/tritium content. | 31/12/2025 |  | delayed | In review
PWIE.D.23 | PSI modelling of DEMO main chamber erosion, deposition and fuel retention. PIC modelling of the sheath in the DEMO divertor (with TSVV). | 31/12/2025 |  | delayed | Awaiting approval
PWIE.D.24 | Neutral gas kinetics modular code upgraded and final verification/validation report (with TSVV). | 31/12/2025 |  | delayed | In review
PWIE.D.25 | Initial PSI modelling of W sources, screening, transport and core concentration in full W-devices (with TSVV-06). | 31/12/2025 |  | delayed | Awaiting approval

## Slide 3: Status of Grant Milestones
ID Sygma | Title in CWP | Due Date | Exp. Del. date | Status | Comments/Reason for delay
PWIE.M.14 | Potential PFCs solutions for an all-W W7-X identified and reference samples exposed in HHF and plasma devices to stellarator relevant power loads and fluence. | 31/12/2025 |  | Completed | 
W7X.M.05 | High-beta HELIAS operation at low collisionalities | 31/12/2025 |  | Completed | 
W7X.M.06 | Operation with High power and long-pulse Completed and 2 GJ energy turn-around achieved (pulse lengths up to 600 s, long-pulse detachment). | 31/12/2025 |  | Completed | 

## Slide 4: News items planning for 2026
WP | News item expected
TE | 10/02/2026
TM | 25/02/2026
TE | 10/03/2026
STEL | 25/03/2026
TE | 10/04/2026
PWIE | 25/04/2026
TE | 10/05/2026
TM | 18/05/2026
STEL | 25/05/2026
TE | 10/06/2026
SA | 25/06/2026
TE | 10/07/2026
PWIE | 18/07/2026
STEL | 25/07/2026
TE | 10/08/2026
TM | 18/08/2026
TE | 10/09/2026
STEL | 25/09/2026
TE | 10/10/2026
PWIE | 25/10/2026
TE | 10/11/2026
TM | 18/11/2026
STEL | 25/11/2026
TE | 10/12/2026
SA | 18/12/2026
FREQUENCY
WP TE: 1 x per month
WP PWIE: 1 x every 3 months
WP TM: 1 x every 3 months (new!)
WP SA: 1 x every 6 months
WP-STEL: 1 x every 2 months