## Slide 1: Actions identified from recent meetings
Title/Description | Resp. | Est. | Deadline | Status | Comments
ITER physics gaps document: WPLs to confirm and agree on the contribution and lead roles | WPLs | 06.03.2026 | 27.04.2026 | IN PROGRESS | 6th July potential meeting between Richard and Alberto (all tech docs of MoU); presenting PL/TFLs in person
JFO to raise an action at BACM for the JT-60SA MPP (Multi annual Program Plan) to update, finalize and approve a new version (by 30th June) | JFO, PWIE, TE, SA, DIV, F4E, FSD | 06.03.2026 | 30.04.2026 | NOT STARTED | 
Circulate JT-60SA operation working group recommendations after being presented at the next GA | MWR | 06.03.2026 | 30.04.2026 | NOT STARTED | 
Initiate the process to convert unused hardware funds (from a JET post-mortem third container that will not be purchased) into PMs | SBK, BMS | 06.03.2026 | TBD | IN PROGRESS | Botond to contact Sebastijan on the steps and rough timing
Follow up on transport issues regarding JET post-mortem tiles | SBK | 06.03.2026 | 30.06.2026 | IN PROGRESS | update?
P1 impact analysis: discuss the scientific impact and indicate risks and delays (i.e. ITER) resulting from low EUROfusion machine time fraction | STEL, PWIE, TE, TM, FSD (Lead) | 06.03.2026 | 30.05.2026 | NOT STARTED | 
MJI to initiate a discussion with WPDIV PL to check if Work Package can absorb assessment and development of 3D technology for plasma-facing components (towards FoaK/ FP10) | MJI | 06.03.2026 | 31.12.2026 | NOT STARTED | 

## Slide 2: Actions identified from recent meetings
Title/Description | Resp. | Est. | Deadline | Status | Comments
List the 2027 deliverables per TSVV that will be dropped or reduced in scope to comply with current budget | XLN | 06.03.2026 | 07.06.2026 | NOT STARTED | TM’s internal deadline is the 27th May, followed by a discussion on the 3rd June
Schedule meetings between Task Force leaders and PIs to define clear boundaries between code development, first validation (TM) and code application and validation (TE/PWIE/STEL) | TE/ TM/ STEL/ PWIE | 06.03.2026 | 07.05.2026 | IN PROGRESS | continuous action till the end of FP9; meeting scheduled for the deadline
Collect ideas on the elements of strength and weakness within the current EUROfusion ecosystem to inform the design of FP10 | MWR | 06.03.2026 | 14.09.2026 | NOT STARTED | 
Integrate AI-assisted coding into the standard workflows of Advanced Computing Hubs (ACHs) and move from open-source to open-data standards [DSO] | XLN | 06.03.2026 | 31.05.2026 | NOT STARTED | request input for information!
Analysis of the potential benefits of different devices to define a broader EUROfusion engagement strategy and identify the physics and modeling gaps that need to be filled in FP10 | FSD (lead), all WPs | 06.03.2026 | 30.06.2026 | NOT STARTED | due date for GA July, after BEST and JT-60SA discussed, better information available; follow up on 15th June
JT-60SA: C wall scientific priorities updated & W wall scientific priorities set-up | MWR | 16.04.2026 | 30.04.2026 | NOT STARTED | input expected from TFLs. The W one will be done once a draft for C is ready
Provide high-level scientific priorities where BEST provides strategic value and complements the European device portfolio, particularly JT-60SA | WPLs | 15/04/2026 | 30/04/2026 | NOT STARTED | 
Propose a coherent EF approach towards BEST | MWR | 15/04/2026 | 15/06/2026 | NOT STARTED | Marco to include it in the intro slides for the meeting 2027 activity priorities

## Slide 3: Unachieved deliverables (L3) statistics 2021-2024
2022 | Not received | In review
PrIO | 1 | 0
2023 | Not received | In review
n/a |  | 
2024 | Not received | In review
PrIO | 8 | 1
PWIE | 1 | 1
TE | 4 | 6 (2)
ACP involved, delivery promised till end of May
Only Enhancement area!
4 fully reviewed
Left out by mistake
(PEX) fully reviewed

## Slide 4: 2025 situation snapshot as of 27/04/2026
2025 | Not received | In review | Approved | Total
TE of which Project Man Exp campaign Operational cost Upgrades AI | 25 of which 1 1 0 22 1 | 15 of which 0 9 0 5 1 | 27 of which 1 9 4 12 1 | 67 of which 2 19 4 39 3
SA | 2 | 17 | 41 | 60
W7X | 4 | 4 | 57 | 65
PWIE | 1 (PEX) | 0 | 178 | 179
PrIO | 33 | 21 | 46 | 100