## Slide 1
Tangential phase-contrast imaging diagnostic for JT-60SA
S. Coda1 , K. Tanaka2 , M. Noël1
1EPFL-SPC, 2NIFS WPSA Enhancements Monitoring meeting, 20.4.2026

## Slide 2: Phase-contrast imaging on JT-60SA
CO2-laser based transmission diagnostic
Will provide localized density fluctuation measurements across the minor radius and in all plasma regimes
  dn/n~10-5, 0.06<kri<12 (ITG/TEM/ETG)
  high spatial resolution in the center and at the edge (very favorable configuration on JT-60SA)
Europe/NIFS collaboration and cost split
S. Coda et al, Nucl. Fusion 61, 106022 (2021), DOI:10.1088/1741-4326/ac2081

## Slide 3: Optical-path design
P01H
P08H
PCI
CO2
YAG
P01H
P08H
PCI
CO2
YAG
PCI
CO2
YAG
3

## Slide 4: Current status and planning
Procurement Agreement signed last year.
Procurements are ongoing on the NIFS side (LN2 filling station, radiation shielding) and on the European side (combined supports for TS and TPCI beam tubes).
The optics and optical supports from the laser room to a point before the beam expander (before entering the torus) are to be installed in ME1. The rest in ME2.
Mechanical and optical design for ME1, including a complete Installation Procedure, to be finished by May 2026. All procurements and manufacturing to follow quickly.
QST is organizing installation with subcontractor.
The ME2 component design is also at a mature stage.

## Slide 5: Optical path layout

## Slide 6: Beam trajectory: mirror supports

## Slide 7: Beam trajectory: mirror supports

## Slide 8: Delivery of supports for TPCI + TS tubes

## Slide 9: Calendar for 2026 and 2027
ME1 component design and installation procedure to be finished in May 2026.
Procurements and fabrication can follow if the F4E-EPFL contract is signed (the process has been underway for some time).
Installation of ME1 components planned for September-November 2026.
The ME2 component design and detailed optical design, with finalized installation procedure, is expected for September 2026.
The full installation of the system is planned for ME2.

## Slide 10: Outstanding needs
The physics personnel is highly insufficient. A postdoc has been advocated and requested for a number of years, but there is no mechanism in place yet to hire one. The F4E-EPFL contract should include a service provision for a postdoc.
The timeline indicated earlier cannot be met without this postdoc.

## Slide 11
additional slides

## Slide 12: Beam expander under optical table

## Slide 13: Beam expander under optical table

## Slide 14: Entry window assembly

## Slide 15: Entry window assembly