## Slide 1: Status of Grant Deliverables: OVERDUE
ID Sygma | Title in CWP | Due Date | Exp. del. date | Status | Comments/Reason for delay
SA.D.05 | Delivery and final tests of EU-REC Completed | 30/06/2024 | 30/09/2026 | delayed | Activity performed in conjunction with QST and F4E and in pace with the schedule of the machine preparation for next operational phase (2026?). (BMS: are the expected delivery date and the comment still reasonable? Note that the GA will be after the 30th September, and unless the GD is uploaded to IDM and approved we can not change the status.)
SA.D.06 | Installation of the EU systems before the OP2 campaign | 31/12/2024 | 31/07/2026 | delayed | The installation plan is strongly dependent on the schedule of the shutdown for the Machine Enhancement 1 (now ongoing), in turn depending on high priority repair/reinforcements activities only partially defined up to now. At present, no installation of EU systems is completed in 2024. (BMS: Please provide a realistic expected delivery date and an associated comment replacing the old one.)
SA.D.10 | Delivery of EU procurements (TBD) for the campaign 2026 Completed. | 31/12/2025 | 31/07/2026 | delayed | Delayed availability of contributing documentation needed for the compilation of the Grant Deliverable (BMS: comments need to be addressed in IDM and new version uploaded to be approved in time for the GA reporting)
PRIO.D.10 | Report on the EUROfusion plan/programme for the involvement and contribution to ITER operation | 30/06/2024 | 31/10/2026 | delayed | report under finalization
STEL.D.01 | Report on fully integrated simulation of high current partially detached plasma scenario | 30/06/2026 | 31/12/2026 | delayed | Amendment not started (BMS: report can be created and uploaded to IDM for review and approval any time; upload to the EC system as soon as possible)

## Slide 2: Status of Grant Deliverables and Milestones: UPCOMING
ID Sygma | Title in CWP | Due Date | Status
TE.D.17 | Report on fully integrated simulation of high current partially detached plasma scenario including assessment of PFC erosion in D and DT plasma | 31/12/2026 | On track
TE.D.18 | Report on reduced model validation for plasma reattachment on multiple devices and wide operational space | 31/12/2026 | On track
TE.D.19 | Report on providing input on design and operation of conditioning systems for next step full W devices and focus on standard boronisation systems | 31/12/2026 | On track
PWIE.D.26 | Report on scaling the integrated first wall W sources in toroidal devices as function of edge plasma conditions, impurity composition, wall clearance deduced from high fidelity PWIE simulations for AUG, JET, ITER and DEMO (H-mode) | 31/12/2026 | On track
ID Sygma | Title in CWP | Due Date | Status
TE.M.08 | Proper figure of merit for cross-scenario comparison among no-ELM / ADC defined | 31/12/2026 | On track
TE.M.09 | First wall particle and heat fluxes quantified via experiment or modelling in XPR in metallic devices | 31/12/2026 | On track
TE.M.10 | ADCs characterised in H-mode conditions in relevant TE devices | 31/12/2026 | On track
SA.D.08 | Commissioning of the Edge Thomson Scattering diagnostics in JT-60SA completed | 31/12/2026 | On track
PWIE.M.16 | Matrix describing the fuel retention in boron layers as function of flux composition, impact energy, and surface temperature on tungsten and steel substrate available | 31/12/2026 | On track