## Slide 1: 2027 Activity priorities WPSA: Relative internal WP priorities of various diagnostics activities
FSD Meeting June 15th, 2026
Carlo Sozzi

## Slide 2: Presently ongoing development
System under procurement or development | Reference person | Proposed Op. | Present status
FILD | Juan Ayllon (CIEMAT, U. Sevilla) | OP3 | Ex-vessel design consolidated and the shielding concept validated by neutronics studies. Ready for procurement
TPCI | Stefano Coda (EPFL) | OP3 | Components to be installed in ME-1 delivered. Mechanical design complete
Doppler Reflectometry | Elena de la Luna (CIEMAT) | OP4 tbc | Consolidated concept for the DR system that meets spectral resolution requirements. Pending decision on the final instrumentation location
EC Stray detection system | Saul Garavaglia (ENEA-CNR) + MPG (W7-X team) | ? | Al2O3+TiO2 as the primary absorbing material for the bolometer system robust bolometer design validated through MISTRAL laboratory tests and W7-X operations sniffer probe design moving into the laboratory testing and calibration
Gamma-ray spectrometer | Massimo Nocente (ENEA, UNIMIB) | OP3 | Design phase for the JT-60SA LaBr3(Ce) Gamma-ray Spectrometer complete. Ready for procurement.
EU Neutron diagnostics (Vertical Neutron Camera) | Marco Cecconello (VR)+IPPLM team | ? | conceptual layout and material composition for the VNC collimator and detector units
EU Neutron spectrometer | Davide Rigamonti (ENEA-CNR) | OP4 tbc | confirmed the feasibility of a LaCl3-based compact spectrometer for 2.5 MeV neutron spectroscopy at JT-60SA
RE monitor | Daniele Marocco (ENEA) | OP3tbc | Detailed feasibility completed, hw partially available, ready for procurement
Neut. Spectrum Reconst. for Activation foils (F4E) | Katarzyna Mikszuta-Michalik (IPPLM) | OP2(?) | high-intensity part of the JT-60SA neutron spectrum can be reliably reconstructed from activation measurements with an uncertainty below 25%.

## Slide 3: Proposals for Edge & SOL diagnostics (WPSA call in 2025)
Deliverable Title | Author (Beneficiary) | Contribute to | W traces exp OP4 | Status
Report on the feasibility study for an EU-DEMO like real-time detachment control diagnostics for JT-60SA | Dunai, Daniel (EK-CER) | Detachment | y | on hold
Report on the feasibility of the installation in JT-60SA of a runaway electron monitor | Marocco, Daniele (ENEA) | Safety (Runaway) | Y (not relevant) | Being considered for ME2/OP3
Report on the Enhancement of the fast charge exchange spectroscopy | Liang, Yunfeng (FZJ) | 3 | - | Lower priority
Report on the feasibility of a MANTIS multispectral visible imaging diagnostics (*) | Perek, Artur (EPFL) | DetachmentW cycle | W imaging ok, traces partial test | on hold
Report on the feasibility study of a high-resolution visible overview camera with real-time and multispectral capabilities (*) | Szepesi, Tamas (EK-CER) | W cycle Safety | y | Update on going (delayed 2025 task)
Quartz Crystal Microbalances (*) | Laguardia, Laura (02-CNR) | W cycle | y | on hold
Report on the feasibility of a Thermal Helium Beam diagnostics for electron temperature and density measurement | Ugoletti, Margherita (01-RFX) | (edge instabilities) | y | on hold
Report on the feasibility of a Neutral Gas Analysis system | Laguardia, Laura (02-CNR) | W cycle Retention | y | on hold
Report on the feasibility of a SOL-Pedestal Imaging Vacuum-Ultraviolet spectrometer(*) | Belpane, Andrea (01-RFX) | W cycle | y | on hold
Report on the feasibility of a Directional Electron Probe diagnostics | Liang, Yunfeng (FZJ) | (edge instabilities) | y | Finalizing Feasibility
Report on the feasibility of a Collective Thomson Scattering diagnostics | Korsholm, Søren Bang (DTU) | 2 | - | Lower priority Finalizing Feasibility
Update of the feasibility report on Hydrogen/Deuterium Beam Emission Spectroscopy | Dunai, Daniel (EK-CER) | 3 | - | Lower priority
Under consideration of the IPT&ET leadership. Expression of priority expected at the end of 2026 - (*) good chances

## Slide 4: Objectives in 2027
Support of systems in operation: Thomson Scattering System, Divertor VUV, EDICAM
  Exploitation and support to operation in OP2
  Raman and other calibration activities between OP2 and OP3 campaign
  Support to operation in OP3 (on site + remote)
Installation and commissioning of OP3 diagnostics: FILD, TPCI, LaBr3(Ce) Gamma Spectrometer, Runaway Electron Monitor (if confirmed)
Development of the Pellet Launching System
  Scientific support to sources development (F4E tender) and integration with the launcher
  Integration and laboratory test
Preparation of OP4 diagnostics
  Systems in advanced status of approval
    Procurement and characterization of the LaCl3(Ce) Compact Neutron Spectrometer
    Finalize the design of Doppler Reflectometry
    Finalize the design of the Vertical Neutron Camera
Support the development of the selected “Edge and SOL diagnostics” (NOT funded at present)

## Slide 5: Boundary conditions
Planning for the period 2026-2027 is based on the assumption that a significant part of the engineering design, engineering analysis and procurement assistance can be supported through F4E- Beneficiary Institution contracts.
F4E contracts | scope | starting period
TPCI | engineering and procurement (installation SNE?) | late 2026
TS | Installation and operation - (SNE) mission costs only, EuF salary costs | 1st August 2026
VUV | installation and operation - (SNE) mission costs only, EuF salary costs | 1st August 2026
DR | Engineering and procurement | late 2026 ?
GRS | Engineering and procurement – (installation SNE?) | Late 2026 ?
FILD | procurement contract at present not covering installation (SNE?) | ongoing
REM | Engineering and procurement | Late 2026 ?
NES | engineering and procurement | 2027?
For such cases, the WPSA support will go only to the scientific PL of the enhancement project, or for the preliminary design needed to reach the maturity to sign a PA (F4E-QST)
9 good new diagnostics proposals for the preparation, still to be discussed/accepted by the Experiment Team (detailed reports available)-Essentially no budget in 2026-27 for their further development (~+48 PMs)
SNE contracts impact: less mission costs (but NO reduction to zero for each system) but large constraints due to EuF salary costs to be guaranteed
Present SNE positions (3 experts for diagnostics) can cover installation & commissioning OR regular operation but NOT both (strategic decision to be taken)

## Slide 6: Present 2026-2027 plan (resources) – in 2027 scientific keep-in touch only)
Role Title | PMs X activity | 2026 | Involved beneficiaries | 2027 | Involved beneficiaries
1.1 Enhancements Area Coordinator | 4 | 2 | CIEMAT (US) | 2 | CIEMAT (US)
1.2 Fast Ion Losses Detector RO | 4 | 2 | CIEMAT | 2 | CIEMAT
1.3 Fast Ion Losses Detector expert | 4 | 4 | CIEMAT | 0 | CIEMAT
1.4 Tangential Phase Contrast Imaging RO | 2 | 1 | EPFL | 1 | EPFL
1.5 TPCI expert | 4 | 4 | EPFL | 0 | EPFL
1.6 Gamma Ray Spectrometer RO | 4 | 2 | ENEA (UNIMIB) | 2 | ENEA (UNIMIB)
1.7 GRS expert | 4 | 2 | ENEA (CNR), UKAEA | 2 | ENEA (CNR), UKAEA
1.8 Compact Neutron Spectrometer RO | 4 | 2 | ENEA (CNR) | 2 | ENEA (CNR)
1.9 CNS expert | 5 | 2 | ENEA (CNR) | 3 | ENEA (CNR)
1.10 Pellet System RO | 4 | 2 | MPG | 2 | MPG
1.11 Pellet System expert | 9 | 6 | MPG | 3 | MPG
1.12 Diagnostic system expert | 15 | 10 | CIEMAT, ENEA, IPPLM(NCBJ), VR,FZJ,DTU | 5 | ENEA, IPPLM(NCBJ), VR
1.13 Diagnostic system RO | 4 | 3 | CIEMAT | 1 | CIEMAT
1.14 Neutronics expert | 12 | 10 | IPPLM | 2 | IPPLM
2.1 Plasma Operations Area Coordinator | 4 | 2 | ENEA | 2 | ENEA
2.2 Thomson Scattering TRO | 4 | 2 | ENEA (CRFX) | 2 | ENEA(CRFX)
2.3 Thomson Scattering Expert | 9 | 7 | IAP(ICIT), ENEA (CRFX) | 2 | ENEA (CRFX)
2.4 Divertor VUV spectroscopy TRO | 3 | 2 | ENEA (CRFX) | 1 | ENEA (CRFX)
2.5 VUV spectroscopy expert | 6 | 5 | IAP(ICIT), ENEA (CRFX) | 1 | ENEA (CRFX)
2.6 MGI expert | 4 | 2 | MPG | 2 | MPG
2.7 EDICAM expert | 6 | 3 | EK-CER | 3 | EK-CER
2.8 Subsystem operation expert | 4 | 1.5 | CEA | 2.5 | CEA, ENEA
3.1 Code Management Area Coordinator | 4 | 2 | CEA | 2 | CEA
3.2 Pulse Design Simulator expert | 6 | 4 | CEA, ENEA(CREATE) | 2 | CEA, ENEA(CREATE)
3.3 Electron Cyclotron Waves simulation expert | 5 | 2 | ENEA(CNR), NCSRD | 3 | ENEA(CNR), NCSRD, CR
3.4 Magnetic control expert | 5 | 3 | ENEA(CREATE), EPFL | 2 | ENEA(CREATE), EPFL
3.5 Cryo-magnet system simulation and data analysis expert | 4 | 2 | ENEA, CEA | 2 | ENEA, CEA
3.6 Control room monitoring tools/ Synthetic diagnostics expert | 6 | 3 | ENEA, ENEA(CNR), EPFL | 3 | ENEA, ENEA(CNR), EPFL
tot PMs(I) |  | 92.5 |  | 56.5 | 

## Slide 7: WPSA - 2027 budget requests and priorities (under revision, May 2026)
Topic | Required resources (PM, hardware, facilities, …) | Associated CC budget* [k€] | Associated EC budget* [k€] | Mission JA (CC) | Associated CC budget* [k€] incl.mission | Associated EC budget* [k€] incl.mission | WP priority (Low, Medium, High) | PSD priority TBD
Installation & commissioning of Tangential Phase Contrast Imaging (TPCI) | 6 | 25.62 | 28.2 | 53.55 | 79.17 | 70.28 | H | 
Installation & commissioning of Fast Ion Losses Detector (FILD) | 5 | 21.35 | 23.5 | 44.63 | 66 | 58.6 | H | 
Installation & commissioning of Gamma Rays Spectrometer (GRS) | 5 | 21.35 | 23.5 | 44.63 | 66 | 58.6 | H | 
Installation & commissioning of Runaway Electron Monitor (REM) | 3 | 12.8 | 14.1 | 26.8 | 39.6 | 35.2 | H | 
Installation & commissioning of Pellet Launching System (PLS) | 4 | 17.1 | 18.8 | 35.7 | 52.8 | 46.9 | H | 
Analysis tools for operation (Installation and test) | 4 | 17.1 | 18.8 | 35.7 | 52.8 | 46.9 | M | 
Support for subsystem operation (EdgeTS, DivVUV, MGI, EDICAM) | 18 | 77 | 84.6 | 161 | 237.5 | 210.83 | H | 
Design of selected Edge and SOL diagnostics for W transition | 48 | 205 | 226 | - | 205 | 226 | H | 
Total | 93 | 397 | 473 | 401.63 | 799 | 753 |  | 
*Conversion: 4.27k€ CC/ PM (@average); 4.70k€ EC/PM; HW/facility CC= 0.5*direct cost; HW/facility EC=0.7*direct cost ** to be reviewed after SNE assignations

## Slide 8: Remarks from TCM-45
CQMS procedure for diagnostics proposal/priority/selection being defined by the IPT management
OP4 diagnostics priorities being decided in 2026 (see later)
Key scientific points for the W phase:
  Evaluation of the screening effect (ions + neutrals) temperature/energy on SOL
  Net versus gross erosion
Heating systems combination and port allocation plays a role in the process of decision

## Slide 10: WPSA mission budget 2026
Scope (mission plan) | (mission or home lab) days | SNE salary 2026 | additional HR | mission costs | total cost €
PDS support (0.5 PM EPFL) | 15 |  | 3,542 € |  | 3542
EdgeTS RO | 180 | 20892 |  |  | 20892
DivVUV RO | 180 | 20892 |  |  | 20892
Operation AC | 90 | 10453 |  |  | 10453
CCG (CCG PhD) | 60 |  |  | 18375 | 18375
ECE tools (PhD) | 30 |  |  | 9187.5 | 9187.5
ECE tools (Expert) | 15 |  |  | 4593.75 | 4593.75
TCM november Naka (PL, ENH AC, CM AC, FILD, TPCI, REM, GRS, CNS, VNC, MGI, EDICAM,...) | 80 |  |  | 24500 | 24500
EDICAM update | 30 |  |  | 9187.5 | 9187.5
EDICAM support 2026 | 30 |  |  | 9187.5 | 9187.5
Training EU (PDS 12 people x 6 days) | 72 |  |  | 17010 | 17010
A&M meeting & training (5 people x 10 days) | 50 |  |  | 11812.5 | 11812.5
MGI support | 60 |  |  | 18375 | 18375
RWM coils support | 30 |  |  | 9187.5 | 9187.5
Management EU missions | 20 |  |  | 4725 | 4725
Management JA missions | 20 |  |  | 6125 | 6125
VUV support (Mech & Alignment, Control, Calibration) | 60 |  |  | 18375 | 18375
TS support (Calibration) | 30 |  |  | 9187.5 | 9187.5
Neutronics course | 12 |  |  | 2835 | 2835
Tot CC € |  |  |  |  | 228442.75
Available mission budget 2026 CC | 222,453 € |  |  | Residual | -5,990 €
HR fully assigned (no NA resources left)
Important activities underfinanced in 2026
Not all the onsite activities can be covered by SNE positions
Mission budget 2026 fully taken. If something can be saved, priority to underfinanced activities.