## Slide 1: Work-Package Theory and Modelling (WPTM): Work-Plan 2026-27
Xavier LITAUDON (Project Leader), Gloria FALCHETTO (Project Support Officer) on behalf of the TSVV PIs
CEA lead lab. for WPTM
xavier.litaudon@cea.fr
Thanks to TSVV PIs for their constructive inputs

## Slide 2: 11 multi-beneficiary TSVV Projects
 | TSVV titles | Principal Investigator | Lead Beneficiary | Other Beneficiaries involved
A | H-Mode and Small/No-ELM Pedestals | Tobias Görler | MPG | CEA, DIFFER, ENEA, EPFL
B | Plasma Particle/Heat Exhaust – Fluid Simulations | Patrick Tamain | CEA | DTU, EPFL, IPP.CR, LPP-ERM-KMS, MPG
C | Plasma Particle/Heat Exhaust – Gyrokinetic Simulations | Daniel Told | MPG | CEA, DIFFER, EPFL, IPP.CR, JSI
D | Plasma-Wall Interactions with Metallic Plasma-Facing Components | Dmitry Matveev | FZJ | CEA, DIFFER, IPP.CR, MPG, VR, VTT
E | Impurity Sources, Transport, and Screening | Guido CIRAOLO | CEA | EPFL, FZJ, IPP.CR, IPPLM, VTT
F | Tokamak Disruptions and Runaway Electrons | Matthias Hoelzl | MPG | CEA, ENEA, EPFL, VR
G | Physics of Burning Plasmas | Oleksiy Mishchenko | MPG | CEA, ENEA, EPFL, KIPT, NCSRD, UKAEA
H | Reliable Prediction of Plasma Performance and Operational Limits in Tokamaks | Michele Marin | EPFL | CEA, DIFFER, ENEA, EPFL, IPP.CR, IST, LPP-ERM-KMS, MPG, UKAEA, VR
I | Stellarator Optimization | Joaquim Loizu | EPFL | CIEMAT, EPFL, MPG, OEAW
J | Stellarator core turbulence | José Manuel García-Regaña | CIEMAT | DIFFER, EPFL, MPG, UKAEA
K | Neutral Particle Models | Dmitriy V. Borodin | FZJ | CEA, DIFFER, ENEA, FZJ, LPP-ERM-KMS, VTT

## Slide 3: Resource considerations
TSVVs call issued with 5-6 PPY/Y for TSVV A-J, 3 PPY/Y for TSVV K for 2026-2027 (30% lower than in 2021-2025)
  Following replies to the call : 45% overbudget despite all proposals within 6 PPY/Y
  Within one week TSVV PIs went down to the minimum limit : 5 (3) PPY/Y (without UKAEA)
  PIs revised the deliverables & PPY following recommendations from E-TASC Scientific Board
Issue 1 for PL/PSO: 1 PPY/Y not included in the 2026-2027 budget estimate (activity previously managed by PMU when call issued)
Issue 2 for TSVVs: Calculation with the actual salary/per beneficiary for 2026-27 leads to budget above TM budget ceiling in k€
TM decision to provide PPY as selected in 2026 and to reduce PPY in 2027 by 28 % (uniformly across all TSSVs/beneficiaries) to stay within the budget ceiling (5864 k€ in CC)
  Mismatch between deliverables and allocated PPY: 3.6 PPY TSVV A-J and 2.1 PPY TSVV K in 2027
Mission budget: 97 k€/year (direct cost) not sufficient to hold at least one in-person meeting per TSVV/Y + E-TASC general meeting and does not include PL/PSO missions (Project Board, E-TASC, HPC Board, FSD ...)
  Request: 130 k€ for 105 participants with one week mission per year

## Slide 4: Significant work-force reduction for Theory and Simulation activity
EUROfusion activity that will not be covered by the PPP call
Some beneficiaries might leave TSVVs since “effort” will not be sufficiently rewarding
Averaged PPY/Y in 2021-2025 for the TSVVs* | PPY in 2026 | PPY in 2027
77,1 PPY/Y | 53,4 PPY/Y | 38,2 PPY/Y
-30%
-28%
-50%
[*EUROFUSION GA (25) 51 - 5.2a - 2021-2025 - Budget Revision v16]
Equivalent of stopping one TSVV per year: -5.5PPY per year

## Slide 5: Grant Deliverables and Impact on TSVV Deliverables
Report on code dissemination, model validation, and comparison with experimental data (for both tokamaks and stellarators)
Report on TSVV Research Software Compliance with EUROfusion Standards
=> Impact on code dissemination and compliance to standard software
Formal coordination established with experimental WPs for model validation and requirement capture for data comparison
Formal coordination established with ACHs in support to TSVV Research Software compliance with EUROfusion standards
Grant milestones
Grant Deliverables
Consequences on the TSVV deliverables:
Analysis performed per TSVVs by PIs with programmatic consequences (work in progress)

## Slide 6: Common TSVV observations on consequences of PM reduction [1/2]
Impact on the 2026 WP, as some 2026 activities have been deprioritised in favour of higher-priority 2027 activities
The nominal 28% reduction in PMs has disproportionately larger consequences due to “non-linear effects”
  Reduction of scientific coherence within TSVV projects
  Deliverables achieved but with reduced physics scope
  Reduction of cross-teams and cross-TSVV activities as efforts re-focused on key deliverables, e.g.
    limited development of reduced models and validation activities
    Impact on integration activities (TSVV-H)
Impact on the broader programme (FSD WPs and ENR)
  Delays in model development will affect validation activities within TM and FSD WPs
  Potential impact on key deliverables e.g. TE.D.19 : Report on qualification with experiment/modelling of the most promising no-ELM scenario in terms of confinement, exhaust capabilities and plasma wall interaction
  Limited support for the ENR-PIE (Pedestal Inference Engine) collaboration
  Lower capacity for code training, dissemination and adoption of EUROfusion software standards (TM deliverables)
Reduced capability for ITER-oriented simulations
Reduced support for future stellarator design and optimisation activities
Reduced synergy Stellarator & ITER on the 3D physics

## Slide 7
Reduced ability to involve (code training) a broader user community beyond the TSVV contributors
Increased resource fragmentation, contrary to both the call requirements and E-TASC objectives
  “Eligibility from the call: to minimize fragmentation, individual participants must commit a significant level of effort (strongly recommended: 6 PMs/year; minimum: 2 PMs/year)”
Risk of losing participants due to insufficient involvement of some beneficiaries
  Balance between scientific benefit and management overhead becomes questionable
  Specific TSVV-H risk of loosing UKAEA involvement (HFPS) no ”Win-Win” benefit
Discontinuity of the theory/Simulation/Validation in contrast to the original E-TASC objective to provide long term development in a “secure” framework
Risk of prioritization of local team activity vs the joint EUROfusion effort
Even stronger impacts are expected beyond 2027
  While teams are currently committed, reduced visibility on future resources (PhD students, postdoctoral researchers, and temporary contracts) will increasingly affect staffing and planning
Common TSVV observations on consequences of PM reduction [2/2]

## Slide 8: Overview of the scientific topics impacted per TSVV
 | TSVV | 1. SOL heat flux decay length, pedestal and L-H transition | 2. Advanced regimes without ELMs | 3. Core-pedestal-SOL-wall workflow including 3-D effects | 4. Disruption, RE and impact on the W wall | 5. High beta plasmas and fast particle effect | 6. Stellarator core turbulence and Optimization | 7. Reduced models | 8. Validation and UQ
A | H-Mode and Small/No-ELM Pedestals | X | X |  |  |  |  | X | X
B | Plasma Particle/Heat Exhaust – Fluid Simulations | X | X |  |  |  |  | X | X
C | Plasma Particle/Heat Exhaust – Gyrokinetic Simulations | X | X |  |  |  | X | X | X
D | Plasma-Wall Interactions with Metallic Plasma-Facing Components |  |  | X | X |  |  | X | X
E | Impurity Sources, Transport, and Screening |  |  | X |  |  |  | X | X
F | Tokamak Disruptions and Runaway Electrons |  |  |  | X |  |  | X | X
G | Physics of Burning Plasmas |  |  |  |  | X |  | X | 
H | Reliable Prediction of Plasma Performance and Operational Limits in Tokamaks | X |  | X |  | X |  | X | X
I | Stellarator Optimization |  |  | X |  |  | X |  | X
J | Stellarator core turbulence |  |  | X |  |  | X | X | X
K | Neutral particle models | X | X |  |  |  |  | X | X

## Slide 9: Topics of the ITER-EUROfusion collaboration impacted
“Emphasis on model validation and extrapolability to ITER to support revision of ITER Research Plan” (sic from IO-EUROfusion agreement) “extrapolability” quoted 12 times ! And “Validation” quoted 32 times
Physics Basis for ITER scenarios:
  ELM control and no ELMS scenarios with W wall
  R&D related to W wall sources and transport : comparison with models for evaluation of W source and transport
  Pedestal transport, interplay with W: Pedestal modelling with W , Reinforce model verification/Validation for W transport through pedestal
Disruptions and disruption mitigation
  Strategy for benign termination of RE plasmas
  Runaway electron avalanche (RAE) behaviour and predictive model validation
  Disruption energy parameters (extrapolation assumptions and validation processes).
HFPS improvements:
  Development of models for burning plasmas
  Model validation at high beta (electromagnetic effects)
  Integrated modelling capturing W from the wall to the core
Validation of HFPS in Neon seeding high performance JET DD and DT plasmas
Integrated modelling capturing W from the wall to the core

## Slide 10: Overview of the impacted codes capabilities (not exhaustive/no specific order)
GENE-X
  improved Tₑ pedestal predictions through the implementation of sub-grid ETG models
  neutral model implementation (PIROCK adaptive time-stepping)
GENE
  multi-scale turbulence characterizations
  comparisons with / assessments of reduced models such as TGLF
GYSELA
  Implementation of kinetic source for plasma-neutral interaction in Gysela-X++
  Surrogate model implementation for sheath boundary condition
  No validation on “no ELM I-mode regime”
SOLEDEG3X and EMC3-EIRENE coupling to ERO2.0 for 3D workflow validation and application for ITER
EIRENE: reduced scope for Collisional Radiative Models
KINDNESS (kinetic neutral model): no coupling to other codes than GBS
JOREK-GK ITG/TEM turbulence studies with RMPs: limited cases
JOREK-DREAM: capability to carry out run-away generation calculations over long time scales in MHD quiet scenarios.
DREAM: incomplete parallelization does not allow the same level of comprehensive physics studies
CARIDDI and FIREWALL compliance with EUROfusion standard software requirements
ASTRA : no EUROfusion support and loss of experts (focus mainly on HFPS & to lesser extent on ETS)
HFPS: Integration of QLK_NN_11, CASTOR, MEQ and tests for broader exploitation of EDGE2DNN, SOLPSNN, PLIKES, ATEP, EQSTABIL
STELLA: IMASification of outputs for systematic database analysis
ERO2.0, MIGRAINe: Applicability of PWI surrogate, W transport from wall to core and time-dependent dust ablation sources
FESTIM, PFC-T-T: Damage-induced trap model parameterization and implementation for validation and predictive applications
Geant4-MEMENTO-LSDYNA framework: finalization of full thermo-mechanical model for W material response to RE impact

## Slide 11: TSVV-A H-Mode and Small/No-ELM Pedestals: 2027 Impacted Deliverables
Label | Description | Topics
D.9 | Scientific report characterizing turbulence, heat & particle transport in GYSELA simulations featuring both ITG & TEM instabilities but occupying various places in the (grad(n),grad(Ti), grad(Te)) parameter space – qualitative comparison to I-mode regimes Reduced scope: GYSELA comparisons with experimental I-mode regimes will be dropped or significantly reduced in scope. | 1
D.11 | Report on the neutral model impact in GENE-X flux-driven power ramps (12/2027); Reduced scope: The progress relies on neutral model developments in TSVV-C that is reduced in scope , e.g. if time schemes such as PIROCK are required to achieve relevant simulation time scales. | 1, 2
D.12 | Report on the impact of sub-ion scale ETG transport on flux driven power ramps on GENE-X (12/2027) Reduced scope: Fewer cases studied with additional sub-ion scale models in GENE-X and fewer comparisons/assessments of available ETG models. | 1
D.13 | Reports/Publications on JET/TCV no/small-ELM regimes and AUG QCE/EDA-H-mode studies performed with GENE/GENE-X with assessments of ETGs, quasi-linearity and TGLF comparisons on a test basis Reduced scope: GENE turbulence characterizations of small-ELMs regime at JET limited to ion-scale transport processes, with potential impact of ETGs related transport left unexplored. The number of considered AUG discharges needs to be cut back. | 1, 8
D.14 | Conference publication on JOREK-GK ITG/TEM turbulence simulations with RMPs in different tokamaks (COMPASS, HL2A, AUG) (12/2027) Reduced scope: The number of JOREK-GK ITG/TEM turbulence studies with RMPs will be reduced: HL2A will be dropped, AUG will be covered less extensively | 1, 3
D.16 | Report on verification of SAP/KEY with saturation rules against NL GK in pedestal and - depending on outcome - release of JAX-ified SAP, KEY codes for integrated modelling (12/2027) Reduced scope: may have to drop one of the two frameworks, which will impact ability to predict pedestal as well as ability of PIE ENR to work with TSVV-A output | 1, 7

## Slide 12: TSVV-B Plasma Particle/Heat Exhaust – Fluid Simulations 2026 Impacted Deliverables
Label | Description | Topics
D1.1 | Assessment of impact of baffles on turbulence and plasma conditions in high-density regime in TCV (CEA, EPFL) Reduced scope: CEA contribution cancelled as deemed as lower priority than some of the 2027 deliverables. | 2
D6.2 | Couple another edge turbulence code to EIRENE or KINDNES, likely starting with GRILLIX (CEA, DTU, EPFL, MPG) Reduced scope: Coupling of KINDNES to another turbulence code cancelled as deemed as lower priority than some of the 2027 deliverables. This would limit the mutualization of tools among European codes. | 2
D7.1 | Implement KINDNESS kinetic neutral solver in GPU-compatible version of GBS (EPFL) Dropped: Similarly to D6.2, future developments of the KINDNESS code, including its GPU-ization postponed beyond 2027, limiting the upscaling of GBS simulations to larger machines. | 2

## Slide 13: TSVV-B Plasma Particle/Heat Exhaust – Fluid Simulations 2027 Impacted Deliverables
Label | Description | Topics
D1.2 | Analysis of turbulence and transport in detached regime in the frame of the TCV-X23 experiments (CEA, EPFL, MPG, DTU, KUL) Reduced scope: Contribution of some of the TSVV-B codes to TCV-X23 reference case analysis (turbulence in high density regimes) will be dropped as priority given to validation exercises that have already been started. This is at least the case for the FELTOR and GRILLIX contributions, as well as for the reduced turbulence model in SOLEDGE-HDG. | 1, 2, 8
D1.3 | First evaluation light impurity turbulent transport in 3D edge turbulence simulation (CEA, EPFL) Reduced scope: Evaluation of the turbulent transport of impurities in the edge plasma, a fully novel topic on which reduced fidelity mean-field models rely on turbulence codes to get an answer, will be limited to very first proof-of-principle studies. This will impact the effort towards reducing the uncertainty in the parameter tuning of mean-field models that are heavily used to determine the operational space of future machines. | 2
D1.4 | Demonstrate capability to model D-T plasmas both for mean-field and turbulence applications (CEA, DTU) Dropped: Implementation of a fluid closure and neutrals model adapted to D-T simulations is a large endeavor and only first steps can be completed by the end of 2027 in case of resource reduction. | 2
D5.1 | Investigate the dependence of the SOL width on key parameters in edge turbulence simulations in L-mode (CEA, MPG) Reduced scope: Investigation of the dependence of the SOL width on key parameters in edge fluid turbulence codes will be drastically reduced in ambition (use of simplified geometry, limited range of scan). This is a very time- and resource-consuming activity as some of the scans (especially the one in toroidal field) are challenging, in realistic X-point geometries. Fundamental activity to validate the capability of our codes to reproduce experimental scaling laws before applying them to predictive studies. Topic that identified as critical for ITER’s operation. | 1
D6.8 | Updated RANS model description applicable to SOL in variety of L-mode regimes (KUL) Reduced scope: Extension of reduced turbulence models to advanced SOL regimes (high density, detached…) will be limited in scope. This will delay the implementation of these models in SOLPS-ITER and their availability to the rest of the modelling community. | 7
D6.9 | Sheath boundary conditions across reactor relevant range of collisionalities, for arbitrary plasma mix (IPP.CR) Reduced scope: The deployment in edge fluid codes of advanced sheath boundary conditions requires large resources as it will likely change significantly the numerical stability of the codes and the way they can be run. Exploring such changes is time-consuming and we will not be able to carry this task. The implementation in codes of newly derived boundary conditions will be postponed beyond 2027. | 2

## Slide 14: TSVV-C Plasma Particle/Heat Exhaust – Gyrokinetic Simulations 2027 Impacted Deliverables
Label | Description | Topics
D.6 | GENE-X with adaptive PIROCK. Report on benchmarking and against existing schemes in GENE-X, including stellarator cases and impurities/neutrals models At risk to be dropped: PIROCK a high-performance time integration for coupled plasma/neutrals simulations. | 1,2,6,8
D.7 | Reports or publications on simulations with enhanced physics (e.g. collisions, neutrals, impurities) in GENE-X Reduced scope : Validation and user support capacity will be reduced compared to original plans. | 1,2,6,8
D.8 | Report or publication on benchmark of kinetic impurity model in JOREK-GK; comparison with JOREK fluid model with kinetic impurities (and neutrals) At risk to be dropped : This deliverable was already planned without co-funding, but will be at risk because the personnel carrying it are co-funded through other affected projects (TSVV-A) | 1,2,8
D.9 | Report or publication detailing the surrogate model implemented in GYSELA for sheath boundary condition, including its first application in turbulent regime with kinetic electrons Reduced scope : Strong impact in the future because of reduced available funding for new PhD projects, impacting development and availability for validation. | 1,2,8
D.10 | report or publication on derivation + implementation of kinetic source for plasma-neutral interaction in Gysela-X++, accounting for ionization and charge exchange – first comparison to its fluid counterpart (in Gysela-X++ or VOICE) Reduced scope : Strong impact in the future because of reduced available funding for new PhD projects, impacting development and availability for validation. | 1, 2, 8
D.12 | Database of edge/SOL boundary condition outputs (radial electric field and related quantities) from GK simulations, prepared for use in integrated modelling, accessible to TSVV-H Reduced scope : minimum viable version will be implemented | 7, 8
D.13 | Report on reduced models and physics implications; design of cross-code post-processing tool Dropped: Cross-code tool will be deprioritized, limiting/delaying the ability to feed reduced models with data from various codes | 7, 8
D.14 | Report or publication on BIT1 simulation results of transient events and/or impurity/neutral studies Reduced scope : Reduced number of simulations / parameter studies | 2

## Slide 15: TSVV-D Plasma-Wall Interactions with Metallic PFC 2027 impacted Deliverables
Label | Description | Topics
D9, D10 | SP1. Wall lifetime, dust and impurity migration. Surrogate model for PWI in ERO2.0 for vector quantities: outgoing energy and angular distributions of reflected and sputtered particles, application to (static) rough surfaces. Reduced scope: material combinations restricted to the most ITER-relevant proof-of-concept cases, limited effort for model training, resulting in limited benefits of the new model against existing approaches. | 3, 7, 8
D11 | W core densities and residence times based on extended ERO2.0 impurity tracing with imposed impurity transport coefficients, validation and ITER predictions. Reduced scope: risk not to be able to finalize iterative improvement of impurity transport coefficients using higher fidelity core transport codes (towards HFPS) and related data exchange via IMAS, risk for framework validation and ITER predictions. | 3, 8
D12 | Self-consistent simulations of transport of W impurities generated by dust ablation (MIGRAINe-ERO2.0 time-dependent framework), validation and ITER predictions. Reduced scope: limited capability for workflow validation and predictive simulations with time-dependent ablation sources. | 3, 8
D13 | SP2. Fuel retention in neutron-damaged wall materials. Damage-induced trap model implementation in FESTIM. Reduced scope: restricted number of defects and interaction mechanisms that can be investigated, limited effort for model optimization – risk of restricting the model to insufficient number of defects/reactions for proper description of underlying processes. | 3,8
D14 | Global scale estimates of fuel retention, permeation and outgassing, validation and ITER predictions. Reduced scope: based on input from D13, limited model parameterization will affect the validation and quality of predictive simulations for ITER. | 1, 2, 8
D15, D16 | SP3. Consequences of transient events : modelling thermo-mechanical response of PFCs to RE impact with new Geant4-LSDYNA workflow, validation and ITER predictions. Reduced scope: concerns regarding successful finalization of full thermo-mechanical model development for W response to RE impact and respective model validation, which are very high priority for ITER. | 4, 8

## Slide 16: TSVV – E Impurity Sources, Transport, and Screening 2027 Impacted Milestones / Deliverables
Label | Description | Topics
M1.10 | Estimation of effective coefficients for impurity transport from kinetic modeling: Derivation of (D, v) maps for impurity transport in edge and pedestal regions considering 3D equilibria effects Reduced scope : reduced number of cases under consideration | 3, 7, 8
M3.1 | SOLEDGE3X and EMC3-EIRENE plasma backgrounds for ITER scenarios with and without RMPs Reduced scope : 3D workflow at risk. no validation on AUG and application for ITER | 3, 7, 8
M3.2 | ERO2.0 for ITER/W7-X: Simulations for full-W ITER and W7-X with 3D backgrounds finished Reduced scope : ERO2.0 simulations for ITER will be not completed. | 3, 7, 8
M4.3 | Application to ITER scenarios: implementation of the modelling in ITER baseline and hybrid scenario in order to assess the behaviour of W impurity in the steady-state phase for a large range of pedestal parameters. Reduced scope : Reduced range of parameters will be considered. Possibility of a postdoc with IO for completing this deliverable | 3, 7, 8

## Slide 17: TSVV-F 2027 Impacted deliverables
Impact the central goal of the TSVV to establish a hierarchy of multi-fidelity models for REs and disruptions
Delay coupled JOREK-DREAM simulations for ITER
Impact the modelling of benign termination simulations
Impact the RE beam scrape-off studies
RE wall damage studies
Reduced compliance with EUROfusion standard software requirements
Several applications in WP TE, WP DES and for ITER relying on DREAM parallelization and/or the JOREK-DREAM coupling would undergo delays or be forced to use reduced fidelity. This would in particular delay full validation for RE generation and RE benign beam termination models.
Topics: 4, 7 , 8
Deliverables & scope reductions
  Completion of the JOREK-DREAM coupling for novel RE generation calculations
  Parallelization of the DREAM code
    Required for DREAM standalone simulations with faster turnaround time and for efficient JOREK-DREAM coupled simulations
  Compliance of the CARIDDI and FIREWALL codes with EUROfusion standard software requirements - strongly affected
Codes impacted & Capability
  JOREK-DREAM: Missing ability to carry out RE generation calculations over long time scales in MHD quiet scenarios
  DREAM: Incomplete parallelization does not allow the same level of comprehensive physics studies
  CARIDDI and FIREWALL: Delayed / missing compliance with EUROfusion standard software requirements
-
-

## Slide 18: TSVV-G Physics of Burning Plasmas 2027 Impacted Deliverables
Label | Description | Topics
D.6 | Global gyrokinetic simulations of energetic-particle physics in JET, MAST-U, W7-X, JT60-SA, ITER, Stable Quasi-Isodynamic configuration , fusion plasmas. High beta regimes in stellarator plasmas assessing the KBM instability. Reduced scope : nonlinear simulations of reactor-size plasmas including turbulence may become impossible if the resources are reduced (ORB5, EUTERPE) | 5
D.7 | Studies of the transients and self-consistent back-reaction of the phase-space transport on fusion power and burn control using reduced-model framework. Reduced scope : studies of burn control and power deposition in fusion plasmas will not been carried out to a full extent if the resources are reduced (ATEP, LIGKA/HAGIS) | 7

## Slide 19: TSVV-H Reliable Prediction of Plasma Performance and Operational Limits in Tokamaks: 2027 Impacted Deliverables
Label | Description | Topics
WP1-2 | WP1 Integrating Modelling Workflow orchestration and module coupling framework - Integrate new IMASsified workflows within HFPS Reduced scope: It would not allow for the integration and test of all target reduced models based on NN in HFPS . Testing of SOLPSNN, EDGE2DNN and MISHKANN might have to be reduced to a single case. Without sufficient testing, no meaningful support for fast and accurate Core-Edge integrated simulations will be available for the other work-packages. This will also reduce our potential to collaborate with WPTE, for example with RT-01 on Neon seeded scenarios | 1, 3, 5, 7, 8
WP2.1 | WP2 key physics modules validation- High beta and energetic particle impact on transport Reduced scope: ATEP within HFPS will be coupled and validated, but not used to extrapolate towards JT-60SA and ITER. Priority will be given to model validation for ATEP, required before reliable extrapolation. Milestone dropped: One JT-60SA and one ITER high beta simulation stored on the gateway . Report on EP transport in ITER | 5, 7, 8
WP2.3-D2 | WP2 key physics modules validation- WP2.3: SOL-Core integration - Test the fast surrogate or simplified modules Reduced scope: Simplified edge models coupling and testing within ASTRA would not be performed within TSVV-H. No direct implementation in ASTRA of reduced edge models will be possible. Work to enable the modelling of XPR within HFPS will continue | 1, 3, 5, 7, 8
WP2.4-D2 | WP2 key physics modules validation- WP2.4: Pedestal modelling WP2.4-D2: Test resistive MHD calculations within integrated modelling Reduced scope: JET simulation with pedestal predicted by CASTOR (resistive MHD) would not be performed Impact the modelling of the pedestal. While it should be possible to test the ideal MHD with MISHKA and compare the prediction between the ETS and HFPS, it will not be possible to expand this work to resistive MHD. Impact the collaboration with the ENR on reduced model development for the pedestal and with the other related TSVVs. Note that, since the fusion performance is very sensitive to pedestal conditions, this effectively introduces a large uncertainty for any extrapolation of the fusion power in future machines (ITER, VNS, ARC, BEST etc.). | 3, 5, 8
WP4.D2 | WP4: Large scale validation WP4-D2: Demonstrate large-scale automated simulation execution, storage, and validation Reduced scope: The large-scale validation of TCV and WEST discharges will be reduced The large-scale validation program might be weakened, with reduced number of shots being considered, no edge modelling included and probably no pedestal modelling. An interpretive workflow to provide for sources and confinement calculation will still be developed, but it might not be possible to reach the level of maturity necessary for routine use. | 8

## Slide 20: TSVV-I Stellarator Optimization: 2027 Impacted Deliverables
Label | Description; | Topics
SD6.8 SD6.9 | SD6.8 : EMC3-EIRENE performance prediction in divertors with unpaired x-points SD6.9: Effect of edge optimization on divertor performance Dropped: the study of the effect of edge optimization on divertor performance with high-fidelity codes; | 6
SD2.3, SD2.4 | SD2.3 Interface SIMPLE-SIMSOPT to treat regions beyond LCFSSD2.4:Extension of SIMPLE to treat divertor region and evaluate wall losses Dropped: the interfacing of efficient orbit-following codes with optimization codes, with a reliable prediction of energetic particle losses on the walls; | 6
SD3.3 | SD3.3: W7-X configurations optimized for the generation of transport barriers Dropped : the application of newly developed topological tools to the study and optimization of internal transport barriers in stellarators and validation in W7-X; | 6, 8
SD7.2: | SD7.2: Characterized piecewise omnigeneous configuration space Dropped : the exploration of piecewise omnigeneous stellarator configurations, which offer the potential of simpler coil designs without compromising the confinement performance. | 6
SD7.4 | SD7.4: Divertor concept for a tokamak-QA hybrid Dropped the design of divertor concepts for a quasi-axisymmetric (QA) tokamak-stellarator hybrid. | 6
Risk : incorporation of divertor physics and alpha particle losses into stellarator optimization, and exploring the space of optimal stellarator shapes in order to ensure the lowest possible coil complexity.
Remaining 2027 Deliverables
  SD1.3 Free-boundary optimization with GVEC-SIMSOPT
  SD2.5 New 2D drift-kinetic solver for arbitrary E-fields
  SD6.5 Tradeoffs of physical properties in quasi-isodynamic (QI) configurations
  SD6.6 Different optimized divertor topologies for Stable Quasi-Isodynamic configuration (SQUID) configuration
  SD6.7 New optimized quasi-isodynamic (QI) configurations using reduced models for turbulence

## Slide 21: TSVV-J Stellarator core turbulence 2026 & 2027 Impacted deliverables
Label | Description; | Topics
D.FAST-TURBTRANSP (2026) | Rapid turbulence diagnostic tool based on an initial electrostatic turbulent transport database (Deliverable) Stellarator core turbulence database for W7-X based on flux-tube simulations (2026 Milestone M.IMAS-TURB-DB) Reduced scope: A turbulent transport database for multiple stellarator configurations and its translation to IMAS was foreseen. The configurations considered for the database generation will be reduced to a few newly designed ones and W7-X standard configuration, and their IMAS translation will be deprioritized. IMASification in stellarators is not as relevant for ITER as the IMASification of tokamaks. These were 2026 deliverables and milestones, but we will sacrifice them in order to advance on some 2027 ones during 2026, in particular D.HEAVY-Z-TRANSP for W7-X. | 6, 7, 8
D.HEAVY-Z-TRANSP | Comprehensive study of tungsten transport in reactor-relevant W7-X scenarios, stellarator reactor candidates from TSVV-I, and ITER with 3D perturbations Reduced scope: This deliverable is reduced solely to the evaluation of turbulent transport of W in W7-X, and its first results are brought forward to 2026. Optimized stellarator and ITER with 3D perturbations are precluded from this deliverable | 3, 6, 7, 8

## Slide 22: TSVV-K Neutral Particle Models: 2026 & 2027 Impacted Deliverables
Label | Description | Topics
D.7, 8, 9 (2026) | WP2- Develop high fidelity collisional-radiative models for H, D, T neutrals further, apply them to mixed fuel plasmas, and assess properties of charge-exchange neutrals Collisional radiative models (CRM) Reduced scope: Provision of at least 2 instead of 3 datasets for new/standalone collisional radiative model ModCR (and for PLOUTOS) including for hydrogen isotope containing molecules with resolution by vibrational (rotational) states for mixed species. Report on the significance of isotope effects and qualification of the uncertainties including those due to the missing/inaccurate A&M data Report on ModCR (with PLOUTOS data) verification against other codes (e;g. Yacora) and validation against one (instead of two) experiment (JET or PSI-2) | 1, 2, 7, 8
D.15, 17, 18, 19 | WP1- Establish a multi-fidelity model hierarchy for the physics of neutrals, ranging from first principles models to reduced representations, and integrate it into fluid and gyrokinetic edge turbulence simulations. Exploit synergies with TSVV-B and TSVV-C. Reduced scope: D15 Report on validity and accuracy of enhanced AFN model through rigorous comparison with EIRENE, incl. D-T simulations and integration of new fluid models into SpH (Spatially Hybrid) scheme advanced : no implementation of molecules into Advanced fluid neutrals (AFN) and fluid-kinetic hybridisation (FKH) to prioritise kinetic diffusion Monte-Carlo (KDMC) development. D17 : Report on implementation/verification of time dependent mode for reduced turbulence case in SOLEDGE3X-EIRENE, incl. corresponding STYX2.0 interface and documentation of proper parameter tuning D18 : Verified EIRENE module including simplified time dependent recycling model D19 : Technical demonstration of a 3D turbulent simulation of a medium size tokamak including full physics neutrals with SOLEDGE3X-EIRENE leveraging the EIRENE Open-MP parallelization layer and leveraging grid decoupling (coarser grid for neutrals) in collaboration with TSVV-B | 1, 2, 7, 8
D.20,22 | WP2- (2027) Develop high fidelity collisional-radiative models for H, D, T neutrals further, apply them to mixed fuel plasmas, and assess properties of charge-exchange neutrals Collisional radiative models (CRM) Reduced scope: D20: EIRENE release with consolidated Milestone Version of ModCR, including documentation but with the 2026 reduced scope for CRMs D21: Extended molecular database in EIRENE including T-T and D-T and report on application with SOLPS-ITER to i) JET-ILW T-T and D-T, and ITER; ii) JT-60SA H and D (if specific data available) | 1, 2, 7, 8

## Slide 24: Back-up slides

## Slide 25
 | Key Objectives/Focus of the 2026-2027 Work-Programme per TSVVs at full scale
A | Develop the capability to perform self-consistent, robust, and validated gyrokinetic simulations of L-H transitions, enabling accurate H-mode pedestal profile predictions. Gyrokinetic simulations of small/no-ELM regimes, transferability to future fusion devices, including ITER
B | Turbulent transport in the SOL with physics of neutrals, impurities, isotopes as well as PWI. Generalization to non-axisymmetric geometries
C | Particle/heat exhaust based on gyrokinetic equations under conditions relevant to a semi-collisional edge and SOL, physics of neutrals and impurities. Generalization to non-axisymmetric geometries
D | First-wall erosion, mixed-material formation, dust generation and transport, and fuel inventory as function of neutron damage. Enhanced models to simulate transients
E | W impurity distributions (sources, transport, screening) and impact on performance. Effects of 3D perturbations and ELM suppression on W impurity and seed impurity distributions in ITER
F | Disruptions, in particular in W-devices. model for runaway electron beam generation and losses, dynamics and mitigation to be integrated into modelling tools and nonlinear MHD
G | Mutual interaction of energetic particles, MHD modes, turbulence, and kinetic plasma profiles in tokamak and stellarator
H | Complete scenarios: breakdown to termination including metallic wall conditions (ITER). Model validation as well as code exploitation and deployment
I | Stellarator optimisation codes with enhanced speed and greater scope
J | Gyrokinetic turbulence codes in 3D magnetic and validation. Reduced turbulent transport models
K | Neutrals, first principles to reduced models and integration fluid and gyrokinetic edge turbulence simulation

## Slide 26: Ongoing assessment: programmatic consequences on cross-TSVV topics
Topic 1. SOL heat flux decay length, pedestal and L-H transition
Topic 2. Simulation of advanced regimes without ELMs by integrating : neutrals, boundary conditions, sheath coupling, impurities
Topic 3. Core-pedestal-SOL-wall workflow including 3-D effects (e.g. RMPs)
Topic 4. Disruption, RE and impact on the W wall at high current
Topic 5. Simulation of high beta plasmas and fast particle effect on confinement/stability
Topic 6. Stellarator core turbulence and optimization
Topic 7. Development and test of reduced models
Topic 8. Validation & Uncertainty Quantification: Enabling Physics Discovery

## Slide 27: Topic 1. SOL heat flux decay length, pedestal and L-H transition
Investigation of the SOL width on key parameters (current, magnetic field, power with realistic X-point geometry) in edge fluid turbulence codes (FELTOR, GBS, GRILLIX, SOLEDGE) & gyro-kinetic codes (GENE-X & GYSELA)
  heat flux decay length scaling to high current and validation against JET at high Ip=3-4 MA
  Delay in Validation neutrals + sheath models in TCV-X21 (GENE-X)
L-H simulation integrating SOL in the simulation domain (GENE-X, GYSELA, JOREK-GKG)
Development/coupling of KINDNESS kinetic neutral codes
Validation TCV-X23 reference case analysis (turbulence in high density regimes)
Evaluation of the turbulent transport of impurities in the edge plasma and simulations of D-T
Code evolution (FELTOR and GRILLIX, GENE-X) to handle 3D geometry (stellarator)
HFPS prediction of the pedestal height (AUG, JET): size, isotope effects and impurity to support ITER prediction
Impacts:
  TE, PWIE, STEL
  ITER-EUROfusion collaboration : “Physics Basis for ITER scenarios”
  ENR MOD/ Developing reduced turbulence transport models for the tokamak scrape-off layer
  ENR-MOD/ Pedestal Inference Engine (PIE)
TSVVs: A, B, C,H, K
Deliverables to be reduced in scope or dropped: on going analysis

## Slide 28: Topic 2. Simulation of advanced regimes without ELMs by integrating : neutrals, boundary conditions, sheath coupling, impurities
First principle (GENE-X, GYSELA, JOREK-GK) and integrated modelling on ITER Seeded baseline (no/small ELMs), X-point radiator (XPR) and quasi-continuous exhaust (QCE) regimes
  Multiple-scale characterisation of AUG QCE/EDA-H mode and JET no-/small-ELM pedestals
  Delay in studying the impact of impurities and validity of dilution models
studying coupled turbulence and neutral interaction
  Impact of isotope physics
Involved TSVVs: A, B, C, H, K
Impacts
  WPs : TE, SA
  ITER-EUROfusion collaboration:
    “Physics Basis for ITER scenarios”: ELM control and no ELMS scenarios with W wall
    Validation of HFPS in Neon seeding high performance JET DD and DT plasmas
TSVVs: A, B, C,H, K
Deliverables to be reduced in scope or dropped: on going analysis

## Slide 29: Topic 3. Core-pedestal-SOL-wall workflow including 3-D effects (e.g. RMPs)
Predicting erosion and migration in the ITER plasma in the presence of RMPs (SOLEDGE3X-ERO2.0 and EMC3-EIRENE+ERO2.0)
  W-source (erosion, migration) and transport in W machines, including effect of RMPs and extrapolation to ITER: core W estimate for ITER ?
study of W transport in reactor-relevant W7-X scenarios, stellarator reactor candidates from TSVV-I, and ITER with 3D perturbations
Extension TSVV codes towards 3D stellarator configurations from erosion to migration up to core impact
WPs Impacted: TE, PWIE, STEL
ITER-EUROfusion collaboration impacted: ITER-EUROFusion “Physics Basis for ITER scenarios”: ELM control and no ELMS scenarios with W wall
TSVVs: D, E, J, K
Deliverables to be reduced in scope or dropped: on going analysis

## Slide 30: Topic 4. Disruption, RE and impact on the W wall at high current
JOREK-DREAM coupling and in the parallelization of DREAM code for efficient RE calculation at high current
  Delay in addressing the highest risk for ITER high-current operation: simulation of the dependency of RE current on the pre-disruption plasma current. Importance of seed generation and losses vs avalanche multiplication effect (high current simulation)
compliance with EUROfusion standard software (CARIDDI and FIREWALL) that will impact code dissemination and users involvement
RE induced damages on W PFC wall: development of thermo-mechanical model with W (Geant4-MEMENTO-LSDYNA): vaporisation, melting , release of debris
WPs Impacted: TE, PWIE (delay in the validation)
ITER-EUROfusion collaboration impacted :
  “Physics Basis for ITER scenarios” : Disruptions
  disruption mitigation : strategy for benign termination of RE plasmas
  Runaway electron avalanche (RAE) behaviour and predictive model validation
TSVVs: D, F
Deliverables to be reduced in scope or dropped: on going analysis

## Slide 31: Topic 5. Simulation of high beta plasmas and fast particle effect on confinement/stability
global gyrokinetic simulations (ORB5/EUTERPE, GENE, GYSELA) of energetic-particle physics in EUROfusion experiments, JT60-SA, ITER, stellarator.
High beta regimes in stellarator plasmas assessing the KBM instability. At risk
integration simulation with realistic burning plasma sources to address the importance of memory effects and nonlinearities when fast particles, profiles and turbulence evolve
WPs Impacted: TE, SA, STEL
ITER-EUROfusion collaboration impacted:
  “HFPS improvements” : development of models for burning plasmas and models validated at high beta (electromagnetic effects)
TSVVs: G, H, I, J
Deliverables to be reduced in scope or dropped: on going analysis

## Slide 32: Topic 6. Stellarator core turbulence and optimization
predicted performance and validation on two experimental W7-X campaigns 2026-27
  “study of tungsten transport in reactor-relevant W7-X scenarios, and ITER with 3D perturbations”
  “Stellarator core turbulence database for W7-X based on flux-tube simulations”
  “Rapid turbulence synthetic diagnostic tool development based on an initial electrostatic turbulent transport database”
study of the effect of edge optimization on divertor performance with high-fidelity codes (EMC3-EIRENE)
coupling of efficient orbit-following codes with stellarator optimization codes
  Delay in the prediction of energetic particle losses on the walls
application of newly developed topological tools
  study and optimization of internal transport barriers in stellarators and validation in W7-X
exploration of piecewise omnigeneous stellarator configurations,
  simpler coil designs without compromising the confinement performance
WPs Impacted: STEL
Impact:
  Support Europe unique position in stellarator experiments , theory and design
  Maintain EU leadership
TSVVs: G, I, J
Deliverables to be reduced in scope or dropped: on going analysis

## Slide 33: Topic 7. Development and test of reduced models
reduced models development and validation for integrating the entire chain of processes involving tungsten — from erosion to migration (including pedestal effects) up to the impact on the core plasma
reduced model for Wall sputtering and reflection
reduced models development and validation for L-H transition
development and validation of reduced model to study the impact of impurities on turbulence in arbitrary geometry
reduced model development and validation for fast ion and burning plasmas
  Delay in Coupling and testing of the ATEP workflow in HFPS, to calculate the transport of fast ions
  Delay in Studies of the transients and self-consistent back-reaction of the phase-space transport on fusion power and burn control using reduced-model framework.
WPs Impacted: TE, PWIE, SA, STEL, DSO/WPAC : Digital twins, PDS, real time control applications
ITER-EUROfusion collaboration impacted: “Joint Development of plasma models” : HFPS improvement
Collaboration
  ENR-MOD/ Massive ASCOT simulations for fast ion tomographic reconstructions and surrogate model training
  ENR MOD/ Pedestal Inference Engine (PIE)
TSVVs: A, B, C, D, E, G, H, J, K
Deliverables to be reduced in scope or dropped: on going analysis

## Slide 34: Topic 8. Validation & Uncertainty Quantification: Enabling Physics Discovery
validation process across all TSVVs
synthetic diagnostic development and integration for interpretive simulations, e.g. HFPS + TWINTOK
Implementation of as strong validation strategy
  Define specific experiments to validate models
  Develop a dedicated validation pathway for first-principles codes
  Develop common validation metrics for integrated modelling
  Large multi-machine discharge databases or parameter scans around selected reference discharges
WPs Impacted: TE, SA, STEL, WPIE, DSO/AC: synthetic diagnostic, PDS, databases
ITER-EUROfusion collaboration impacted:
  “Joint Development of plasma models”: Analysis workflow for experimental data ; Use and validation models
TSVVs: A, B, C, D, E, F, G, H, J
Deliverables to be reduced in scope or dropped: on going analysis