## Slide 1: PMO and PSO roles … in more details
B. Meszaros, F. Vinagre, C. de Andres, J. Gafert, J. Liviu
Project Management Office
Information half day| 12 January 2021

## Slide 2: Role definition as of Management Chapter 4 of Grant Proposal…
The PMO responsibilities include:
Provide project support for planning and implementation by defining and ensuring the use of the appropriate processes;
Maintain and develop project management standards, providing the relevant tools and software, templates and standardize documents such as PEP and project charts;
Monitoring and control of project scope, and schedule of the grant agreement deliverables;
Coordinate communication across Work Packages, in particular with the Lead Beneficiaries;
Reinforce the standard quality through training of the project teams.
The PSO responsibilities include:
Ensure compliance with the project management policies and processes
Provide best practice advices and guidance, templates for common documents or processes
Support the PL ensuring support functions mainly in the preparation of the PEP, definition of the scope, schedule and budget and in the monitoring of project deliverables and use of resources in the WP.
Provide quality check of the project task reports following guidelines and templates from the PMO.
Support the PL in delivering the annual project technical report to the LB for submission to the PMU

## Slide 3: …and the details where the devil lies
Topic | Role of the PMO | Role of the PSO
Program Progress monitoring | 1. Monitor and ensure that WP/Campaign activities are within agreed schedule and scope (grant deliverables, WP high level milestones and high level project deliverables) 2. Report periodically to GA on status of grant deliverables 3. Follow up status of Grant deliverables | 1. Report progress to PMO on achieving high level milestones and high level deliverables
Project Progress monitoring | 1. Review information provided by PSO on the status of deliverables that contribute to the accomplishment of a grant deliverable 2. Identify critical issues, implementation risks and report to department heads and PM | 1. monitor WP progress in terms of all WP deliverables and milestones (in percentage terms) 2. Assist PL/TFL in organizing progress meetings and in using IMS 3. Provide periodic progress report to PMO (status of deliverables contributing to grant deliverables; critical issues, etc. ) 4. Monitor and update campaign participation requests and verify actual participation (visits) with the machine Host 5. Assist PLs/TFLs in creating the Annual Technical Reports and forward them to COs for compilation of the department WPs 6. Collect project deliverables reports and ensure that reports are approved in IDM, following PMU procedure, to enable payments.
Knowledge area: MONITORING

## Slide 4: …and the details where the devil lies
Topic | Role of the PMO | Role of the PSO
Budget management | 1. Issue guidelines on method of assigning values to deliverable, in consultation with PLs and ADMIN 2. Together with PLs identify items with the highest potential budgetary impact to assess single-point risks. (part of the outcome of the risk assessment) 3. Investigate, together with Admin, deviations above/below a given significance to determine if they have arisen due to financial and/or technical reasons – errors, delays, profiling, unplanned changes etc. and propose appropriate corrective action to be taken (ADMIN establish biannual “snapshot” financial reporting to identify variances with a level of significance and inform PMO). | 1. Assess if technical progress (according to time schedule) is in line with assigned financial resources 2. Inform PMO and ADMIN about any changes that may result in major deviations in the use of resources 3. Review periodically the status of pending deliverables and timely process deliverables to be withdrawn or cancelled.
Resource allocation (WP level) | n/a | 1. Assist the PL in the preparation of tasks in IMS 2. Oversee resources on the project level 3. Assist PL/TFL in updating the Project/campaign resource allocation
Knowledge area: BUDGET

## Slide 5: …and the details where the devil lies
Topic | Role of the PMO | Role of the PSO
Integrated schedule management | 1. Establish & maintain integrated schedule at programm level 2. Update of the integrated schedule with information received from WPs (via PSOs, SCPs) & Report; 3. Define, integrate and follow up of KPIs | 1. Provide information on WP schedules to PMO as required 2. Provide WP KPIs to PMO for integration
Project schedule management | 1. Define extent of project schedule reporting (i.e. which Ds and Ms, etc.) - and exchange format to be used by PSO (and SCP) 2. Communicate complete set of KPIs to WPs (as defined in the integrated schedule) | 1. Assist PL/TFL in creating and updating the project schedule and provide schedule information to PMO 2. Assist PL/TFL in keeping WP/Campaign schedule aligned with schedule of Grant deliverables and other KPIs
Knowledge area: SCHEDULE

## Slide 6: …and the details where the devil lies
Topic | Role of the PMO | Role of the PSO
Project PMP definition/ update | 1. provide PMP template 2. provide PM support to PL/TFL/PSOs 3. Follow up the updates of the PMPs 4. Ensure alignment of PMP with grant deliverables | 1. Assist PL in the preparation of the PMP 2. Inform the PMO about the progress as required
Annual Workplan definition/ update | 1. Oversee the alignment of individual WP schedules 2. Stay informed of the AWP. | 1.Assist PLs / TFLs in planning and drafting the Workplan document / update 2. Send finalised and approved input from PLs / TFLs to the PMU
Task Specification definition/ update | n/a | 1. Assist the PL in the preparation of the task specification
Knowledge area: SCOPE

## Slide 7: …and the details where the devil lies
Topic | Role of the PMO | Role of the PSO
Project Change Management | 1. Provide PCR template and process 2. Assess the PCR wrt. scope, schedule and resources (in consultation with Admin), prepare recommendation 3. Participate and present PCR assessment to PBs as change management board (TBD by process) | 1. Assist PL in creating PCRs and follow up of the change process 2. Provide required information to PMO
Configuration Management | n/a | n/a
Knowledge area: CHANGE
Topic | Role of the PMO | Role of the PSO
Document Storage & Access Control | 1. Create and maintain IDM structure 2. Administer permissions in IDM | 1. coordinate with IT-admin the IDM access of members within the WP (request access for newcomers, request closing access to those who leave) 2. Check (within respective WP) for compliance (of uploads, etc.) with established rules 3. Create detailed WP related folder structure (further to those defined by the PMO)
Documentation management | 1. Define review process for various types of documents | 1. Keep WP documentation in IDM up-to-date 2. Ensure that reviewers and approvers of documents of the WP are assigned according to PMO/PMU guidelines
Knowledge area: DOCUMENT

## Slide 8: …and the details where the devil lies
Topic | Role of the PMO | Role of the PSO
Project Reviews / Assessment | 1. Assessment of WPs in terms of established rules and processes | 1. Assist PL to ensure compliance of PMP with established rules 2. Oversee that established procedures / guidelines are followed (within WP)
Deliverables Review (formal) | 1. Oversee deliverables compliance with established rules | 1. Ensure compliance of all WP deliverables with established rules (submitted for approval to the PL) following guidelines and templates from the PMO
Knowledge area: QUALITY
Topic | Role of the PMO | Role of the PSO
Program Risk management | 1. Collect, review the risks on a programmatic level ensuring mitigating strategy is in place and applied (critical risks included in the Grant Agreement) | 1. Report to PMO on any delays / unforeseen events that may jeopardise the overall progress of the WP
Project risk management | 1. Provide standard templates for risk management 2. Coach PSOs in providing the risk register in a suitable form | 1. Support PL /TFLs in establishing and maintaining the risk register following the template provided by PMO 2. Support PL /TFL in reviewing and updating the risk register 3. Provide required information to PMO according to the agreed interface format
Knowledge area: RISK

## Slide 9: …and the details where the devil lies
Topic | Role of the PMO | Role of the PSO
Communication | 1. Communicate methods, (software) tools & techniques for successful implementation of the WPs | 1. Keep PMO informed about interfaces with other WPs (Campaigns) and potential issues 2. Promote internal communication within the WP and be the contact point towards the participating labs
Training | 1. Deliver training to WP Team members, PL/TFL, PSO, COs, SCP in the use of tools, project management, procedures and standards established by the PMO 2. Review training effectiveness (lessons learnt) 3. Identify in collaboration with PSOs the areas/ needs and map out development plans for WP teams | 1. Identify training areas/ needs for the WP team
Knowledge area: COMMUNICATION

## Slide 10: Questions